## Traffic Speed Sign Project
Overall Sign # | Amount from this vendor | LED FONT Size 12" or 18" | Manufacturer | Model | DOT Warehouse Stock # | Cost | Serial Number | Requisition # | Brief Description | PO # | Originally Shipped to: | Date Received | Status | Receipted? | Invoice # | Amount$$ | Sent to Danielle for Payment | Danielle Paid in WkDay | Location of Install | Sign # (from SFB Site Visit / Installation details Form | Baker Install Complete | Total Install Complete
Summary
1 | 1 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050021 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 | 121750 | 2023-07-12 | 2023-07-20
2 | 2 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050022 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
3 | 3 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050023 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
4 | 4 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050024 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
5 | 5 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050025 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
6 | 6 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050026 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
7 | 7 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050027 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
8 | 8 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050028 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
9 | 9 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050029 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
10 | 10 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050030 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
11 | 11 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050031 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
12 | 12 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050032 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
13 | 13 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050033 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
14 | 14 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050034 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
15 | 15 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050035 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
16 | 16 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050036 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
17 | 17 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050037 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
18 | 18 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050038 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
19 | 19 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050039 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
20 | 20 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050040 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
21 | 21 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050041 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
22 | 22 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050042 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
23 | 23 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050043 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
24 | 24 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050044 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
25 | 25 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050045 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
26 | 26 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050046 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
27 | 27 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050047 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
28 | 28 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050048 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
29 | 29 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050049 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
30 | 30 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050050 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
31 | 31 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050051 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
32 | 32 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050052 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
33 | 33 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050053 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
34 | 34 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050054 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
35 | 35 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050055 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
36 | 36 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050056 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
37 | 37 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050057 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
38 | 38 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050058 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
39 | 39 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050059 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
40 | 40 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050060 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
41 | 41 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050061 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
42 | 42 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050062 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
43 | 43 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050063 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
44 | 44 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050064 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
45 | 45 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050065 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
46 | 46 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050066 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
47 | 47 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050067 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
48 | 48 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050068 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
49 | 49 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050069 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
50 | 50 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050070 | RQ-00004618 | Originial Order of 50 | PO-00006250 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN20811 |  | 2023-07-12 | 2023-07-20
51 | 51 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050101 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 | 73050 | 2023-07-12 | 2023-07-20
52 | 52 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050102 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
53 | 53 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050103 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
54 | 54 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050104 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
55 | 55 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050105 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
56 | 56 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050106 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
57 | 57 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050107 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
58 | 58 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050108 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
59 | 59 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050109 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
60 | 60 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050110 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
61 | 61 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050111 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
62 | 62 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050112 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
63 | 63 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050113 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
64 | 64 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050114 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
65 | 65 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050115 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
66 | 66 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050116 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
67 | 67 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050117 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
68 | 68 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050118 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
69 | 69 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050119 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
70 | 70 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050120 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
71 | 71 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050121 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
72 | 72 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050122 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
73 | 73 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050123 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
74 | 74 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050124 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
75 | 75 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050125 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
76 | 76 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050126 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
77 | 77 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050127 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
78 | 78 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050128 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
79 | 79 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050129 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
80 | 80 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23050130 | RQ-00004618 | 2nd order (60% increase) | PO-00006256 | Baker Warehouse in DM | 2023-05-31 | Received | Yes, on 7/6/23 for 5/31/23 | SIN0810 |  | 2023-07-12 | 2023-07-20
81 | 81 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060071 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 | 73050 | 2023-07-12 | 2023-07-20
82 | 82 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060072 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
83 | 83 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060073 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
84 | 84 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060074 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
85 | 85 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060075 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
86 | 86 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060076 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
87 | 87 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060077 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
88 | 88 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060078 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
89 | 89 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060079 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
90 | 90 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060080 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
91 | 91 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060081 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
92 | 92 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060082 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
93 | 93 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060083 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
94 | 94 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060084 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
95 | 95 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060085 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
96 | 96 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060086 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
97 | 97 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060087 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
98 | 98 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060088 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
99 | 99 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060089 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
100 | 100 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060090 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
101 | 101 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060091 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
102 | 102 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060092 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
103 | 103 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060093 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
104 | 104 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060094 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
105 | 105 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060095 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
106 | 106 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060096 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
107 | 107 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060097 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
108 | 108 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060098 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
109 | 109 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060099 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
110 | 110 | 12" | TrafficLogix | EV12FMEYL-SOLLA | #880-800010 | 2435 | 23060100 | RQ-00004779 | 3rd order (30 more units) | PO-00006440 | Econolite Warehouse in Ankeny | 2023-06-20 | Received | Yes, on 7/6/23 for 6/20/23 | SIN21069 |  | 2023-07-12 | 2023-07-20
111 | 1 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 | 195278 | 2023-07-12
112 | 2 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
113 | 3 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
114 | 4 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
115 | 5 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
116 | 6 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
117 | 7 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
118 | 8 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
119 | 9 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
120 | 10 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
121 | 11 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
122 | 12 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
123 | 13 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
124 | 14 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
125 | 15 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
126 | 16 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
127 | 17 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
128 | 18 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
129 | 19 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
130 | 20 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
131 | 21 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
132 | 22 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
133 | 23 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
134 | 24 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
135 | 25 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
136 | 26 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
137 | 27 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
138 | 28 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
139 | 29 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
140 | 30 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
141 | 31 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
142 | 32 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
143 | 33 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
144 | 34 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
145 | 35 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
146 | 36 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
147 | 37 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
148 | 38 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
149 | 39 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
150 | 40 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
151 | 41 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
152 | 42 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
153 | 43 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
154 | 44 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
155 | 45 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
156 | 46 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
157 | 47 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
158 | 48 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
159 | 49 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
160 | 50 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | Original Order of 50 units | PO-00006251 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266610 |  | 2023-07-12
161 | 51 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 | 58583.4 | 2023-07-12
162 | 52 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
163 | 53 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
164 | 54 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
165 | 55 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
166 | 56 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
167 | 57 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
168 | 58 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
169 | 59 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
170 | 60 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
171 | 61 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
172 | 62 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
173 | 63 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
174 | 64 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
175 | 65 | 18" | Carmanah/MoboTrex | SPEEDCHCK-18 | #880-800020 | 3905.56 | ? | RQ-00004620 | 2nd Order (15 of the 60%) | PO-00006257 | Baker Warehouse in DM | 6/27/2023 +/- Baker | Received Ames 7/7/23 | Yes, on 7/11/23 for 6/27/23 | 266611 |  | 2023-07-12
176 | 1 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2266 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 | 80257.5 | 2023-07-13
177 | 2 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2267 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
178 | 3 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2268 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
179 | 4 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2269 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
180 | 5 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2270 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
181 | 6 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2271 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
182 | 7 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2272 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
183 | 8 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2273 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
184 | 9 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2274 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
185 | 10 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2275 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
186 | 11 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2276 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
187 | 12 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2278 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
188 | 13 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2279 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
189 | 14 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2280 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
190 | 15 | 18" | Stalker | 200-1318-00 18" PMG w/Traffic Analyst | #880-800030 |  | 2361 | RQ-00004637 | 1st order (15 of 60%) | PO-00006462 | Baker Warehouse in DM | 6/22/2023 at Baker | Received Ames 7/7/23 | Yes, on 7/13/23 for 6/22/23 and again on 7/20/23 for 6/22/23 (RC-00014175) | 421240 |  | 2023-07-13
Group 3 | Line 1 | 18' Poles | General Traffic | 15 |  | 441 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 | 38882 | 2023-07-13
| Line 2 | 16' Poles | General Traffic | 15 |  | 391 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 3 | Helical Footing | General Traffic | 10 |  | 557 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 4 | Anchor Bolts Kit (Conc) | General Traffic | 6 |  | 22 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 5 | Anchor Bolts Kit (Helical) | General Traffic | 10 |  | 48 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 6 | Ped Cap | General Traffic | 60 |  | 19.5 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 7 | Ped Collar | General Traffic | 60 |  | 66 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 8 | Ped Base | General Traffic | 60 |  | 172 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 9 | 13' Poles | General Traffic | 15 |  | 318 |  | RQ-00004631 | Additional 60% | PO-00006254 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/6/23 for 6/15/23 | 23373 |  | 2023-07-13
| Line 1 | 15' Poles | General Traffic |  |  | 367 |  | RQ-00004631 | Additional 60% | PO-00006255 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23374 | 5505 | 2023-07-13
| Line 1 | 18' Poles | General Traffic | 25 |  | 441 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 | 115220 | 2023-07-13
| Line 2 | 16' Poles | General Traffic | 25 |  | 391 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 | All photos and | 2023-07-13
| Line 3 | Helical Footing | General Traffic | 100 |  | 557 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 | Insurance Cert | 2023-07-13
| Line 4 | Anchor Bolts Kit (Conc) | General Traffic | 10 |  | 22 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 | Are in this | 2023-07-13
| Line 5 | Anchor Bolts Kit (Helical) | General Traffic | 100 |  | 48 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 | Receipt | 2023-07-13
| Line 6 | Ped Cap | General Traffic | 100 |  | 19.5 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 |  | 2023-07-13
| Line 7 | Ped Collar | General Traffic | 100 |  | 66 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 |  | 2023-07-13
| Line 8 | Ped Base | General Traffic | 100 |  | 172 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 |  | 2023-07-13
| Line 9 | 13' Poles | General Traffic | 25 |  | 318 |  | RQ-00004626 | Original Order | PO-00006262 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23371 |  | 2023-07-13
| Line 1 | 15' Poles | General Traffic | 25 |  | 367 |  | RQ-00004626 | Original Order | PO-00006261 | Baker Warehouse in DM | 2023-06-15 | Received | Yes, on 7/13/23 for 6/15/23 | 23372 | 9175 | 2023-07-13
Baker | Line 1 | Install 1 pole (based on 4 per day) |  |  |  | 1905.235

## Accounting Codes
Cost Center: | 6310
Business Unit | 631085
Function Code: | 781 | Traffic Signs
Project # | NHSN-000-T(275)--2R-00
Spend Category | 5780 | Traffic Warning Devices
Spend Code:
Must Use "Work Bench" to pay