Pre-Installation Steps for Speed Feedback (SFB) sign

(Draft Dated 9/22/23 v9)

District (Traffic Tech):  Receive an inquiry from a city.  Confirm they are eligible:

______ Is the location(s) on a Primary Highway? (Excluding Interstates & Freeways)

______ Is the City’s population between 1,000+/- & 10,000+/-?

______ Are they willing to take ownership and maintain sign(s) after install?

District (Traffic Tech):  If “Yes” to all 3 above, schedule a site visit with City Representative.

_____ e-mail them a blank TCD (SFB Specific) form with added language about ownership and maintenance responsibilities or send them to the website form here:                                                                     https://iowadot.gov/traffic/Speed-Feedback-Signs

_____ Ask City where they would like them.  If no preference, DOT recommends at 1st speed reduction.

_____ Complete the ‘Site visit / Installation details’ form for each location. https://iowadot.gov/traffic/Speed-Feedback-Signs

_____ Scan in the above mentioned form(s) and e-mail to ron.mcdaniel@iowadot.us in TAS along with a signed TCD permit application.  Include a map showing all the proposed locations.

_____ Confirm with local garage that they will hang the SFB and Static Speed Limit sign on the pole.

_____ Order any Static Speed Limit Signs from Sign Shop (if necessary).  Have delivery to local garage.   Charge to NHSN-000-T(275)--2R-00).

TAS:   Receive: 1) TCD permit, 2) Site visit / Installation details, and 3) Map attachments from District:

_______ (Ron & Willy) Confirm application meets the criteria and is signed by City (Electronic or   signed/scanned).

_______ (Ron) Review the TCD Permit and forward to State Traffic Engineer for signature.

_______ (Chris) Return a signed copy to Ron, Brad & Traffic Tech.

_______ (Brad) Add location to TCD Database & Statewide SFB map (color code as “pending” or “installed”)

_______ (Ron/Willy) Add information to DOT excel spreadsheet in Sharepoint.  (much of this info can be in the GIS layer, but keeping track of allocated inventory will be important.  (Willy & Ron to work on details of this).

TAS:  Once TCD has been approved, proceed to enter a work order into “Smart Sheets” to get Baker Electric to install the Footings/Base/Poles. (The contractor’s price to install assumes they can do 4 locations in one day-trip.)

- Description:  	Town, Route/Direction, Speed Limit, GSP Coordinates

- Sign Font Size:  	12” or 18”

- Sign vendor: 	Traffic Logix (12”), Carmanah (18”) or Stalker (18”)

- Length of Pole:  Copy from application (13’, 15’, 16’, or 18’)

- Install Pole only? Or do we need contractor to hang SFB sign also (usually, DOT Maintenance will hang SFB sign and static sign).  In some cases we can ask Econolite/Baker to install the SFB.

TAS:  Using the “Procurement Support” section in WorkDay, create a requisition for the warehouse to ‘pick & deliver’ SFB signs to the nearest DOT garage to where the signs will be installed.  See Route Truck and monthly calendar for “cut-off” dates for each route.

TAS:  Send an e-mail to the DOT Maintenance Supervisor(s) for the area(s).  This is giving them a heads up that:

- A contractor will be in the area within a month (or two) to install the footings/base & pole.

- Static Speed Limit sign(s) (if being replaced) are being sent to their garage (ordered by Traffic Tech).

- The SFB sign and solar panels will be dropped off at their garage by DOT Delivery truck.

- After poles are installed, another e-mail notice will be given.  At that time, DOT sign crews can be dispatched to: hang the SFB sign, connect the solar panels, install the static speed limit sign and remove the old post/sign.

- Include a set of instructions on how to put together the SFB sign and solar panels.

TAS:  Tracking/Project Management.  Keeping good records on installation dates in the DOT spreadsheet will be important and useful for ownership and warranty questions.  Also, a future research effort will need to know when each location is fully operational.  Attend bi-weekly coordination calls (Every other Tuesday at 9am).

TAS:  After Pole/Base/Footing installation has been completed, send 2nd e-mail to the DOT Maintenance Supervisor and Traffic Tech.  Tell them the pole is available to have the SFB sign/solar panels and Speed Limit signs installed at their convenience.

District (Maintenance Supervisor):  When you have possession of both signs (SFB sign/solar panel & new static speed limit sign (if applicable), schedule your sign crews to install the signs.

After installation and operational, please notify Ron McDaniel (ron.mcdaniel@iowadot.us) & your Traffic Tech.

Owner’s Manuals: https://iowadot.gov/traffic/Speed-Feedback-Signs

TAS:  Update DOT Spreadsheet (on Sharepoint) with install date & notify Hossein with locations, placement date & operation start dates.

District (Traffic Tech):  Notify the city that the installation is finished and that the signs are now theirs to own and maintain. Include copies of the owner’s manual & warranty information found here: https://iowadot.gov/traffic/speedfeedbacksigns