## Slide 1: Iowa ABC Demonstration Project US 6 over Keg Creek
IOWA DOT / InTRANS ABC WORKSHOP
May 2014

## Slide 2: Background
SHRP2 / HNTB – R04 Research Team needed to demonstrate ABC modular design concept for typical multi-span stream crossings – a common rural bridge replacement.
Proposed a demonstration project in Iowa.
Successful project may pave the way for developing national ABC standards.
Keg Creek is 1st generation bridge in Iowa
where bridge is completely modular.
Notes: Previous speakers already discussed the scope of SHRP2 – R04

## Slide 3: PROJECT LOCATION
US Highway 6 Bridge over Keg Creek
6 miles east of Council Bluffs, IA
Rural Location - 3900 AADT with 9% Trucks
22 Mile Detour (13 miles out-of-distance travel)
Detour
US 6
I-80

## Slide 4
EXISTING BRIDGE
180’ x 28’-0 Continuous concrete girder bridge
Built in 1953
3 spans 53’6”,73’,53’6”
Moderate sized, typical rural crossing
Small, meandering stream
Narrow bridge width on primary road system
Sufficiency rating = 33

## Slide 5: Why Keg Creek?
Typical rural, moderate size stream crossing in Iowa. Indicative of many bridges throughout the mid-west and country. SHRP2 looking to standardize ABC design plans.
Detour: 22 mile detour less desirable for traveling public over 4 to 6 month period versus 2 week ABC period.
Funding Schedule: Keg Creek already programmed for 2011 construction.

## Slide 6: Why Keg Creek?
Size of bridge favorable for pilot project in term of cost.
Low AADT = ideal for demonstration site.
Narrow existing bridge width allowed for drilled shaft foundation construction prior to bridge closure (outside of ABC).
Bridge geometry: 0 degree skew and flat grade.

## Slide 7: Project Data
Design: HNTB (M. LaVoilette, B. Sivakumar, F. Hubbard, and K. Price)
Owner: Iowa DOT (D. Evans – Design Review, B. Flippin & G. Feazell)
Testing: ISU (M. Rouse, B. Phares, D. Hartwell, D. Wood, and T. Wipf)
Contractor: Godbersen-Smith $2,658,823 (7 bidders from $2.66M to $3.99M)
Unit cost: $231 per sq.ft. (bid price)
vs. $124 per sq. ft. (estimated for conventional CIP)

## Slide 8: Project Data
Contract period: Fall 2011 Construction
  Phase 1: Drilled shaft installation ( 9 working days )
  Phase 2: ABC Period (14 calendar days of road closure with Traffic Detour)
  Phase 3: Revetment, grading, and flumes ( 20 working days )
Incentive/Disincentive on 14 days ABC: $22,000 / day
ABC approximate start date: 9/19/11 (actual 10/17/11)
SHRP2 funds: $250,000 (M. Starnes – Program Officer)
HFL funds: $600,000 or 20% (M. Huie – Program Coordinator)
UHPC Cost: $5000 / cu. yd. x 33 cu. yd = $165,000

## Slide 9
Project Innovations
Precast modular deck system
  Precast Module = 8.5” HPC slab casted on 2 steel I-beams (RSB W30x99)
Precast pier columns & bent caps
Precast abutment footings & wings
Precast approach pavement slabs
Semi-integral abutments
UHPC joint between modules

## Slide 10
First bridge in US with full, moment-resisting UHPC joint at the piers.
Grouted couplers for column connection to pier cap and drilled shafts
Structural Health Monitoring System
Barriers placed on superstructure module before erection
SCC used to improve consolidation and increase the speed of construction for abutment piles.
Use of fully-contained, flooded backfill
Project Innovations

## Slide 11: Proposed Bridge Geometry
204’-6 x 44’ Steel Modular Bridge
3 span: 67’-3,70’-0,67’-3
0 degree skew
Relatively flat profile grade line on straight road
Simple geometry allows for replication of units
  Same girder length and shear studs used for all spans and all units
  Un-cambered girders (choice of contractor)
2% deck slope from centerline with no parabolic crown

## Slide 12: PROJECT SITE - RURAL
N

## Slide 13: FABRICATION
Precasting: precast plant per Standards Specs and Materials IM 570 “Precast & Prestressed Concrete Bridge Units”.
Godberson-Smith elected to self perform casting on site as allowed per “Alternate Site Casting” notes provided in project plans.
Site casting was a large cost-savings for project
HPC with 5,000 psi concrete except drilled shaft
Mild epoxy coated steel reinforcing

## Slide 14: Iowa Bridge Farm (Self Performing Modular Casting)
TEMPORARY STREAM CROSSING FOR PRECAST DELIVERY

## Slide 15: Precast Substructure Components Casting
Cast cap in
channel area
168 kips pier cap weight
4 ft wide square columns casted vertical
52 kips
Abutment wings
and
footings

## Slide 16: Superstructure Modules –Structural Steel Assembly
Temporary bolting at
Pier bents for deck casting
Falsework for
Modular Deck Casting
Girders assembled on bents with diaphragms bolted

## Slide 17: Superstructure Modules Deck Forming
Modular Deck
Backwall
Connection over Pier
Formed Blockouts

## Slide 18: Deck Concrete Placement

## Slide 19: Precast Approach Slabs
Traditional CIP – 4 units each end of bridge
Double Reinforced Mat
Sleeper Slabs
Form slab edge around barrier end

## Slide 21: PIER DETAILS
LONG SPAN CAP
EPOXY COUPLERS
FILLED WITH GROUT
CAST
VOID

## Slide 22
Pier Connection Details
NON-SHRINK
BEDDING GROUT
EPOXY COUPLERS
FILLED WITH GROUT

## Slide 23
  Cont. reinforced concrete abutment footing
  Corrugated metal pipe to form pile pockets
  H-piles with shear studs or anchor rods
  SCC to fill pile pockets; high early strength
  Temporary support of backwall until SCC reaches 3000 psi
Abutment Details

## Slide 24: ABUTMENTS DETAILS
WING UNIT
ABUT STEM
PILE POCKET
SCC POUR

## Slide 25: ABUTMENTS DETAILS
SUSPENDED BACKWALL
MODULE
2” thermal
gap

## Slide 26: Modular Superstructure Details
6 modules per spans
Same girder lengths for each module

## Slide 27: DECK MODULE DETAILS
Hairpin rebar
Barrier rail prior to erection
Notice small development
UHPC
5 longitudinal UHPC joints

## Slide 28: CONTINUITY CONNECTION OVER PIER
FIXED
EXP.
Steel key
Single sole plate on laminated bearing pads detail at all locations
This pier connection detail does not provide any margin of error in a ABC setting.

## Slide 29: Post-Tensioning Retrofit

## Slide 30: Drilled Shaft Construction (Phase 1)
Location of drilled shaft is critical because of limited tolerance of pier placement
Typ. shaft tolerance is 2” or 3” per CIP Std Specs….. FOR THIS CASE 1” TOLERANCE.
Double template for connecting shaft dowels to the column couplers is a MUST!
Dowels for
Splice coupler connection
Drilled Shaft location allows for work under traffic

## Slide 31: 14-Day ABC Timeline – Phase 2 (as proposed by the Contractor)
Actual ABC period: Oct. 17 – Nov. 1
(OPEN TO TRAFFIC NOV. 2)
critical path items
went slower than expected

## Slide 32: Day 1 Oct. 17
PROTECT DRILLED SHAFT
PROTECT PIER CAPS

## Slide 33: Day 3 – Oct. 19
Drive Pile!
Move
Pier Caps

## Slide 34: Day 4 – Oct. 20 Column Assembly
Cutoff dowels
and shim plates
Add non-shrink bedding
grout
Bedding grout should be slightly overfilled and crowned
52 kips

## Slide 35: Day 4 , Oct. 20 - Column Assembly
Removal of bottom form with rubber coupler plugs
Columns need to be match marked for placement

## Slide 36
Mid-afternoon contractor done with column erection ~ 1 hour / column
Precast Column Erection

## Slide 37: Bedding and Coupler Grouting
Coupler Grouting
Procedure is critical! Workers need to be trained and supervised by manufacturer.
Sponge rubber
bedding grout dam for retention

## Slide 38: Temporary Abutment Supports
Contractor casted high early strength bearing pads after pile driving

## Slide 39: Day 5 Oct, 20 Abutment / Wing Erection
93 kips
26 kips

## Slide 40: Day 5 – Oct. 21
3 crane erection sequence went well

## Slide 41: SCC – Abutment Pile Pockets
Cast SCC
ASAP for cure time

## Slide 42: Day 6 – Oct. 22
168,000 LBS (84Ton)
Largest Iowa precast lift.
Used typical embedded P/S strand details for lifting.
Cap Beam Erection & Assembly

## Slide 43
Cap Beam Erection & Assembly
This was certainly easy! This could be utilized for 4 span or larger bridge. Access in the stream channel was key!

## Slide 44: Superstructure Module Transport
Day 8 – Oct. 24
1 week into closure period. Erecting superstructure modules.

## Slide 45: Superstructure Module Erection
69-80 kips
102-112 kips
Exterior modules had to be carefully rigged for a balanced lift.
Lifting points attached to top flange of steel girders.
2 crane pick

## Slide 46
Superstructure Module Erection

## Slide 47: Module Assembly
Module deck design should minimize reinforcing to avoid
interferences

## Slide 48: Deck Joint Reinforcing, Bolting and Forming – Days 10 & 11
Lots of joint forming
Bolting modules over pier

## Slide 49: Deck Joint Reinforcing, Bolting and Forming – Days 10 & 11
Joint rebar =
$$ labor
Epoxy coating can be damaged
Need to minimize rebar congestion

## Slide 50: Flooded Backfill System – Days 10 & 11

## Slide 51: Precast Approach Preparation Days 11 & 13
35 kips
Subgrade surface needs to be level and well compacted

## Slide 52: Precast Approach Slab Placement – Days 11 & 13
31-37 kips
20’ approach panels
4 panels / end
Outside panels were formed to fit around wing end section

## Slide 53: UHPC JOINT POUR – DAY 12
UHPC MIXING REQUIREMENTS ARE SPECIFIC AND CONTROLLED BY SPECIAL PROVISIONS.
STEEL FIBERS
PRECISION INGREDIENTS
DUCTAL BAG MIX

## Slide 54: UHPC Joint Prep – Day 12
SSD Precast
Edge
at longitudinal joints
Saturated surface dry precast surface.
Textured edge of precast is ideal, but unable to sandblast.
Application of bonding agent (Rezi-Weld 1000) for bonding UHPC to precast edge for Transverse Joints.
Recommend using stainless steel bars and sandblasting precast edge.
Bonding agent applied

## Slide 55: UHPC Placement – Day 12
Transport UHPC with buggy
UHPC is very flowable. No voids.
Provide cap forms for curing
UHPC is environmentally sensitive.
Heat accelerators can be used.
Grinding after 10ksi is verified.
Cap forms
Flowability
Motorized buggy

## Slide 56: Day 15 – POST-TENSION OVER PIERS
48 Post-tension locations:
(4) rods per module stressed simultaneously to a min. 70 kips per rod

## Slide 57: Day 16 – Nov. 1
2 days over ABC
Finish bridge deck grinding/grooving.
Guardrail placement
Shoulder panel & ML PCC paving (w/ M-mix)
Paint lines
ISU installing Health Monitoring Hardware
Bridge can be opened to traffic when UHPC has 15 ksi strength. Can occur in 3 to 4 days.
PROFILOMETER
Deck Grinding for profile and smoothness of joints.

## Slide 58: Completed Bridge – Open Nov. 2

## Slide 59: Conclusions
ABC modular design concept was successfully demonstrated, but there were some challenges along the way.
Post construction review identified problem areas, as expected, and provided recommendations for improvements which are documented.
As the result of this project (and other past ABC projects), Iowa DOT gained a better understanding of risks and benefits associated with ABC and is developing ABC policy.
Notes: I thought about including lessons learned but there is enough for an entire presentation.
Challenges:
Buy America waiver for steel fiber
Lifting pockets
Field casting of UHPC
Field weld

## Slide 60: Project Website
http://www.iowadot.gov/us6KegCreek/
Questions?

## Slide 61
Time Lapse Construction

## Slide 62
Following Slides for Discussion

## Slide 63: Precast Abutments & Wings
Holes in abutment stem for anchors
Pile pockets voids
Cheek wall integral with abutment
Wing wall w/ barrier casted previous to setting wing.

## Slide 64: Precast Columns
Tie rebar cage w/ steel template for dowel alignment with epoxy couplers
Cast concrete column vertical with template secured to top of column
Proper bracing
Bracing
Steel
Guys
Steel template is
CRITICAL!!!!

## Slide 65: Precast Column to Shaft Connections
Need to fabricate column form with proper hole alignment
Column bottom form
RUBBER PLUGS TO PREVENT CONCRETE INGRESS
REMOVE FORM AND RUBBER PLUGS JUST BEFORE SETTING COLUMNS

## Slide 66: Day 4 – Oct. 20
Dayton-Superior “Sleeve-Lock Grout Couplers” with S-L grout
Hand pump as recommended by D-S. (no backup pump)
Do not start grouting until bedding grout has cured. Wait 12 hours
Grout the bottom port. This will fill up bottom dowel chamber
Grout will push out top. Install top plug while continuing grouting then install bottom plug
Recheck and top off top plug
COUPLER GROUTING
CRITICAL ACTIVITY - ABC

## Slide 67: Column Installation Lessons Learned
This is a critical ABC activity.
Properly prepare and cure grout bedding
  Overfilling the grout slightly
  Provide a bedding grout dam
  Curing the bed grout a proper time
Have extra pumps and mixers available
  Paddle mixers on-site our helpful.
Project inspector must be on-site for bedding and coupler grouting activities. THIS IS A MUST.
This method of construction for piers can be feasibly used in Iowa to build multiple span bridges.

## Slide 68: DECK MODULE DETAILS

## Slide 69: DECK MODULE DETAILS
Pick point leaves slab void
Pick point
detail
Drain

## Slide 70: Modular Deck Design Lessons Learned
Need to reduce steel congestion in precast corners and joints
Need to revisit barrier closure pour reinforcing
Need to revisit the location of the lifting points in exterior modules.
Need to rethink the configuration of the lifting attachments and the formed block-outs.
Need to change overhang diaphragms in end span modules.

## Slide 71: Day 11 – Oct. 27 More Rebar
LOTS OF JOINT REBAR = LOTS OF LABOR
EPOXY COAT DAMAGE
STEEL CONGESTION!!

## Slide 72: Approach Slab Lessons
Backfill process will be on critical path on 14 day ABC schedule. (Can’t backfill until modules placed)
This will make it difficult to pour all UHPC on the same day for deck and approach slabs.
Contractor installed West precast approach slabs on day 13. NOT GOOD!
Contractor suggested using traditional cast-in place approach with a m-mix pavement would probably speed along the process.

## Slide 73: UHPC JOINT PERFORMANCE
Several bridge projects and some research testing projects have been conducted with UHPC being cast in the longitudinal joints
  Ben Graybeal at Turner Fairbanks tested a series of full scale 6” joints casted between deck panels.
  With proper precast surface preparation, UHPC casted joints have preformed well causing failure to occur in similar fashion as traditional decks.
  UHPC has enhanced bonding mechanism to concrete and rebar
  UHPC has low shrinkage and high compressive strengths from 14 ksi to 28 ksi.
  UHPC also contains 290 ksi fibers; capable of resisting tension.

## Slide 74: HOW WILL JOINT UHPC PERFORM IN A TRANSVERSE JOINT?
The transverse joint over the pier is a region of high direct tensile loading in a bridge slab with continuity.
To our knowledge, this had not been a subject of research for UHPC to date.
ISU conducted a full scale module test to research the UHPC transverse joint capabilities.
  This was conducted after the letting, but before the bridge construction.
  To obtain information on long-term serviceability and fatigue resistance (1,000,000 million truck cycles).
  Ultimate load capacity of 1 module over the pier
Other research at ISU
  Post-construction, ISU is researching the bonding characteristics of UHPC in direct tension to various surface substrates.

## Slide 75: WHAT DID WE FIND OUT FROM TESTING?
Under service II loading, the strain gages embedded in the UHPC joint and precast and surface mounted on the specimen measured significant displacements.
  Indication the UHPC is debonding at the interface of the precast
  This means significant opening of cracks in the deck.
  The highest strain was across the joint interface.
What did this mean for Keg Creek?
  Retro-fit of continuity connection of the girders over the pier.

## Slide 76: Day 12 – Oct. 28 UHPC TESTING
Flowability
test
CYLINDER TESTS
48 HOURS ~ 10 ksi
28 DAYS ~ 21 ksi
THERMAL TEST

## Slide 77: LESSONS LEARNED
ABC is a viable bridge construction alternative for Iowa.
Margin of error is lower than CIP.
However, refinement of contract agreements, our own construction inspection program, and improvements to design/specifications.
The premium cost for ABC is about double (based on Keg Creek). Difficult to rationalize this. (User Cost)

## Slide 78: LESSONS LEARNED
Design / Construction
  Geometry/shape of the abutment diaphragm overhang needs rework. This includes the need to reduce joint bar in the vertical plane.
    Difficult to seal inside face enabling UHPC to leak
    Rectangular shape makes it difficult to backfill
    Vertical joint rebar is congested causing erection difficulties.
  Joint steel congestion leads to increased labor costs and delays. Lets take advantage of UHPC tensile properties.
  The beveled edge (or diamond shape) joint style is problematic at modular deck corners. Experiment with a key-way joint.
  LOTS MORE TO IMPROVE ON!!