## Sheet1
WORKING AND SHOP DRAWINGS - UPDATED MAY 2015 WITH DOCUMENT RETENTION GUIDELINES
|  |  |  | OFFICE RESPONSIBLE FOR |  |  |  | DISTRIBUTION OF | RESPONSIBILITY FOR FINAL APPROVAL
DESCRIPTION | SPECIFICATION ARTICLE | REVIEW OFFICE | DOCUMENTATION RETENTION | DOCUMENT RETENTION | NO. OF COPIES | SUBMITTAL TIME | REVIEW TIME | APPROVED COPIES | AND DISTRIBUTION
FALSEWORK FOR CONTINUOUS CONCRETE SLAB | 2403.17 | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
SLAB & CAST-IN-PLACE CONCRETE BOX | [7 empty] | 1 - CONSTRUCTION
GIRDER BRIDGES | [7 empty] | 2 - RCE
2 - CONTRACTOR
COFFERDAM DESIGN (WHEN REQUIRED BY | 2405.02 | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
THE CONTRACT DOCUMENTS) | [7 empty] | 1 - CONSTRUCTION
2 - RCE
2 - CONTRACTOR
RECONSTRUCTION OF SUBSTRUCTURE | 2405.12 | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
(DETAILED PLANS FOR SUPPORTING THE | [7 empty] | 1 - CONSTRUCTION
SUPERSTRUCTURE) | [7 empty] | 2 - RCE
2 - CONTRACTOR
STEEL STRUCTURES: | 2408.02 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
1 - FABRICATOR
DETAILED SHOP DRAWINGS |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 7 |  |  | 2 - CENTRAL MATERIALS
1 - DISTRICT MATERIALS
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1 |  |  | 1 - RCE
|  | ENGINEER | [5 empty] | 1 - CONTRACTOR
DETAIL PLANS FOR FALSEWORK OR | 2408.33 | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
CENTERING SUPPORT OF STEEL | [7 empty] | 2 - RCE
STRUCTURE (IE: ERECTION PLANS) | [7 empty] | 2 - CONTRACTOR
COVER LETTER TO:
DISTRICT ENGINEER
OFFICE OF CONSTRUCTION
PIPE & STRUCTURAL STEEL PEDESTRIAN | 2414.03 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 2 - CENTRAL MATERIALS | BRIDGE DESIGN
HAND RAILINGS: | [7 empty] | 1 - FABRICATOR
1 DISTRICT MATERIALS
DETAILED SHOP DRAWINGS |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 |  |  | 1 - RCE
1 - BRIDGE DESIGN
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1 |  |  | 1 - CONTRACTOR
ENGINEER
ALUMINUM PEDESTRIAN HAND RAILINGS: | 2414.06 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 2 - CENTRAL MATERIALS | BRIDGE DESIGN
1 - FABRICATOR
DETAILED SHOP DRAWINGS |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 |  |  | 1 DISTRICT MATERIALS
1 - RCE
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1 |  |  | 1 - BRIDGE DESIGN
|  | ENGINEER | [5 empty] | 1 - CONTRACTOR
SUPPORT STRUCTURES FOR HIGHWAY | 2423.02 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
SIGNS: (IE: TRUSSES, CANTILEVERS, & | [7 empty] | 1 - FABRICATOR
BRIDGE MOUNTS)
2 - CENTRAL MATERIALS
DETAILED SHOP DRAWINGS |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 |  |  | 1 - DISTRICT MATERIALS
1 - RCE
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1 |  |  | 1 - CONTRACTOR
ENGINEER
|  |  |  | OFFICE RESPONSIBLE FOR |  |  |  | DISTRIBUTION OF | RESPONSIBILITY FOR FINAL APPROVAL
DESCRIPTION | SPECIFICATION ARTICLE | REVIEW OFFICE | DOCUMENTATION RETENTION | DOCUMENT RETENTION | NO. OF COPIES | SUBMITTAL TIME | REVIEW TIME | APPROVED COPIES | AND DISTRIBUTION
PRECAST PRESTRESSED CONCRETE DECK | 2425.03 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
PANELS - SHOP DRAWINGS FOR | [7 empty] | 1 - FABRICATOR
FABRICATION | [7 empty] | 2 - CENTRAL MATERIALS
1 - DISTRICT MATERIALS
1 - RCE
1 - CONTRACTOR
TOWER LIGHTING - SHOP DRAWINGS FOR | 2522.02 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
FABRICATION AND SUPPLIED COMPONENTS | [7 empty] | 1 - FABRICATOR
2 - CENTRAL MATERIALS
DETAILED SHOP DRAWINGS - FABRICATION |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 |  |  | 1 - DISTRICT MATERIALS
1 - RCE
DETAILED SHOP DRAWINGS - COMPONENTS |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2 |  |  | 1 - CONTRACTOR
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1
ENGINEER
HIGHWAY LIGHTING - SHOP DRAWINGS FOR | 2523.02 | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - CENTRAL MATERIALS | TRAFFIC & SAFETY
FABRICATION AND SUPPLIED COMPONENTS | [7 empty] | 1 - DISTRICT MATERIALS
(IE: DRAWINGS TO INCLUDE CATALOG CUTS, | [7 empty] | 1 - FABRICATOR
DIAGRAMS, DRAWINGS, BROCHURES, AND | [7 empty] | 1 - TRAFFIC ENGINEERING
OTHER DESCRIPTIVE DATA) | [7 empty] | 2 - RCE
1 - CONTRACTOR
DETAILED SHOP DRAWINGS - FABRICATION |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2
DETAILED SHOP DRAWINGS - COMPONENTS |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1
ENGINEER
HIGHWAY SIGNING - SHOP DRAWINGS FOR | 2524.02 B | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - CENTRAL MATERIALS | TRAFFIC & SAFETY
FABRICATION OF POSTS AND LIST OF | [7 empty] | 1 - DISTRICT MATERIALS
EQUIPMENT AND MATERIALS TO BE | [7 empty] | 1 - FABRICATOR
FURNISHED | [7 empty] | 1 - TRAFFIC ENGINEERING
2 - RCE
DETAILED SHOP DRAWINGS - FABRICATION |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2 |  |  | 1 - CONTRACTOR
DETAILED SHOP DRAWINGS - COMPONENTS |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1
ENGINEER
TRAFFIC SIGNALIZATION - SHOP DRAWINGS | 2525.01 B | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY |  | SEE NOTE (1) | 30 CALENDAR DAYS | 1 - CENTRAL MATERIALS | TRAFFIC & SAFETY
FOR FABRICATION OF POLES AND MAST | [7 empty] | 1 - DISTRICT MATERIALS
ARMS, LIST OF EQUIPMENTS AND MATERIALS | [7 empty] | 1 - FABRICATOR
TO BE FURNISHED | [7 empty] | 1 - TRAFFIC ENGINEERING
2 - RCE
DETAILED SHOP DRAWINGS - FABRICATION |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2 |  |  | 1 - CONTRACTOR
2 - LOCAL JURISDICTION
DETAILED SHOP DRAWINGS - COMPONENTS |  | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1
ENGINEER
PRECAST REINFORCED CONCRETE | 2415.01 | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
BOX CULVERTS | [7 empty] | 1 - FABRICATOR
2 - CENTRAL MATERIALS
1 - DISTRICT MATERIALS
2 - RCE
1 - CONTRACTOR
HIGHWAY SIGNING - SHOP DRAWINGS FOR | 2524.02 B | TRAFFIC & SAFETY | SEE NOTE (4) | TRAFFIC & SAFETY | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - TRAFFIC ENGINEERING | TRAFFIC & SAFETY
TYPE B SIGNS | [7 empty] | 1 - FABRICATIOR
2 - RCE
1 - CONTRACTOR
|  |  |  | OFFICE RESPONSIBLE FOR |  |  |  | DISTRIBUTION OF | RESPONSIBILITY FOR FINAL APPROVAL
DESCRIPTION | SPECIFICATION ARTICLE | REVIEW OFFICE | DOCUMENTATION RETENTION | DOCUMENT RETENTION | NO. OF COPIES | SUBMITTAL TIME | REVIEW TIME | APPROVED COPIES | AND DISTRIBUTION
PRECAST ITEMS (IE: NOISE WALL PANELS | CONTRACT DOCUMENTS | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
AND ARCH SECTIONS) | [7 empty] | 1 - FABRICATOR
2 - CENTRAL MATERIALS
1 - DISTRICT MATERIALS
2 - RCE
1 - CONTRACTOR
BRIDGE BEAM COMPONENTS (IE: SOLE | CONTRACT DOCUMENTS | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
PLATES, CURVED SOLE PLATES, BEARINGS, | [7 empty] | 1 - FABRICATOR
MASONRY PLATES, PROTECTION PLATES, | [7 empty] | 1 - CENTRAL MATERIALS
DECK DRAINS, STEEL INTERMEDIATE | [7 empty] | 1 - DISTRICT MATERIALS
DIAPHRAGMS FOR PPC BEAMS, AND | [7 empty] | 1 - RCE
EXPANSION JOINTS) | [7 empty] | 1 - CONTRACTOR
DETAILED SHOP DRAWINGS - FABRICATION |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1
ENGINEER
PRE-ENGINEERED STEEL TRUSS | CURRENT SUPPLEMENTAL | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN |  | SEE N0TE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
RECREATIONAL TRAIL BRIDGE | SPECIFICATION | [6 empty] | 1 - FABRICATOR
1 - CENTRAL MATERIALS
DETAILED SHOP DRAWINGS - FABRICATION |  | BRIDGE DESIGN | SEE NOTE (4) | BRIDGE DESIGN | 2 |  |  | 1 - DISTRICT MATERIALS
2 - RCE
WELDING PROCEDURES |  | STRUCTURAL MATERIALS | SEE NOTE (3) |  | 1 |  |  | 1 - CONTRACTOR
ENGINEER
MSE. SEGMENTAL, AND MODULAR BLOCK | CURRENT DEVELOPMENTAL | DESIGN SOILS | SEE NOTE (4) | DESIGN SOILS | PRELIMINARY SUBMITTALS: | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - SOILS DESIGN | SOILS DESIGN
RETAINING WALLS | SPECIFICATION |  |  |  | 3 DESIGN CALCS. |  |  | 1 - CENTRAL MATERIALS
[5 empty] | 3 FIELD CONSTRUCTION DRAWINGS |  |  | 2 - RCE
[5 empty] | FINAL SUBMITTALS: |  | 14 CALENDAR DAYS | 3 - CONTRACTOR | SOILS DESIGN
[5 empty] | 3 DESIGN CALCS |  |  | 1 - CONSULTANT GEOTECH
[5 empty] | 3 DETAILED SHOP DRAWINGS |  |  | 1 - OFFICE OF DESIGN
[5 empty] | 3 FIELD CONSTRUCTION DRAWINGS |  |  | 1 - BRIDGE DESIGN
1 - DISTRICT MATERIALS
1 - OFFICE OF CONSTRUCTION
1 - FHWA
SOIL NAIL AND TIE-BACK RETAINING WALLS | CURRENT SPECIAL | DESIGN SOILS | SEE NOTE (4) | DESIGN SOILS | 6 FINAL DESIGN PLANS | SEE NOTE (2) | 60 CALENDAR DAYS | 1 - SOILS DESIGN | SOILS DESIGN
| PROVISION | [6 empty] | 1 - CENTRAL MATERIALS
1 - DISTRICT MATERIALS
2 - RCE
2 - CONTRACTOR
1 - BRIDGE DESIGN
1 - OFFICE OF DESIGN
1 - OFFICE OF CONSTRUCTION
1 - GEOTECH CONSULTANT
1 - FHWA
INTERMEDIATE FOUNDATION IMPROVEMENT | CURRENT SPECIAL | DESIGN SOILS | SEE NOTE (4) | DESIGN SOILS | 4 DESIGN CALCS | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - SOILS DESIGN | SOILS DESIGN
(IFI) (IE: STONE COLUMNS, GEOPIERS, ETC.) | PROVISION |  |  |  | 8 FIELD CONSTRUCTION DRAWINGS |  |  | 2 - RCE
2 - CONTRACTOR
1 - GEOTECH CONSULTANT
1 - OFFICE OF CONSTRUCTION
REMOVAL OF BOX GIRDER BRIDGES | CURRENT DEVELOPMENTAL | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
| SPECIFICATION | [6 empty] | 2 - RCE
2 - CONTRACTOR
STRUCTURAL ERECTION MANUAL | CURRENT SPECIAL | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
| PROVISION | [6 empty] | 2 - RCE
2 - CONTRACTOR
TEMPORARY SHORING | CONTRACT DOCUMENTS | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
2 - RCE
2 - CONTRACTOR
TEMPORARY SHEET PILE RETAINING WALL | CONTRACT DOCUMENTS | BRIDGE DESIGN | SEE NOTE (3) | RCE | 2 | SEE NOTE (2) | 30 CALENDAR DAYS | 1 - BRIDGE DESIGN | BRIDGE DESIGN
2 - RCE
2 - CONTRACTOR
NOTE (1): WITHIN 45 DAYS FROM THE DATE OF AWARD OF CONTRACT.
NOTE (2): UNLESS OTHERWISE SPECIFIED IN THE CONTRACT DOCUMENTS, CONTRACTOR
SUBMITTAL TIME IS SUBJECT TO THE SPECIFIED REVIEW TIME AND THE CONTRACTOR'S
NEED BASED ON THEIR SCHEDULE FOR THE WORK.
NOTE (3): RETAIN THESE DOCUMENTS UNTIL EITHER: 1) 3 YEARS AFTER NOTICE OF
RECEIPT OF FINAL FEDERAL REIMBURSEMENT FROM FINANCE, OR 2) ON NON-PARTICIPATING
PROJECTS, A MAXIMUM OF 3 YEARS FROM DATE OF FINAL PAYMENT.
NOTE (4): THESE DOCUMENTS ARE TO BE PERMANENTLY RETAINED. THE PRIMARY REVIEW
OFFICE IS REPONSIBLE FOR PROCESSING THE DOCUMENTS FOR RETENTION. THE
DOCUMENTS ARE TO BE ELECTRONICALLY RETAINED IN ERMS.
THE PRIMARY REVIEW OFFICE SHALL CONTACT KELLY POPP, OFFICE OF DOCUMENT SERVICES,
AT 515-239-1295 FOR INSTRUCTIONS ON HOW TO ELECTRONICALLY FILE THE RETAINED
DOCUMENTS IN ERMS.