## Slide 1: 2021-2025 Highway Program Development
April 13, 2020

## Slide 2
April Workshop Agenda
  Revisit previously discussed Decision Points
  Review 2021-2025 Highway Program Balances
  Summarize 2021-2025 Highway Program Objectives
  Discuss detailed project lists
April 13, 2020

## Slide 3
Commission Program Development Schedule (2021-2025)
  April 2020
  Develop the Draft 2021-2025 Highway Program
  Action Item: 2021-2025 Highway Program Objectives
  May 2020
  Present the Draft 2021-2025 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2021–2025 Highway Program)
  June 2020
  Action Item: Approve the 2021–2025 Iowa Transportation Improvement Program
April 13, 2020

## Slide 4: Decision Points
At what levels should the line item targets be programmed?
Should projects in the 2021-2024 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
April 13, 2020

## Slide 5: Revisiting Decision Points
1. At what levels should the line item targets be programmed?
Commission direction based on February 11 discussion and March 10 action:
Increase the following line item targets
  Construction Industry Training Program by $500,000 from $500,000 to $1 million
  Post Letting Project Cost by $10 million from $10 million to $20 million
  Prevocational Training and DBE Support Services by $60,000 from $300,000 to $360,000
  Statewide Consultant Services by $2,500,000 from $82,500,000 to $85,000,000.
  Statewide Contract Maintenance by $4 million from $31,350,000 to $35,350,000
Continue to fund all other line items at previously approved target levels.
April 13, 2020

## Slide 6: Revisiting Decision Points
2. Should projects in the 2021-2024 program continue to be
programmed with cost/schedule updates?
Commission direction based on March 10 and 26 discussion:
Yes, there is program capacity to do so with some rebalancing.
In many cases, local jurisdictions have made commitments and project scheduling decisions based on current program schedules.
April 13, 2020

## Slide 7: Revisiting Decision Points
3. How should the Program be balanced and what projects should be added to the Program?
Commission discussion on March 10 and 26:
There is program capacity to continue the incremental increases to the stewardship targets in the later years of the Program based on asset management discussions.
Continue to program in FY 2025 previously programmed multi-year projects.
Delay six Non-Interstate Capacity/System Enhancement projects to balance the Program (no projects removed from the Program)
Add Iowa 2 resiliency project in Fremont County (Phase 1)
Add US 18 Super-2 project in Hancock County.
Add US 30 Super-2 project from ECL Lisbon to ECL Mechanicsville in Cedar County.
Add several small sized projects to address safety and operational needs that cannot otherwise be met with the stewardship category.
April 13, 2020

## Slide 8
 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Beyond | 
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  | 
US 75 Plymouth: N of Maple St in Hinton to S of 2nd St in Merrill (SB) | 20.2 |  |  |  |  |  |  | 
US 75 Plymouth: N of Maple St in Hinton to S of 2nd St in Merrill (SB) |  |  | 22.1 |  |  |  |  | 
Iowa 27 Black Hawk: US 20 to Ridgeway Ave in Cedar Falls (NB&SB) |  | 5.1 |  |  |  |  |  | 
Iowa 27 Black Hawk: US 20 to Ridgeway Ave in Cedar Falls (NB&SB) |  |  | 5.3 |  |  |  |  | 
Iowa 1 Jefferson: S of Libertyville Rd to Fillmore Ave in Fairfield |  | 3.5 |  |  |  |  |  | 
Iowa 1 Jefferson: S of Libertyville Rd to Fillmore Ave in Fairfield |  |  | 3.7 |  |  |  |  | 
Iowa 92 Keokuk: Iowa 21 and Co Rd V33 Intersections |  | 6.0 |  |  |  |  |  | 
Iowa 92 Keokuk: Iowa 21 and Co Rd V33 Intersections |  |  | 6.3 |  |  |  |  | 
US 30 Story: 0.5 MI E of I-35 to E of 590th Ave |  | 14.1 | 9.9 | 0.4 |  |  |  | 
US 30 Story: 0.5 MI E of I-35 to E of 590th Ave |  |  | 14.5 | 10.3 | 0.4 |  |  | 
Capacity |  |  |  |  |  |  |  | 
US 61 Louisa: 0.5 MI N of Iowa 78 to 2.0 MI S of Iowa 92 |  |  |  | 5.8 | 41.0 |  |  | 
US 61 Louisa: 0.5 MI N of Iowa 78 to 2.0 MI S of Iowa 92 |  |  |  |  | 5.8 | 42.9 | 51.5 | 
Project Reschedule Scenario
For Highway Planning Purposes Only (x $1,000,000)
April 13, 2020
As presented March 26, 2020

## Slide 9
Projected Funds as of March 2020 826.3 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 242.1 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0
Non-Interstate Pavement Modernization 105.7 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 64.1 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0
Safety Specific 25.6 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 125.0 137.8 226.7 217.6 102.1
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 280.1 200.5 111.8 68.9 125.4
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Cedar (scaled back to just include replacement of Sugar Creek bridges)
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (16.3) (50.1) (50.3) (25.0) (19.5) 51.4 87.8 84.7 106.2 91.2
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
    Changes to Projected Funds
    FY 2020 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2021 to 2024, add 2025
    Adjusted federal funding forecast
    Added highlighted projects
    Additional project schedule changes
April 13, 2020

## Slide 10
April 13, 2020
Chart: Iowa Primary Highway Investments Includes Interstate Highway System
| 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Pavement - Stewardship | 180029140.12 | 243383426.67 | 266261338.34 | 321336244.22 | 315135602.2 | 364598993.43 | 231757286.78 | 298000000 | 231000000 | 323118000 | 372000000 | 418821000 | 292688000 | 473633000 | 380850000 | 329243000
Bridge - Stewardship | 76212446.31 | 90815539.28 | 58535096.84 | 73574046.26 | 126975846.86 | 140909171.27 | 132548153.82 | 169000000 | 170000000 | 186236000 | 167000000 | 156865000 | 180629000 | 161082000 | 196081000 | 217836000
System Capacity | 96491746.86 | 131408013.59 | 182498016.09 | 122495162.36 | 176334373.08 | 110164518.82 | 311344175.14 | 346000000 | 282000000 | 208700000 | 180000000 | 133593000 | 218000000 | 120000000 | 121623000 | 114568000
Other Investments | 23601321.95 | 47772112.98 | 33837527.55 | 64953341.51 | 88110203.63 | 77471824.93 | 52245066.71 | 10000000 | 36000000 | 23913000 | 37000000 | 39433000 | 29765000 | 23730000 | 16971000 | 12701000
Percent Stewardship | 0.68089 | 0.65098 | 0.60022 | 0.67812 | 0.62573 | 0.7293 | 0.50049 | 0.56744 | 0.55772 | 0.68649 | 0.71296 | 0.7689 | 0.6564 | 0.81536 | 0.8063 | 0.81127

## Slide 11
  Projects in the 2021-2024 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
Potential FY 2021-2025 Highway Program Objectives
April 13, 2020

## Slide 12
Explanation of Highway Program Changes
Project costs increased
Project costs increased
Added new project
for year 2025
Project moved from 2022 to 2021
and costs increased
April 13, 2020
Project costs decreased

## Slide 13
  Program Estimates
    Project initially programmed in year 4/5: High-level estimate
    As project moves closer to construction (years 2/3): Project estimates are refined as development and design advances. Updated each year as part of the program development process.
    Best estimate is when project is in year 1 of the Program as design is complete or nearly complete. Cost is updated as part of the program development process.
  Project Letting
    Projects are let for bid each month.
    Analysis is completed to compare awarded bid with program estimate for each project and total amount over or under program estimates are reflected in Commission monthly balance report
  Project Construction
    As projects are constructed, sometimes unexpected conditions arise (e.g. pavement deterioration, soil conditions, safety considerations) that require a change order to approve additional work.
    Those additional costs are accounted for by the back-of-the-program line item labeled “Post Letting Project Cost”
Project Costs: Initial estimates to construction
April 13, 2020

## Slide 14: Next Steps
  April
  Action Item: Approve 2021-2025 Highway Program Objectives
  May
  Present the Draft 2021-2025 Iowa Transportation Improvement Program to the public (including all previous program approvals and draft 2021–2025 Highway Program)
  June
  Action Item: Approve 2021-2025 Iowa Transportation Improvement Program
April 13, 2020