## Slide 1
JOHN DEERE ROAD
CORRIDOR PROJECT
Iowa DOT Commission Meeting – April 13, 2021

## Slide 2
FOR TODAY
DISCUSSION
Project Development Review
Planned Improvements
ROW
Update on Decoupling Process & Schedule
Construction
Budget

## Slide 3
GOALS
PROJECT
Address safety and operational challenges
affecting traffic at John Deere.
Traffic Flow
Reduce travel delays
Boost freight mobility
Safety
Reduce accidents
Stakeholders
Support John Deere Expansion

## Slide 4
REVIEW
DEVELOPMENT
Stakeholder Engagement
Meetings with John Deere (9/16/20, 11/2/20) and DuTrac (11/18/20)
Update to Dubuque County Board of Supervisors
11/9/20, 2/22/21 (Public Outreach Meeting)
Preliminary Plans Submitted & Cleared
1/12/21
Environmental Concurrence
John Deere Road work complete; efforts focused on NW Arterial portion
ROW Acquisition
in progress
Private Utility Coordination
in progress
PROJECT

## Slide 5
Peru Road
S John Deere Road
IMPROVEMENTS
PROPOSED
W John Deere Road
Roundabout
Roundabout
Trail

## Slide 6
S John Deere Road
IMPROVEMENTS
PROPOSED
W John Deere Road
Trail
Overlay

## Slide 7
UPDATE
ROW
Appraisals
Under Review
Right-of-Way Public Hearing
3/1/21
Send Appraisals to Property Owners/Offers
June/July 2021

## Slide 8
Peru Road
S John Deere Road
UPDATE
ROW
W John Deere Road
DuTrac
John Deere
Dubuque County

## Slide 9
SCHEDULE
Environmental Concurrence
John Deere Road work complete; efforts focused on NW Arterial portion
June/July 2021
Final Design/Check Plans
10/12/21l
Letting
Late 2021/Early 2022

## Slide 10
CONSTRUCTION
When will it start?
Spring 2022
Traffic During Construction
When will it end?
Spring/Early Summer 2023

## Slide 11
UPDATE
BUDGET
$6.8M
Project Budget
Preliminary Estimate within budget
Planned improvements
Includes contingency
ROW acquisition costs
Utility relocation costs

## Slide 12
Peru Road
S John Deere Road
W John Deere Road
QUESTIONS