## Slide 1: 2023-2027 Highway Program Development
April 11, 2022

## Slide 2
April Workshop Agenda
  Revisit previously discussed Decision Points
  Review 2023-2027 Highway Program Balances
  Summarize 2023-2027 Highway Program Objectives
  Discuss detailed project lists
April 11, 2022

## Slide 3
Commission Program Development Schedule (2023-2027)
  April 2022
  Develop the Draft 2023-2027 Highway Program
  Action Item: 2023-2027 Highway Program Objectives
  May 2022
  Present the Draft 2023-2027 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2023–2027 Highway Program)
  June 2022
  Action Item: Approve the 2023–2027 Iowa Transportation Improvement Program
April 11, 2022

## Slide 4: Decision Points
At what levels should the line item targets be programmed?
Should projects in the 2023-2026 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
April 11, 2022

## Slide 5: Revisiting Decision Points
1. At what levels should the line item targets be programmed?
Commission direction based on February 9 discussion and March 9 action:
Increase the Americans with Disabilities Act line item target by $500,000 and increase by $500,000 each year until it reaches $5.5 million in 2027.
Split out statewide operations from statewide consultant services in a revenue neutral manner.
Continue to fund all other line items at previously approved target levels.
April 11, 2022

## Slide 6: Revisiting Decision Points
2. Should projects in the 2023-2026 program continue to be
programmed with cost/schedule updates?
Commission direction based on March 8 and 24 discussion:
Yes, there is program capacity to do so.
April 11, 2022

## Slide 7: Revisiting Decision Points
3. How should the Program be balanced and what projects should be added to the Program?
Commission discussion on March 8 and 24:
Add in project continuation costs in FY 2027 for previously programmed multi-year projects
Advance and compress I-80/Madison Avenue schedule
Add additional targeted Interstate and Non-Interstate projects
Increase stewardship levels beyond already scheduled increases (i.e., pavement, bridge, safety)
Add several smaller projects to address safety and operational needs that cannot otherwise be met with the stewardship category.
April 11, 2022

## Slide 8
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | 
Major Interstate Capacity/System Enhancement |  |  |  |  |  |  |  | 
CBIS: I-80 and Madison Avenue |  |  | 37.6 | 28.4 | 24.7 | 39.0 | 1.0 | 
CBIS: I-80 and Madison Avenue | 65.0 | 55.0 |  | 1.0 |  |  |  | 
Project Advance
For Highway Planning Purposes Only (x $1,000,000)
April 11, 2022
as presented March 24, 2022

## Slide 9
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | 
Major Interstate Capacity/System Enhancement |  |  |  |  |  |  |  | 
I35/80/235 Polk: Southwest Mixmaster |  |  |  |  | 36.1 | 86.4 | 13.0 | 
I-380 Linn: Segment 3 120th St NW to US 30 (Wright Brothers Blvd Interchange) |  |  | 99.5 |  |  |  |  | 
I-35 Story: US 30 Interchange Bridges and mainline widening south to Skunk River |  |  |  |  | 4.9 | 10.4 | 56.7 | 
I-80 Scott: Middle Road Interchange |  |  | 45.8 |  |  |  |  | 
Project Addition Scenario
For Highway Planning Purposes Only (x $1,000,000)
April 11, 2022
as presented March 24, 2022

## Slide 10
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | 
Non-Interstate Capacity/System Enhancement |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  | 
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  |  | 20.6 |  |  | 
Iowa 333: Hamburg Resiliency | 2.0 |  |  |  |  |  |  | 
Polk: Iowa Traffic Training Center – Phase 1 | 10.0 |  |  |  |  |  |  | 
US 75 North of Sioux Center to S Jct US 18 |  |  | 0.1 |  | 13.7 |  |  | 
IA 149: Des Moines River Bridge to Woodland Ave in Ottumwa |  |  |  |  | 4.7 |  |  | 
Culverts/Slide Repairs (multiple locations statewide) | 2.9 | 0.5 | 0.6 | 0.5 | 0.5 |  |  | 
Capacity |  |  |  |  |  |  |  | 
IA 58 Black Hawk: Greenhill Road Interchange |  |  |  |  | 33.5 |  |  | 
US 151 Linn: Co Rd X-20 Interchange at Springville |  |  |  |  | 35.0 |  |  | 
US 30 Story: 610th Ave Interchange (Nevada) |  |  | 1.7 |  | 11.0 | 11.1 | 0.7 | 
US 63 Tama: NCL Traer to Hudson (Super-2) |  |  |  |  | 7.1 |  |  | 
Stewardship |  |  |  |  |  |  |  | 
Interstate Stewardship |  |  |  |  | 25.0 |  |  | 
Non-Interstate Pavement Modernization |  |  |  |  | 35.0 | 35.0 | 35.0 | 
Non-Interstate Bridge Modernization |  |  |  |  | 20.0 | 20.0 | 20.0 | 
Safety |  |  |  |  | 5.0 | 5.0 | 5.0 | 
Transfer of Jursidiction US 6 Pottawattamie: 6th Street in Council Bluffs east to I-80 |  | 7.0 | 5.0 | 5.0 |  |  |  | 
US 30 Harrison: Missouri Valley Bypass (TJ) |  |  |  |  |  | 2.0 |  | 
US 30 Harrison: Missouri Valley Bypass (TJ) | 2.0 |  |  |  |  | (2.0) |  | 
Project Addition Scenario
For Highway Planning Purposes Only (x $1,000,000)
April 11, 2022
as presented March 24, 2022

## Slide 11
Projected Funds 820.9 855.6 856.1 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 166.7 136.8 191.4 203.2 200.0 180.0 185.0 190.0 195.0 200.0
Non-Interstate Pavement Modernization 139.5 145.0 150.0 155.0 200.0 210.0 220.0 225.0 230.0 235.0
Non-Interstate Bridge Modernization 102.0 109.1 144.6 141.0 175.0 190.0 205.0 210.0 215.0 220.0
Safety Specific 31.6 32.0 33.0 34.0 40.0 41.0 42.0 43.0 44.0 45.0
Non-Interstate Capacity/System Enhancement 219.1 300.0 110.4 218.4 24.4
US 30 Missouri Valley bypass 32.9
US 61 1 mi N of IA 78 to 2 mi S of IA 92 45.7
Stewardship Projects 14.9 0.5 0.7 0.5 39.5
Capacity Projects 1.7 86.6 11.1 0.4
Transfer of Jurisdiction 2.0 7.0 5.0 5.0 (2.0)
Major Interstate Capacity/System Enhancement 181.0 148.3 82.3 146.1 51.7
I-80 Scott Mississippi River Bridge 50.0
I-35/80/235 Polk Southwest Mixmaster 36.1 86.4 13.0
I-380 Linn 120th St to NW to US 30 99.5
I-35 Story US 30 Interchange Bridges and Mainline 4.9 10.4 29.9 25.6 1.2
I-80 Scott Middle Road Interchange 45.8
Highway Program Balance (35.9) (23.1) (8.3) (45.3) (7.6) (4.9) 155.0 157.0 165.4 150.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
    Changes to Projected Funds
    FY 2022 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2023 to 2026, add 2027
    Advance CBIS – Madison Avenue
    Project Funding Scenario
April 11, 2022
as presented March 24, 2022

## Slide 12
Projected Funds 820.9 855.6 856.1 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 166.7 136.8 191.4 203.2 200.0 180.0 185.0 190.0 195.0 200.0
Interstate Stewardship 0.2 0.4 0.9
Non-Interstate Pavement Modernization 139.5 145.0 150.0 155.0 200.0 210.0 220.0 225.0 230.0 235.0
Non-Interstate Bridge Modernization 102.0 109.1 144.6 141.0 175.0 190.0 205.0 210.0 215.0 220.0
Safety Specific 31.6 32.0 33.0 34.0 40.0 41.0 42.0 43.0 44.0 45.0
Non-Interstate Capacity/System Enhancement 219.1 300.0 110.4 218.4 24.4
US 30 Missouri Valley bypass 32.9
US 61 1 mi N of IA 78 to 2 mi S of IA 92 45.7
Stewardship Projects 14.9 0.5 0.7 0.5 39.5
Capacity Projects 1.7 86.6 11.1 0.4
Transfer of Jurisdiction 2.0 7.0 5.0 5.0 (2.0)
Major Interstate Capacity/System Enhancement 181.0 148.3 82.3 146.1 51.7
I-80 Scott Mississippi River Bridge 50.0
I-35/80/235 Polk Southwest Mixmaster 36.1 86.4 13.0
I-380 Linn 120th St to NW to US 30 99.5
I-380 Linn 120th St to NW to US 30 0.3 (0.4) 0.1
I-35 Story US 30 Interchange Bridges and Mainline 4.9 10.4 29.9 25.6 1.2
I-80 Scott Middle Road Interchange 45.8
Highway Program Balance (35.9) (23.4) (8.1) (45.8) (8.5) (4.9) 155.0 157.0 165.4 150.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
April 11, 2022
    Changes to Projected Funds
    FY 2022 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2023 to 2026, add 2027
    Advance CBIS – Madison Avenue
    Project Funding Scenario
    Adjustment for final 2027 stewardship project lists

## Slide 13
Projected Funds 820.9 855.6 856.1 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 166.7 136.8 191.6 203.6 200.9 180.0 185.0 190.0 195.0 200.0
Non-Interstate Pavement Modernization 139.5 145.0 150.0 155.0 200.0 210.0 220.0 225.0 230.0 235.0
Non-Interstate Bridge Modernization 102.0 109.1 144.6 141.0 175.0 190.0 205.0 210.0 215.0 220.0
Safety Specific 31.6 32.0 33.0 34.0 40.0 41.0 42.0 43.0 44.0 45.0
Non-Interstate Capacity/System Enhancement 219.1 300.0 110.4 218.4 24.4
US 30 Missouri Valley bypass 32.9
US 61 1 mi N of IA 78 to 2 mi S of IA 92 45.7
Stewardship Projects 14.9 0.5 0.7 0.5 39.5
Capacity Projects 1.7 86.6 11.1 0.4
Transfer of Jurisdiction 2.0 7.0 5.0 5.0 (2.0)
Major Interstate Capacity/System Enhancement 181.0 148.3 82.3 146.1 51.7
I-80 Scott Mississippi River Bridge 50.0
I-35/80/235 Polk Southwest Mixmaster 36.1 86.4 13.0
I-380 Linn 120th St to NW to US 30 0.3 99.1 0.1
I-35 Story US 30 Interchange Bridges and Mainline 4.9 10.4 29.9 25.6 1.2
I-80 Scott Middle Road Interchange 45.8
Highway Program Balance (35.9) (23.4) (8.1) (45.8) (8.5) (4.9) 155.0 157.0 165.4 150.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
April 11, 2022
    Changes to Projected Funds
    FY 2022 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2023 to 2026, add 2027
    Advance CBIS – Madison Avenue
    Project Funding Scenario
    Adjustment for final 2027 stewardship project lists

## Slide 14
April 11, 2022
  Projects in the 2023-2026 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Provide a targeted increase and then maintain increasing funding levels for safety
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Provide a targeted increase and then maintain increasing funding levels for non-interstate pavement modernization
    Provide a targeted increase and then maintain increasing funding levels for non-interstate bridge modernization
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
    Invest in operational and Integrated Corridor Management improvements
    Invest in additional truck parking at Interstate Rest Areas
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
Potential FY 2023-2027 Highway Program Objectives

## Slide 15
Explanation of Highway Program Changes
April 11, 2022
Project costs increased
New project added to year 2027
Project moved from year 2024 to 2025

## Slide 16: Next Steps
  April
  Action Item: Approve 2023-2027 Highway Program Objectives
  May
  Present the Draft 2023-2027 Iowa Transportation Improvement Program to the public (including all previous program approvals and draft 2023–2027 Highway Program)
  June
  Action Item: Approve 2023-2027 Iowa Transportation Improvement Program
April 11, 2022