## Slide 1: FY 2020 Highway Program Balance ($ in millions)
Program Balance (June 2019) |  | (51.7)
Forecast PRF Receipts (through June) | 827.7 | 
Actual PRF Receipts (through June) | 870.0 | 
Difference |  | 42.3
Programmed Amounts (through June) | 663.5 | 
Project Costs (through June) | 756.4 | 
Difference |  | (92.9)
Program Balance (June 2020) |  | (102.3)
Previous Balance Reported: (107.8)
August 11, 2020

## Slide 2: FY 2021 Highway Program Balance ($ in millions)
Program Balance (June 2020) |  | (16.3)
Forecast PRF Receipts (July) | NA | 
Actual PRF Receipts (July) | NA | 
Difference |  | NA
Programmed Amounts (July) | 71.0 | 
Project Costs (July) | 76.4 | 
Difference |  | (5.4)
Program Balance (July 2020) |  | (21.7)
Previous Balance Reported: (NA)
August 11, 2020

## Slide 3
Fiscal Year 2021 Overview
Revenue: COVID-19 impacts have reduced revenues for FY 20 and are expected to continue into FY 21.
Lettings:
  100 percent of the FY 2020 Program has now been awarded.
  8 percent of the FY 2021 Program has now been awarded.
  Next letting is scheduled for August 18, 2020.
  The July letting was about $ 71 million.
August 11, 2020

## Slide 4
In order to mitigate the loss of revenue due to COVID-19, the letting of the following FY 2021 projects has been delayed
  The final phase of the I-80/I-380 Interchange reconstruction in Johnson County
  I-80 widening in Johnson County
  I-29/I-480 interchange reconstruction in Council Bluffs
  US 65 pavement resurfacing in Story County
  Iowa 175 pavement resurfacing in Calhoun/Webster County
These delays were necessary to assure sufficient funding was available to complete work already under construction this season
Each month, additional reviews are conducted and additional project letting delays may be necessary
Without backfill of lost funding, additional project delays may be necessary, including removal of projects scheduled to be let this fiscal year, which would require significant changes in the Five-Year Program.
Fiscal Year 2021 Overview
COVID-19 Impacts on Lettings
August 11, 2020