## Slide 1
Transportation Commission
Iowa Interstate Investment Plan
December 12, 2023

## Slide 2
Planning Efforts & Project Development Activities Highlight Iowa’s Transportation Needs Exceed Available Funding
Background: Why an Interstate Plan?
Desired a tool that helps us identify realistic candidates for future programming based on a constrained interstate budget
Notes: Reminder of why we have developed the interstate plan.
Planning Shows the Need but we do not have the funds
5 years now with Interstate Plan
Inflation Impacts
  Higher Materials Costs
    Concrete
    Asphalt
    Steel
  Higher Labor Costs
    Grading
    Excavation

## Slide 3
Concept of a “fiscally constrained” Plan for Iowa’s Interstate System
Initiated by a 2-day Workshop including 70 Participants in Summer of 2018
Identified Statewide Interstate Needs and Budget Estimates
  Rehabilitation Needs vs. Capacity Expansion Needs
  Goal: Contrast the timing between both by corridor
Workshop Summer 2018
2 Days - 70 Participants
Balancing Design and $$
Notes: Quick Reminder of the Workshop that led to the I3P

## Slide 4
Workshop Recommendations
Stewardship - All participants recommended that the focus should be on preservation treatments to keep the system in its current state of good repair.
Consider Technology Options First - Expansion projects in urban corridors will be limited and focus on technology solutions and other management strategies before adding lanes.
  Transportation Systems Management & Operations (TSMO)
  Integrated Corridor Management (ICM)
Widening Options - Many segments of Interstate have significant pavement life remaining, so adding capacity in those areas will first consider widening the existing pavement rather than a complete rebuild.
Notes: Recommendations

## Slide 5
Coordination of Department Goals
Performance Based Design or “Right Sizing”
  System thinking rather than project thinking
  Don’t over-solve the problem
  Reducing low impact upgrades on one project will allow us to get more miles addressed to achieve the high value upgrades
  Better Timing of Projects to Minimize Potential Waste
Resiliency and Sustainability
  A transportation system:
    able to withstand or recover quickly from man-made or environmental disruptions.
    maintain a state of good repair while managing our resources in a way that promotes environmental stewardship and is fiscally responsible
Asset Management
  Maintenance strategies that optimize the performance and cost-effectiveness of the Interstate System
Notes: Right Sizing at the Right Time

## Slide 6
Initial Plan Result
$330 Million Annual Budget
Project Budgets Set Very Tight to Promote Right Sizing
Chart: Project Total vs Budget Through Interstate Plan Year 2040
| 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Project Costs | 349000000 | 422400000 | 339600000 | 382400000 | 324900000 | 237300000 | 302875642.78 | 376958627.94 | 265924713.74 | 286677024.35 | 289305467.07 | 310762120.44 | 325097533.03 | 301760657.05 | 496243735.28 | 493416351.16 | 590095614.31 | 494747613.21 | 418562355.52 | 500749680.48 | 227550000 | 423661000 | 140030000
Budget | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000
$330 Million Annual Budget
Notes: Horizon to year 2040
Priority Projects Near Term
Large Number of Projects in out years

## Slide 7
Last Year’s (2022) Project Totals
$330 Million Annual Budget
Project Budgets Set Very Tight to Promote Right Sizing
Program Years
Notes: Includes 5% increase in budget – implemented after 2nd year
Capacity Project Priority driven by Traffic Needs

## Slide 8
2023 Project Totals and Annual Budget
$330 Million Annual Budget
Project Budgets Set Very Tight to Promote Right Sizing
Program Years
Notes: Many projects pushed past year 2050 to give most realistic expectation of what we can accomplish in the next 25+ years.

## Slide 9
Project Timing
Notes: Explain How Graph Works
Moved up expansion I-80 - DSM to Mitchellville
Mitchellville to Iowa City pushed past 2050
Iowa City to Cedar River remains priority
Sugar Creek Bridges over Cedar River priority

## Slide 10
Project Timing
Notes: Scott County expansion not yet warranted by traffic
Spot Improvements will be needed
I-380 Iowa City to Cedar Rapids priority to finish – Middle Section over Iowa River
Wright Bros Interchange Priority
Boyson Rd north of Cedar Rapids programmed

## Slide 11
Project Timing
Notes: I-80 widening West of DSM – GPP to 60th under construction
I-80/US 169 interchange at DeSoto programmed
Focus on SW and NE Systems Interchanges in DSM

## Slide 12
Other Projects
Madison Ave Interchange – Programmed (2024-2025)
Middle Road Interchange – Programmed 2026
Hickman Road Interchange – Programmed (2025-2028)
Other Interstate Work

## Slide 13
Des Moines NE Mixmaster Phases
Stage Timing
Stage 1/2 - Complete
Stage 3 – Currently under Construction
  EB to NB Flyover
  WB to NB Ramp
Stage 4 – 2039
  South I-235 Widening
Stage 5 – 2034
  West I-80 through Interchange
  Widening and Aux Lanes
Stage 6 – 2040
  I-80 WB to SB Flyover
Stage 7 – 2043
  North I-35 Widening
Stage 8 – 2048
  North I-35 SB to EB Flyover
Example Plan Graphic

## Slide 14
Des Moines SW Mixmaster Stages
Phase Timing
Phases 1,2,3 – 2027 & 2028
  ROW in 2026
  Erosion Control in 2029
Phase 4 - 2038
Phase 5 - 2039
Phase 6 - 2040

## Slide 15
Interstate 35 Story County
South Skunk River Bridges
I-35 Mainline Bridges Over Skunk River Completed
I-35 Alignment Shift:
  Construction
  Traffic Management
I-35
Notes: Explain Skunk River bridge work already complete in this corridor.

## Slide 16
Interstate 35 Ames
I-35 Mainline Bridges over US 30
N of Co Rd E57/260th St to 0.6 mi N of US 30
2027 - $11.8 million
2028 - $11.5 million
2029 - $30.9 million
2030 - $26.6 million
2031 - $1.2 million
260th St
Notes: Explain all the work that goes into MOT etc.

## Slide 17
Interstate 35 - Story County
North of 315th St to
E57/260th St
Reconstruction to 6-lanes
2029 - $2.0 million
2030 - $6.0 million
2031 - $38.3 million
2032 - $37.0 million
I-35
Huxley
Ames
260th St
315th St

## Slide 18
Interstate 35 - Story County
North of US 30 to 13th St Ames
Reconstruction to 6-lanes
2035 - $30.2 million
2036 - $30.2 million
I-35
13th St
US-30

## Slide 19
Interstate 380 Johnson/Linn
North of Swan Lake Rd to North of 120th St
Reconstruction to 6-lanes
Delayed One Year
2029 - $50.2 million
2030 - $55.4 million
2031 - $60.2 million
120th St
Swan Lake Rd
Notes: Iowa River Crossing

## Slide 20
Interstate 380 Linn County
Blairs Ferry Rd to County Home Rd
Reconstruction to 6-lanes
2030 - $15.4 million
2031 - $32.5 million
Boyson Rd Interchange Programmed for 2025
$24.1 million
Boyson Rd
I-380

## Slide 21
Based on Timing of Capacity Need due to Traffic Volumes – I-80 Scott County corridor widening to 6-lanes moved to post 2050.
However, there are spot locations that will need addressed sooner than 2050.
Interstate 80 Scott County
US 61
I-74
I-80
Notes: Spot Treatments
US 61 Interchange
Mainline between US 61 and I-74

## Slide 22
Interstate 80 Scott County
Mississippi River Bridge
PEL Study Completed
Phase 1 Engineering
  4 Public Meetings to Date
Preferred Alternative Chosen
Alt 5 – Companion Bridge West
One Year Programmed 2028
Total Iowa Share $150 M
Illinois DOT - lead Agency

## Slide 23
Phil Mescher, AICP, CPM
PROJECT MANAGEMENT BUREAU
IOWA DEPARTMENT OF TRANSPORTATION
Phil.Mescher@iowadot.us
Office Phone: 515-233-7969
THANK YOU