## Slide 1
Iowa Interstate Investment Plan
Transportation Commission Update December 2024
3/2/2023
December 10, 2024

## Slide 2
Planning Efforts & Project Development Activities Highlight Iowa’s Transportation Needs Exceed Available Funding
Background: Why an Interstate Plan?
Desired a tool that helps us identify realistic candidates for future programming based on a constrained interstate budget

## Slide 3
Initiated by a 2-day Workshop including 70 Participants in Summer of 2018
Identified Statewide Interstate Needs and Budget Estimates
  Rehabilitation Needs vs. Capacity Expansion Needs
  Goal: Contrast the timing between both by corridor
Concept of a “fiscally constrained” Plan for Iowa’s Interstate System
Balancing Design and $$
Workshop Summer 2018
2 Days - 70 Participants

## Slide 4
Stewardship - All participants recommended the focus should be on preservation treatments to keep the system in its current state of good repair.
Consider Technology Options First - Expansion projects in urban corridors will be limited and focus on technology solutions and other management strategies before adding lanes.
  Transportation Systems Management & Operations (TSMO)
  Integrated Corridor Management (ICM)
Widening Options - Many segments of Interstate have significant pavement life remaining, so adding capacity in those areas will first consider widening the existing pavement rather than a complete rebuild.
Workshop Recommendations

## Slide 5
Initial Plan Result
Chart: Project Total vs Budget Through Interstate Plan Year 2040
| 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Project Costs | 349000000 | 422400000 | 339600000 | 382400000 | 324900000 | 237300000 | 302875642.78 | 376958627.94 | 265924713.74 | 286677024.35 | 289305467.07 | 310762120.44 | 325097533.03 | 301760657.05 | 496243735.28 | 493416351.16 | 590095614.31 | 494747613.21 | 418562355.52 | 500749680.48 | 227550000 | 423661000 | 140030000
Budget | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000
$330 Million Annual Budget
Project Budgets Set Very Tight to Promote Right Sizing

## Slide 6
2024 Project Totals and Annual Budget
Project Budgets Set Very Tight to Promote Right Sizing
$330 Million Annual Budget
Program Years

## Slide 7
Proposed Project Timing

## Slide 8
Proposed Project Timing

## Slide 9
Proposed Project Timing

## Slide 10
I-29 Madison Ave Interchange – Programmed (2025-2026)
I-80 Middle Road Interchange – Programmed 2026
I-80 Hickman Road Interchange – Programmed (2025-2026)
Other Notable Interstate Work
I-80 Hickman Interchange
I-80 and Middle Road

## Slide 11
Des Moines NE Mixmaster Phases
Stage Timing
Stage 1/2 - Complete
Stage 3 – Currently under Construction
  EB to NB Flyover
  WB to NB Ramp
Stage 4 – 2039
  South I-235 Widening
Stage 5 – 2034
  West I-80 through Interchange
  Widening and Aux Lanes
Stage 6 – 2040
  I-80 WB to SB Flyover
Stage 7 – 2043
  North I-35 Widening
Stage 8 – 2048
  North I-35 SB to EB Flyover

## Slide 12
Des Moines NE Mixmaster Flyover Now Open

## Slide 13
Des Moines SW Mixmaster Phases
Phase Timing
Phases 1,2,3 – 2027 & 2028
  ROW in 2026
  Erosion Control in 2029
Phase 4 - 2038
Phase 5 - 2039
Phase 6 - 2040

## Slide 14
Interstate 35 – Polk/Story County
2026 - $53.5 million
2027 - $1.2 million
315th St
NE 36th St
Huxley
Ankeny
Reconstruction to 6-lanes
North of NE 36th St Ankeny to North of 315th St

## Slide 15
Interstate 35 Story County
South Skunk River Bridges
I-35 Mainline Bridges Over Skunk River Completed
I-35 Alignment Shift:
  Construction
  Traffic Management
I-35

## Slide 16
Interstate 35 Ames
I-35 Mainline Bridges over US 30
N of Co Rd E57/260th St to 0.6 mi N of US 30
2027 - $6.9 million (ROW)
2028 - $11.6 million
2029 - $31.9 million
2030 - $26.6 million
2031 - $1.2 million
I-35

## Slide 17
Interstate 35 – Story County
Reconstruction to 6-lanes
North of 315th St to 260th St
2030 - $2.0 million
2031 - $6.0 million
2032 - $38.3 million
2033 - $37.0 million
I-35
Huxley
Ames
260th St
315th St

## Slide 18
Interstate 35 – Story County
Reconstruction to 6-lanes
North of US 30 to 13th St Ames
2035 - $30.2 million
2036 - $30.2 million
I-35
13th St
US-30

## Slide 19
Interstate 380 – Linn County
Reconstruction to 6-lanes
North of 120th St to South of US 30
(including Wright Bros Blvd interchange reconstruction)
2025 - $112.3 million
2026 - $1.6 million
120th ST
US 30

## Slide 20
Interstate 380 – Johnson/Linn County
Reconstruction to 6-lanes
North of Swan Lake Rd to North of 120th St
2029 - $7.9 million
2030 - $57.8 million
2031 - $56.3 million
2032 - $27.0 million
120th St
Swan Lake Rd

## Slide 21
Interstate 380 – Linn County
Boyson Road Interchange Reconstruction
Programmed for 2025
$24.1 million

## Slide 22
Interstate 80 – Scott County
Based on Timing of Capacity Need due to Traffic Volumes – I-80 Scott County corridor widening to 6-lanes moved to post 2050.
However, there are spot locations that may need to be addressed sooner than 2050.
  Below is an example of potential interchange improvements at I-80 and US 61 (southbound US 61 to eastbound I-80 flyover)
US 61
I-80

## Slide 23
Interstate 80 – Scott County
Mississippi River Bridge
US 61
I-80
PEL Study Completed
Phase 1 Engineering
  5 Public Meetings to Date
Preferred Alternative Chosen
Alt 5 – Companion Bridge West
Bike/Ped Facility Added
Two Years Programmed 2028-2029
Total Iowa Share $210 M
  Reflected in New Program
Illinois DOT - lead Agency

## Slide 24
Phil Mescher, AICP, CPM
515-233-7969
Phil.Mescher@iowadot.us​
iowadot.gov
Questions?