## Slide 1: IOWA INTERSTATE INVESTMENT PLAN 2040 WORKSHOP
Matt Haubrich
Deanna Maifield

## Slide 2: Interstate Needs – as calculated during the workshop
$330m
or
50% of
current
program
Interstate Needs by Year
Notes: At the end of the workshop, it was evident that the there was ideal solution

## Slide 3: Since the Workshop
Quality review of the concepts
Refine cost estimates
Additional reductions in the scope of work for projects
Delayed potential projects to fit within available funding levels

## Slide 4: System Goals
Maintain pavement and bridge conditions
as they are today
Provide capacity expansion according to the mapped priorities
Look to innovative solutions to maximize the life of our system
Limit spending to 50% of our current funding
Minimize project costs today by focusing on the immediate issues and keeping a narrow scope of work
Notes: Most important slide

## Slide 5: Where We Are Today- a baseline
Chart: Project Total vs Budget Through Interstate Plan Year 2040
| 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Project Costs | 349000000 | 422400000 | 339600000 | 382400000 | 324900000 | 237300000 | 302875642.78 | 376958627.94 | 265924713.74 | 286677024.35 | 289305467.07 | 310762120.44 | 325097533.03 | 301760657.05 | 496243735.28 | 493416351.16 | 590095614.31 | 494747613.21 | 418562355.52 | 500749680.48 | 227550000 | 423661000 | 140030000
Budget | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000 | 330000000

## Slide 6: Purpose of Today’s Conversation
Not the map, but the process
Goals are defined
Project teams develop projects that align with the goals
Goals will be adjusted and communicated as things change
Notes: Before we jump into the maps I’d like to talk about the purpose of today’s conversation
  The maps represent the amount of capacity expansion we can complete in a year, and a reasonable start for prioritizing based upon traffic volumes and condition

## Slide 7: Define / Monitor / Adjust Cycle
Prioritize capacity improvement projects and schedule corridors
Manage and deliver individual projects to meet the defined goals
Develop dashboards to monitor progress and key assumptions
Refresh cost, schedule and condition data and provide updates
Notes: Key Message

## Slide 8: Proposed Capacity Expansion Priorities

## Slide 9: Proposed Capacity Expansion Priorities
DeSoto
Ames
Colfax
Kellogg
Marengo
Durant
US 30

## Slide 10: Results
Budget was only balanced to 2031
Many segments were delayed beyond 2031 and do not fit within the budget
Currently recommend holding to the $330m budget for interstate funding
Notes: Key Message

## Slide 11: The Budget – flat funding and 50% to Interstate
Chart: Historical Percent of Program Dollars Invested in Iowa Interstates
| 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Interstate | 0.25 | 0.39 | 0.3 | 0.41 | 0.43 | 0.35 | 0.4 | 0.39 | 0.39 | 0.56 | 0.42 | 0.47 | 0.4 | 0.34 | 0.47 | 0.57 | 0.51 | 0.56 | 0.51 | 0.39
Non-Interstate | 0.75 | 0.61 | 0.7 | 0.59 | 0.57 | 0.65 | 0.6 | 0.61 | 0.61 | 0.44 | 0.58 | 0.53 | 0.6 | 0.66 | 0.53 | 0.43 | 0.49 | 0.44 | 0.49 | 0.61
Target | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## Slide 12: Results
Budget was only balanced to 2031
Many segments were delayed beyond 2031 and do not fit within the budget
Currently recommend holding to the $330m budget for interstate funding
Establish budgets for each segment
Notes: Key Message

## Slide 13: Budgets
Stewardship projects were funded to maintain current condition
Budgets do not allow projects to include all of the approaches or features that most include today.
Notes: Budgets were set relatively tight
We will expect the project teams to find the best value solutions for each location
But here are some examples of the Cadillac vs Chevy adage

## Slide 14: Ideal Interstate Design
Future
Existing Roadway

## Slide 15: Ideal Interstate Construction Sequence (animated in next 7 slides)

## Slide 22: Cost Saving Examples
Preserve Existing Pavement
Notes: Examples- not prescriptive or all inclusive

## Slide 23
Narrow Median through Existing Bridges
- Also reduces sideroad and interchange work
Cost Saving Examples

## Slide 24
Add future lanes by repainting
Don’t flatten existing foreslopes
Cost Saving Examples

## Slide 25: What are we committing to
Not the map, but the process
Goals are defined
Project teams develop projects that align with the goals
Goals will be adjusted and communicated as things change
Notes: Key Message

## Slide 26: Thank You