## Slide 1: 2020-2024 Highway Program Development
February 11, 2019

## Slide 2
Overview
  Discuss Highway Program Development Process
  Discuss 2020-2024 Highway Program Development Schedule
  Discuss Extended Highway Program Analysis
  Discuss Statewide Line Items
  At what levels should the line item targets be programmed?
  Discuss Federal Funding
  Discuss Program Objectives/Priorities/Considerations
  Action Item: Project Prioritization Weighting
February 11, 2019

## Slide 3: Highway Program Development Process
Public Policy and Input
What direction do we have?
Transportation Plans
What type of system do we need?
Performance Monitoring
Are we successful?
Five-Year Program
What projects will be done and when?
February 11, 2019

## Slide 4
Step 1: Project identification
February 11, 2019

## Slide 5
Step 2: Establishing the Transportation Commission’s annual programming objectives
February 11, 2019

## Slide 6
Step 3: Evaluating potential project candidates
February 11, 2019

## Slide 7
Step 4: Developing the final program
February 11, 2019

## Slide 8
Commission Program Development Schedule (2020-2024)
  February 2019
  Discuss Highway Program Development Process
  Discuss 2020-2024 Highway Program Development Schedule
  Discuss Extended Highway Program Analysis
  Discuss Statewide Line Items
  At what levels should the line item targets be programmed?
  Discuss Federal Funding
  Discuss Program Objectives/Priorities/Considerations
  Action Item: Project Prioritization Weighting
  March 2019
  Discuss 2020-2024 available Highway Program funding
  Discuss 2020-2024 Highway Program Options
  Determine 2020-2024 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2019
  Develop the Draft 2020-2024 Highway Program
  Action Item: 2020-2024 Highway Program Objectives
  May 2019
  Present the Draft 2020-2024 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2020–2024 Highway Program)
  June 2019
  Action Item: Approve the 2020–2024 Iowa Transportation Improvement Program
February 11, 2019

## Slide 9
Projected Funds 722.6 649.3 643.2 633.7 657.7 657.7 657.7 657.7 657.7 657.7
Highway Program Components
Interstate Stewardship 202.6 148.2 173.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0
Non-Interstate Pavement Modernization 95.4 100.0 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0
Non-Interstate Bridge Modernization 54.4 54.7 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0
Safety Specific 19.7 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 150.0 155.6 110.4 106.5 166.7
IA 9 Allamakee Mississippi River Bridge 40.0
IA 17 Boone N of US 30 and E 3 mi 6.0 0.1
US 30 Story E of I-35 to E of 600th Ave 0.3
US 30 Benton from IA 21 to US 218 0.2
US 61 Des Moines from 210th St to N of Mediapolis 14.6 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 3.7 23.5 0.1
IA 92 Washington/Louisa from US 218 to IA 70 0.2
Major Interstate Capacity/System Enhancement 219.8 191.4 209.3 150.3 95.6
I-35 Polk/Story 30.5 52.5 1.0
I-80 Cedar 33.0 34.0
I-80 Scott Mississippi River Bridge 100.0
Highway Program Balance (19.3) (25.6) (36.7) (3.5) (17.3) (0.8) 97.5 181.6 152.7 122.7
Approved Highway Program Extended Highway Program
2019 2020 2021 2022 2023 2024 2025 2026 2027 2028
2019-2028 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Approved by the Commission as of June 12, 2018, or implied commitment by the Commission by an established target amount or multi-year project
    ( ): Indicates Highway Program is over-programmed
February 11, 2019
(as shown May 8, 2018)

## Slide 10
Projected Funds 649.3 643.2 633.7 657.7 657.7 657.7 657.7 657.7 657.7 657.7
Highway Program Components
Interstate Stewardship 148.2 173.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0 185.0
Non-Interstate Pavement Modernization 100.0 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0 170.0
Non-Interstate Bridge Modernization 54.7 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0 185.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 155.6 110.4 106.5 166.7
IA 9 Allamakee Mississippi River Bridge 40.0
IA 17 Boone N of US 30 and E 3 mi 6.0 0.1
US 30 Story E of I-35 to E of 600th Ave 0.3
US 30 Benton from IA 21 to US 218 0.2
US 61 Des Moines from 210th St to N of Mediapolis 14.6 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 3.7 23.5 0.1
IA 92 Washington/Louisa from US 218 to IA 70 0.2
Major Interstate Capacity/System Enhancement 191.4 209.3 150.3 95.6
I-35 Polk/Story 30.5 52.5 1.0
I-80 Cedar 33.0 34.0
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance (25.6) (36.7) (3.5) (17.3) 99.2 (52.5) 181.6 152.7 122.7 92.7
Proposed Highway Program Extended Highway Program
2020 2021 2022 2023 2024 2025 2026 2027 2028 2029
2020-2029 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Approved by the Commission as of June 12, 2018, or implied commitment by the Commission by an established target amount or multi-year project
    Green: Changes since previous discussion
    ( ): Indicates Highway Program is over-programmed
February 11, 2019

## Slide 11
 | DRAFT 2020 - 2024 IOWA HIGHWAY PROGRAM |  |  |  |  |  |  | 
 |  |  |  | PROJECT ESTIMATED COSTS X $1000 |  |  |  | 
 | LOCATION | FUNDING | TYPE OF WORK | 2020 | 2021 | 2022 | 2023 | 2024
 | (00) STATEWIDE |  |  |  |  |  |  | 
 | STATEWIDE INTERSTATE PAVEMENT MAINTENANCE | 4R | PAVEMENT REHAB | 9500 | 9500 | 9500 | 9500 | 9500
 | STATEWIDE INTERSTATE GUARDRAIL REPAIR | 4R | GUARDRAIL REPAIR | 650 | 650 | 650 | 650 | 650
 | STATEWIDE INTERSTATE LIGHTING | 4R | LIGHTING | 500 | 500 | 500 | 500 | 500
 | STATEWIDE INTERSTATE REST AREA MAINTENANCE | 4R | REST AREA IMPROVE | 3700 | 3700 | 3700 | 3700 | 3700
 | STATEWIDE INTERSTATE SIGNING | 4R | TRAFFIC SIGNS | 1000 | 1000 | 1000 | 1000 | 1000
 | NON-INTERSTATE PAVEMENT PRESERVATION | 3R | PAVEMENT REHAB |  | 105000 | 115000 | 125000 | 130000
 | STATEWIDE SAFETY SPECIFIC | SR | MISCELLANEOUS |  | 25000 | 25000 | 25000 | 25000
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
 | EMERGENCY & CONTINGENCY - U-STEP/C-STEP |  | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 10000 | 10000 | 10000 | 10000 | 10000
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 300 | 300 | 300 | 300 | 300
 | SCENIC BYWAY PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 80000 | 80000 | 80000 | 80000 | 80000
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 31350 | 31350 | 31350 | 31350 | 31350
 | STATEWIDE RAILROAD CROSSINGS |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE ROADSIDE IMPROVEMENT |  | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE TRAFFIC CONTROL DEVICES |  | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000
 | ABBREVIATIONS |  |  |  |  |  |  | 
 | 4R - INTERSTATE STEWARDSHIP |  |  |  |  |  |  | 
 | 3R - NON-INTERSTATE PAVEMENT MODERNIZATION |  |  |  |  |  |  | 
 | SR - SAFETY SPECIFIC |  |  |  |  |  |  | 
  At what levels should the line item targets in the blue box be programmed?

## Slide 12
Federal Funding Status
The FAST Act authorizes federal funding through September 30, 2020.
Core programs remain in place with some growth in funding.
FAST Act funding allocations were determined by Commission in 2016.
The next Highway Trust Fund cliff is in 2021, leaving uncertainty in the last four years of this next five-year program.
Contingency plan has been developed should significant reduction in federal funding occur. Consider identifying specific project impacts with this Program.
Currently operating under a continuing resolution through Feb. 15. There were no immediate impacts on federal highway funding due to the shutdown.

## Slide 13
Current Highway Program Objectives
  Stewardship Investments
  Interstate (Pavement Reconstruction/Modernization, Bridges, Pavement Patching/Maint., Rest Areas/Misc.)
  - Maintain scheduled completion of I-35 in Polk County from Oralabor Road to NE 36th St. in Ankeny
  - Maintain scheduled completion of I-35/80 Interchange NE of Des Moines in Polk County
  - Maintain scheduled completion of I-80 in Polk County at Iowa 141 interchange in Urbandale
  - Maintain scheduled completion of I-80/380 interchange reconstruction in Johnson County
  Non-Interstate Pavement Modernization
  Non-Interstate Bridge Modernization
  Safety
  Major Interstate Capacity/System Enhancement Projects
  Maintain scheduled completion of I-29/I-80/I-480 in Council Bluffs (CBIS)
  Maintain scheduled completion of I-74 in Davenport/Bettendorf (Central Section)
  Maintain scheduled completion of I-80 in Johnson/Cedar Counties
  Maintain scheduled completion of I-380 in Linn County for Tower Terrace
  Non-Interstate Capacity/System Enhancement Projects
  Maintain scheduled completion of Iowa 1 in Jefferson County in Fairfield
  Maintain scheduled completion of Iowa 3 in Dubuque County from Luxemburg to Sageville
  Maintain scheduled completion of Iowa 13 in Linn County from N of County Home Rd to S of Central City
  Maintain scheduled completion of Iowa 14 in Marshall and Grundy Counties from Co Rd E18 to Iowa 175
  Maintain scheduled completion of Iowa 17 in Boone County north of U.S. 30
  Maintain scheduled completion of U.S. 18 in Floyd County at the U.S. 218 intersection in Floyd
  Maintain scheduled completion of U.S. 20 in Webster County from E of Co Rd P73 to Iowa 17
  Maintain scheduled completion of U.S. 20 in Black Hawk County from Iowa 21 to I-380 in Waterloo
  Maintain scheduled completion of U.S. 20 in Dubuque County at Swiss Valley Road intersection
  Maintain scheduled completion of U.S. 30 in Story County from 0.5 miles east of I-35 to east of 590th Ave
  Maintain scheduled completion of U.S. 30 in Tama and Benton Counties
  Maintain scheduled completion of U.S. 52 in Jackson County from the Mississippi River to Sabula
  Maintain scheduled completion of U.S. 61 in Des Moines County from Burlington to N of Mediapolis
  Maintain scheduled completion of U.S. 69 in Polk County from I-80 to SE 33rd St in Ankeny
  Maintain scheduled completion of U.S. 69 in Wright County from N of UP RR to Co Rd C20
  Maintain scheduled completion of U.S. 75 in Plymouth County from Hinton to Merrill
  Maintain scheduled completion of Iowa 92 in Washington and Louisa Counties
February 11, 2019

## Slide 14
Program Development Considerations
  Continue to increase stewardship investments on existing highway system (i.e., bridges, pavements, safety)
  Balance capacity improvements with stewardship needs
  Address increasing safety/operational needs on the Interstate
    I-35 in central Iowa
    I-80 in eastern Iowa
    I-380 from Iowa City to Cedar Rapids
  Address major river crossing needs
  Continue to complete existing priority corridors
February 11, 2019

## Slide 15
Program Development Considerations
  Review existing priority corridors and determine if changes are necessary
    U.S. 30 in Harrison County for Missouri Valley bypass
    U.S. 30 in Greene/Boone Counties from Jefferson to Ogden
    U.S. 30 in Cedar County from Lisbon to Stanwood
    U.S. 30 in Clinton County from Calamus to U.S. 61
    U.S. 61 in Des Moines/Louisa Counties from 0.5 miles north of Iowa 78 to 2.0
    miles south of Iowa 92
    U.S. 63 in Davis/Wapello Counties from North of Bloomfield to Ottumwa
February 11, 2019

## Slide 16
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Total
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  |  | 
IA 1 Johnson: SB in Iowa City from Burlington to N Dodge St |  |  |  | 3.1 |  |  |  |  |  |  | 3.1
IA 9 Allamakee: Mississippi River Bridge (state share) |  |  |  |  | 40.0 |  |  |  |  |  | 40.0
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  |  |  |  |  | TBD |  |  | TBD
IA 13 Delaware: N of Co Rd D13 to S Jct IA 3 |  |  |  |  | 10.0 |  |  |  |  |  | 10.0
IA 21 Iowa: South of Belle Plaine |  |  |  |  | TBD |  |  |  |  |  | TBD
US 20 Woodbury: US 75 in Sioux City to Little Whiskey Creek (EB/WB) |  |  |  | 11.0 |  |  |  |  |  |  | 11.0
US 20 Black Hawk: Hudson Rd to US 63 (EB/WB) |  |  |  | 14.1 |  |  |  |  |  |  | 14.1
US 30 Story: Co Rd S-14 in Nevada |  |  |  |  | 4.0 |  |  |  |  |  | 4.0
US 34 Montgomery: W of IA 48 to Co Rd H34 |  |  |  | 12.0 |  |  |  |  |  |  | 12.0
IA 38 Cedar: SCL to NCL in Tipton (state share) |  | 2.1 |  |  |  |  |  |  |  |  | 2.1
IA 44 Dallas: At Co Rd R30 2 mi W of Grimes (state share) | 0.3 |  |  |  |  |  |  |  |  |  | 0.3
US 63 Poweshiek: W Jct US 6 to SCL of Tama |  |  |  |  | 10.0 |  |  |  |  |  | 10.0
IA 64 Jackson: US 61 to IA 62 in Maquoketa (state share) |  | 3.6 |  |  |  |  |  |  |  |  | 3.6
US 65 Cerro Gordo: 0.1 mi S of 27th St SW to 6th St S in Mason City |  |  |  |  | 11.1 |  |  |  |  |  | 11.1
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  |  |  |  | 110.0 | 110.0
US 71 Dickinson: Okoboji Grove Rd in Arnolds Park to East View Ave |  |  |  | 11.7 |  |  |  |  |  |  | 11.7
US 75 Plymouth: Woodbury Co to S of W Grover St in Hinton (SB) | 12.9 |  |  |  |  |  |  |  |  |  | 11.9
US 75 Sioux: In Sioux Center pavement replacement (state share) |  |  | 0.3 | 13.0 | 7.0 |  |  |  |  |  | 20.3
US 75 Sioux: N of Sioux Center to US 18 |  |  |  |  |  | 10.0 |  |  |  |  | 10.0
IA 150 Buchanan: In Independence from 8th St to CN RR |  |  | 3.8 |  |  |  |  |  |  |  | 3.8
US 151 Linn: Co Rd X20 in Springville |  |  | 8.3 | 14.4 | 0.3 |  |  |  |  |  | 23.0
IA 141 Polk: NW 121st St intersection including local road connections |  |  |  |  | 7.8 |  |  |  |  |  | 7.8
IA 160 Polk: DMACC Blvd in Ankeny (state share) | 0.5 |  |  |  |  |  |  |  |  |  | 0.5
IA 415 Polk: Co Rd R6F/NW Beaver Dr 1.5 mi NE of IA 141 (state share) |  | 0.4 |  |  |  |  |  |  |  |  | 0.4
IA 922 Linn: 29th to 31st St NE in Cedar Rapids (state share) | 0.5 |  |  |  |  |  |  |  |  |  | 0.5
ITS (multiple locations statewide) | 0.8 |  |  | 0.8 |  |  |  |  |  |  | 1.6
Culverts (multiple locations statewide) | 1.8 | 1.0 | 0.8 | 0.8 |  |  |  |  |  |  | 4.4
Slide Repairs (multiple locations statewide) | 0.9 | 1.0 |  |  |  |  |  |  |  |  | 1.9
Jasper: Traffic Incident Management (TIM) Training Center | TBD | TBD |  |  |  |  |  |  |  |  | 11.8
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available

## Slide 17
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Total
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 30 Harrison: Missouri Valley bypass |  |  |  |  | 10.5 | 43.5 | 18.5 | 17.9 | 0.5 |  | 90.9
US 30 Tama: Meskwaki interchange |  |  |  |  |  |  |  |  |  |  | TBD
US 61 Louisa: 1 mi N of IA 78 to 2 mi S of IA 92 |  |  |  |  | 5.8 | 37.1 |  | 16.2 | 29.6 | 19.3 | 108.0
US 63 Mahaska: Bypass NW of Oskaloosa |  |  |  |  | 6.1 | 14.7 | 18.7 | 0.3 |  |  | 39.8
US 218 Bremer: Cedar River in Janesville to IA 116 in Waverly |  |  |  |  | 18.8 | 12.9 |  |  |  |  | 31.7
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  |  |  | TBD |  |  |  |  |  |  | TBD
IA 78 Henry: Olds to Louisa County | 13.7 |  |  |  |  |  |  |  |  |  | 13.7
IA 78 Louisa: Henry County to US 61 | 8.4 |  |  |  |  |  |  |  |  |  | 8.4
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available

## Slide 18
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Total
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  |  |  | 45.0 | 50.0 | 25.0 |  | 120.0
I-74 Scott: In Bettendorf from N of Lincoln Rd to S of US 6 |  |  |  |  |  | 59.5 |  |  |  |  | 59.5
I-74 Scott: US 6 Interchange in Davenport (reconstruction) |  |  |  |  |  |  | 24.9 |  |  |  | 24.9
I-74 Scott: In Davenport from S of US 6 to 67th St |  |  |  |  |  |  |  | 63.7 |  |  | 63.7
I-80 Polk: I-35/235 to US 65 near Altoona |  |  |  |  |  |  | 27.9 | 28.9 |  |  | 56.8
I-80 Polk/Jasper: Altoona to Colfax |  |  |  |  |  |  |  |  |  | TBD | TBD
I-80 Iowa/Johnson: US 151 to I-380 |  |  |  |  |  |  |  |  |  | TBD | TBD
I-80 Cedar: 0.5 mi E of Co Rd X30 to E of the Cedar River |  |  |  |  |  |  |  | 40.0 | 45.0 | 45.0 | 130.0
I-80 Cedar/Scott: 0.5 mi W of Co Rd Y26 to I-280 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: I-280 to US 61 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: US 61 to W of Middle Road in Bettendorf |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: W of Middle Road in Bettendorf to Mississippi River |  |  |  |  | TBD | TBD |  |  |  |  | TBD
I-80 Scott: Mississippi River Bridge |  |  |  |  |  | 150.0 |  |  |  |  | 150.0
I-380 Johnson: Forevergreen Rd to S of Co Rd F12 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-380 Johnson/Linn: S of Co Rd F12 to US 30 |  |  |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  | TBD | TBD |  |  | TBD
Stewardship (Shelf-Ready) Projects |  | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  | 500.0
    Subject to change as additional information becomes available

## Slide 19: Next Steps
Discuss 2020-2024 available Highway Program funding
Discuss 2020-2024 Highway Program Options
Determine 2020-2024 Highway Program Objectives
Action Item: Line Item Targets for Programming
February 11, 2019