## Slide 1: 2022-2026 Highway Program Development
February 9, 2021

## Slide 2
Overview
  Discuss Highway Program Development Process
  Discuss 2022-2026 Highway Program Development Schedule
  Discuss Extended Highway Program Analysis
  Discuss Statewide Line Items
  At what levels should the line item targets be programmed?
  Discuss Federal Funding
  Discuss Program Objectives/Priorities/Considerations
February 9, 2021

## Slide 3: Highway Program Development Process
Public Policy and Input
What direction do we have?
Transportation Plans
What type of system do we need?
Performance Monitoring
Are we successful?
Five-Year Program
What projects will be done and when?
February 9, 2021

## Slide 4
Step 1: Project identification
February 9, 2021

## Slide 5
Step 2: Establishing the Transportation Commission’s annual programming objectives
February 9, 2021

## Slide 6
Step 3: Evaluating potential project candidates
February 9, 2021

## Slide 7
Step 4: Developing the final program
February 9, 2021

## Slide 8
Commission Program Development Schedule (2022-2026)
  February 2021
  Discuss Highway Program Development Process
  Discuss 2022-2026 Highway Program Development Schedule
  Discuss Extended Highway Program Analysis
  Discuss Statewide Line Items
  At what levels should the line item targets be programmed?
  Discuss Federal Funding
  Discuss Program Objectives/Priorities/Considerations
  March 2021
  Discuss 2022-2026 available Highway Program funding
  Discuss 2022-2026 Highway Program Options
  Determine 2022-2026 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2021
  Develop the Draft 2022-2026 Highway Program
  Action Item: 2022-2026 Highway Program Objectives
  May 2021
  Present the Draft 2022-2026 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2022–2026 Highway Program)
  June 2021
  Action Item: Approve the 2022–2026 Iowa Transportation Improvement Program
February 9, 2021

## Slide 9
Projected Funds as of March 2020 826.3 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 242.1 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0
Non-Interstate Pavement Modernization 105.7 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 64.1 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0
Safety Specific 25.6 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 125.0 137.8 226.7 217.6 102.1
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 280.1 200.5 111.8 68.9 125.4
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Cedar (scaled back to just include replacement of Sugar Creek bridges)
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (16.3) (50.1) (50.3) (25.0) (19.5) 51.4 87.8 84.7 106.2 91.2
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
February 9, 2021
as presented May 12, 2020

## Slide 10
Projected Funds as of March 2020 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0
Safety Specific 25.6 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 137.8 226.7 217.6 102.1
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 200.5 111.8 68.9 125.4
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Cedar (scaled back to just include replacement of Sugar Creek bridges)
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (50.1) (50.3) (25.0) (19.5) 51.4 87.8 84.7 106.2 91.2
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
February 9, 2021

## Slide 11
 | DRAFT 2022 - 2026 IOWA HIGHWAY PROGRAM |  |  |  |  |  |  | 
 |  |  |  | PROJECT ESTIMATED COSTS X $1000 |  |  |  | 
 | LOCATION | FUNDING | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 1000 | 1000 | 1000 | 1000 | 1000
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 250 | 500 | 750 | 1000 | 1000
 | EMERGENCY & CONTINGENCY - U-STEP/C-STEP |  | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 20000 | 20000 | 20000 | 20000 | 20000
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 360 | 360 | 360 | 360 | 360
 | SCENIC BYWAY PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 85000 | 85000 | 85000 | 85000 | 85000
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 35350 | 35350 | 35350 | 35350 | 35350
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 500 | 1000 | 1500 | 2000 | 2500
 | STATEWIDE RAILROAD CROSSINGS |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE ROADSIDE IMPROVEMENT |  | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE TRAFFIC CONTROL DEVICES |  | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000
  At what levels should the line item targets be programmed?
February 9, 2021

## Slide 12
  Projects in the 2021-2024 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
FY 2021-2025 Highway Program Objectives
February 9, 2021
as approved April 14, 2020

## Slide 13
Federal Funding Status
The FAST Act authorizes federal funding through September 30, 2021.
FAST Act funding allocations were determined by Commission in 2016.
The next Highway Trust Fund cliff is in 2022, leaving uncertainty in all but one year of this next five-year program.
Contingency plan has been developed should significant reduction in federal funding occur. Continue to identify specific project impacts with this Program.
Recent annual appropriations have included additional funding beyond authorized levels.
February 9, 2021

## Slide 14
Program Development Considerations
  Long-term COVID-19 impacts on state RUTF
  Negative program balances in FY 2022
  Continue to increase bridge and pavement stewardship investments on existing highway system
  Increase safety target
  Balance capacity improvements with stewardship needs
  Address increasing safety/operational needs on the Interstate
  Address major river crossing needs
  Continue to complete existing priority corridors
February 11, 2020

## Slide 15
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Beyond | Total | Score | Rank
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  | 4.9 | 30.7 | 39.3 | 67.6 | 1.2 |  | 143.7 |  | 
I-80 Scott: Middle Road Interchange (4R or MI) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-380 Johnson: Segment 1 N of Forevergreen Rd to N of Penn St |  | 8.3 | 10.5 | 11.0 |  |  |  |  |  |  | 29.8 |  | 
I-380 Johnson: Segment 2 N of Penn St to N of Iowa River |  |  |  |  |  |  |  | 40.0 | 46.1 | 27.0 | 113.1 |  | 
I-380 Johnson: Segment 3 N of Iowa River to N of 120th St NW |  |  |  |  |  |  | 17.8 | 10.2 |  |  | 28.0 |  | 
I-380 Linn: Segment 4 N of 120th St NW to US 30 |  |  |  |  |  | 33.5 | 19.2 |  |  |  | 52.7 |  | 
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  |  |  | 15.4 | 32.5 | 47.9 |  | 
Stewardship (Shelf-Ready) Projects | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  |  | 500.0 |  | 
    Subject to change as additional information becomes available
February 9, 2021

## Slide 16
 |  |  |  |  |  |  |  |  |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 2 Fremont: Resiliency improvements (Phase II) IA 12 Woodbury: Gordon Drive bridge in Sioux City |  | 3.5 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | TBD |  |  | 
IA 21 Iowa: South of Belle Plaine |  |  |  | 5.0 |  |  |  |  |  | 
US 34 Mills: Resiliency improvements (could be ER) | TBD |  |  |  |  |  |  |  |  | 
US 34 Wapello: Wildwood Dr to US 63 in Ottumwa |  |  |  |  | 30.8 |  |  |  |  | 
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  |  | 
US 75 Sioux: N of Sioux Center to US 18 |  |  |  | 10.0 |  |  |  |  |  | 
IA 76 Clayton: McGregor | 4.5 |  |  |  |  |  |  |  |  | 
Polk: Traffic Incident Management (TIM) Training Center |  |  | TBD | TBD |  |  |  |  |  | 
ITS (multiple locations statewide) | TBD |  |  |  |  |  |  |  |  | 
Culverts (multiple locations statewide) | TBD |  |  |  |  |  |  |  |  | 
Slide Repairs (multiple locations statewide) | TBD |  |  |  |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
February 9, 2021

## Slide 17
 |  |  |  |  |  |  |  |  | Priority |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Corridor | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 18 Kossuth/Hancock: East of Algona to Hutchins (Super-2) | 5.5 |  |  |  |  |  |  |  | N |  | 
US 30 Cedar/Clinton: ECL Mechanicsville to ECL Clarence (Super-2) |  |  |  |  | TBD | TBD |  |  | Y |  | 
US 63 Tama: Toledo to Co Rd E29 (Super-2) |  |  |  | 9.0 |  |  |  |  | N |  | 
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  | 13.0 |  |  |  |  |  |  |  |  | 
IA 81 Van Buren: Missouri State Line to IA 2 | TBD |  |  |  |  |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
February 9, 2021

## Slide 18: Next Steps
Discuss 2022-2026 available Highway Program funding
Discuss 2022-2026 Highway Program Options
Determine 2022-2026 Highway Program Objectives
Action Item: Line Item Targets for Programming
February 9, 2021