## Options
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000) | [13 empty] | Commission Weight | 18% | 10% | 12% | 16% | 15% | 15% | 14%
[14 empty] | IDOT Staff Weight | 17% | 10% | 11% | 15% | 17% | 14% | 16%
Non-Interstate Capacity/System Enhancement (NR funds) | [11 empty] | 2018-12-01 |  | FAC Weight | 18% | 11% | 14% | 14% | 14% | 15% | 14%
Stewardship |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Total |  |  | Safety | Road Class | Freight | Pavement | Bridge | Traffic | Mobility | Commission | IDOT Staff Overall | FAC
PIN | Location | [11 empty] | District | Category | [7 empty] | Overall |  | Overall
16-03-009-010 | IA 9 Allamakee: Mississippi River Bridge (state share) | 2024: 40 |  | 40 | 2 | NR Stewardship | 73 | 50 | 92 | 40 | 16 | 91 | 99 | 65.49 | 65 | 66.87
19-97-012-010 | IA 12 Woodbury: Gordon Drive bridge in Sioux City | 2027: TBD |  | TBD | 3 | NR Stewardship | 10 | 20 | 38 | 58 | 13 | 58 | 50 | 35.29 | 36 | 34.96
18-28-013-010 | IA 13 Delaware: N of Co Rd D13 to S Jct IA 3 | 2024: 20 |  | 20 | 2 | NR Stewardship | 88 | 30 | 92 | 38 | 83 | 90 | 99 | 75.77 | 76 | 76.32
17-97-020-010 | US 20 Woodbury: US 75 in Sioux City to Little Whiskey Creek (EB/WB) | 2024: 11 |  | 11 | 3 | NR Stewardship | 38 | 14 | 52 | 68 | 74 | 71 | 71 | 57.05 | 58 | 56.13
16-07-020-030 | US 20 Black Hawk: Hudson Rd to US 63 (EB/WB) | 2023: 14.1 |  | 14.1 | 2 | NR Stewardship | 54 | 30 | 45 | 62 | 82 | 54 | 71 | 58.38 | 59 | 57.52
16-69-034-010 | US 34 Montgomery: W of IA 48 to Co Rd H34 | 2023: 12 |  | 12 | 4 | NR Stewardship | 46 | 20 | 67 | 68 | 52 | 81 | 81 | 60.49 | 61 | 60.15
19-16-038-010 | IA 38 Cedar: SCL to NCL in Tipton (state share) | 2021: 2.1 |  | 2.1 | 6 | NR Stewardship | 48 | 50 | 86 | 49 | 100 | 78 | 50 | 65.5 | 65 | 65.74
19-25-044-010 | IA 44 Dallas: At Co Rd R30 2 mi W of Grimes (state share) | 2020: 0.3 |  | 0.3 | 4 | NR Stewardship | 11 | 62 | 61 | 100 | 100 | 83 | 48 | 65.67 | 67 | 64.51
19-17-065-010 | US 65 Cerro Gordo: 0.1 mi S of 27th St SW to 6th St S in Mason City | 2024: 10 |  | 10 | 2 | NR Stewardship | 7 | 19 | 9 | 25 | 100 | 82 | 87 | 47.72 | 51 | 46.59
S0067-120618-01 | US 67 Scott: Mississippi River Bridge | [9 empty] | 110 | 110 | 6 | NR Stewardship | 3 | 42 | 26 | 46 | 22 | 12 | 81 | 31.66 | 33 | 31.46
17-30-071-010 | US 71 Dickinson: Okoboji Grove Rd in Arnolds Park to East View Ave | 2023: 11.7 |  | 11.7 | 3 | NR Stewardship | 11 | 31 | 71 | 66 | 65 | 65 | 91 | 56.4 | 58 | 56.16
16-75-075-020-01 | US 75 Plymouth: Woodbury Co to S of W Grover St in Hinton (SB) | 2020: 12.9 |  | 11.9 | 3 | NR Stewardship | 28 | 20 | 44 | 65 | 51 | 67 | 92 | 53.3 | 55 | 52.57
13-84-075-010 | US 75 Sioux: In Sioux Center pavement replacement (state share) | 2022: 0.3; 2023: 13; 2024: 7 |  | 20.3 | 3 | NR Stewardship | 12 | 30 | 52 | 70 | 100 | 76 | 83 | 60.62 | 63 | 59.56
17-84-075-010 | US 75 Sioux: N of Sioux Center to US 18 | 2025: 10 |  | 10 | 3 | NR Stewardship | 52 | 30 | 56 | 62 | 100 | 78 | 98 | 69.42 | 71 | 68.6
08-57-151-010 | US 151 Linn: Co Rd X20 in Springville | 2023: 14.4; 2024: 0.3 |  | 14.7 | 6 | NR Stewardship | 4 | 47 | 51 | 79 | 76 | 78 | 99 | 61.14 | 63 | 60.29
18-77-160-010 | IA 160 Polk: DMACC Blvd in Ankeny (state share) | 2020: 0.5 |  | 0.5 | 1 | NR Stewardship | 0 | 20 | 26 | 79 | 100 | 58 | 95 | 54.76 | 57 | 52.9
NA | ITS (multiple locations statewide) | 2020: 0.5; 2021: 2.5 |  | 3 | 0 | NR Stewardship | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
NA | Pipe Culverts (multiple locations statewide) | 2020: 1.4; 2021: 0.9; 2022: 0.8; 2023: 0.8 |  | 3.9 | 0 | NR Stewardship | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
NA | Slide Repairs (multiple locations statewide) | 2020: 0.8; 2021: 0.8 |  | 1.6 | 0 | NR Stewardship | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
NA | Jasper: Traffic Incident Management (TIM) Training Center | 2020: TBD; 2021: TBD |  | 11.8 | 1 | NR Stewardship | --- | --- | --- | --- | --- | --- | --- | --- | --- | ---
18-43-030-010 | US 30 Harrison: Missouri Valley bypass | 2024: TBD; 2025: TBD; 2026: TBD |  | 80 | 4 | NR Capacity | 45 | 31 | 71 | 63 | 74 | 73 | 50 | 58.85 | 59 | 58.58
08-86-030-010 | US 30 Tama: Meskwaki interchange | [10 empty] | TBD | 1 | NR Capacity | 2 | 43 | 64 | 85 | 100 | 84 | 97 | 67.12 | 69 | 66.13
11-58-061-010 | US 61 Louisa: 1 mi N of IA 78 to 2 mi S of IA 92 | 2024: 5.8; 2025: 37.1; 2027: 16.2; 2028: 29.6 | 19.3 | 108 | 5 | NR Capacity | 66 | 30 | 60 | 52 | 72 | 85 | 95 | 67.25 | 68 | 66.99
13-62-063-020 | US 63 Mahaska: Bypass NW of Oskaloosa | 2023: 4.5; 2024: 19.2; 2025: 18.7; 2026: 0.3 |  | 42.7 | 5 | NR Capacity | 57 | 30 | 63 | 62 | 78 | 82 | 94 | 67.9 | 69 | 67.44
06-07-218-010-02 | US 218 Bremer: Cedar River in Janesville to IA 116 in Waverly | 2024: 18.8; 2025: 12.9 |  | 31.7 | 2 | NR Capacity | 9 | 30 | 39 | 79 | 100 | 69 | 99 | 61.15 | 63 | 59.65
15-77-035-040-02 | I-35 Story: N of IA 210 to E 13th St in Ames | 2026: 45; 2027: 50; 2028: 25 |  | 120 | 1 | MI Capacity | 1 | 19 | 44 | 85 | 73 | 24 | 63 | 44.33 | 46 | 42.97
03-82-074-010-04 | I-74 Scott: In Bettendorf from N of Lincoln Rd to S of US 6 | 2025: 59.5 |  | 59.5 | 6 | MI Capacity | 0 | 10 | 20 | 78 | 70 | 42 | 50 | 39.68 | 41 | 37.92
03-82-074-010-06 | I-74 Scott: US 6 Interchange in Davenport (reconstruction) | 2026: 24.9 |  | 24.9 | 6 | MI Capacity | 48 | 27 | 53 | 77 | 70 | 49 | 47 | 54.45 | 55 | 53.54
03-82-074-010-05 | I-74 Scott: In Davenport from S of US 6 to 67th St | 2027: 63.7 |  | 63.7 | 6 | MI Capacity | 28 | 10 | 29 | 81 | 69 | 61 | 50 | 48.98 | 50 | 47.35
16-77-080-050 | I-80 Polk: I-35/235 to US 65 near Altoona | 2026: 27.9; 2027: 28.9 |  | 56.8 | 1 | MI Capacity | 10 | 17 | 3 | 83 | 78 | 25 | 71 | 42.53 | 45 | 40.32
S0080-052218-02 | I-80 Polk/Jasper: Altoona to Colfax | [9 empty] | TBD | TBD | 1 | MI Capacity | 16 | 28 | 16 | 77 | 73 | 3 | 42 | 37.2 | 38 | 35.53
S0080-052218-05 | I-80 Iowa/Johnson: US 151 to I-380 | [11 empty] | 6 | MI Capacity | 35 | 29 | 68 | 89 | 68 | 2 | 88 | 54.42 | 55 | 53.61
S0080-052218-09 | [10 empty] | TBD | TBD | 6 | MI Capacity | 48 | 26 | 75 | 83 | 58 | 2 | 49 | 49.38 | 49 | 48.9
S0080-052218-08 | I-80 Cedar: 0.5 mi E of Co Rd X30 to E of the Cedar River | 2027: 40; 2028: 45 | 45 | 130 | 6 | MI Capacity | 16 | 28 | 72 | 87 | 62 | 0 | 97 | 51.12 | 53 | 50.48
S0080-052218-04 | I-80 Cedar/Scott: 0.5 mi W of Co Rd Y26 to I-280 | 2027: TBD; 2028: TBD | TBD | TBD | 6 | MI Capacity | 40 | 27 | 36 | 82 | 59 | 1 | 48 | 43.06 | 43 | 41.82
19-82-080-010 | I-80 Scott: I-280 to US 61 | 2027: TBD; 2028: TBD | TBD | TBD | 6 | MI Capacity | 22 | 12 | 32 | 83 | 55 | 48 | 44 | 43.89 | 44 | 42.44
19-82-080-010 | I-80 Scott: US 61 to W of Middle Road in Bettendorf | 2027: TBD; 2028: TBD | TBD | TBD | 6 | MI Capacity | 22 | 12 | 32 | 83 | 55 | 48 | 44 | 43.89 | 44 | 42.44
19-82-080-010 | I-80 Scott: W of Middle Road in Bettendorf to Mississippi River | 2024: TBD; 2025: TBD |  | TBD | 6 | MI Capacity | 22 | 12 | 32 | 83 | 55 | 48 | 44 | 43.89 | 44 | 42.44
19-82-080-030 | I-80 Scott: Mississippi River Bridge | 2025: 150 |  | 150 | 6 | MI Capacity | 13 | 6 | 62 | 81 | 46 | 56 | 47 | 45.22 | 45 | 44.44
16-52-380-030 | I-380 Johnson: Forevergreen Rd to S of Co Rd F12 | 2027: TBD; 2028: TBD | TBD | TBD | 6 | MI Capacity | 2 | 22 | 41 | 88 | 71 | 21 | 35 | 40.26 | 41 | 38.83
16-52-380-030 | I-380 Johnson/Linn: S of Co Rd F12 to US 30 | 2025: TBD; 2026: TBD; 2027: TBD; 2028: TBD | TBD | TBD | 6 | MI Capacity | 2 | 22 | 41 | 88 | 71 | 21 | 35 | 40.26 | 41 | 38.83
96-57-380-050-03 | I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) | 2026: TBD; 2027: TBD |  | TBD | 6 | MI Capacity | 24 | 10 | 42 | 90 | 82 | 52 | 50 | 51.86 | 53 | 50.18