## Slide 1: Primary Road Fund Experience July 2018 to November 2018
Forecast PRF receipts $335.5 million
Actual PRF receipts $365.1 million
Difference +$29.6 million
previous difference reported +$18.2 million
Jan 8, 2019

## Slide 2: Project Costs vs. Programmed Amounts July 2018 to December 2018
Programmed Amounts $325.7 million
Project Costs $324.7 million
Difference +$1.0 million
previous difference reported +$6.2 million
Jan 8, 2019

## Slide 3: Program Balance (19.3) (June 2018) PRF Forecast Experience 29.6 (Nov 2018) Project Costs vs. Programmed Amounts 1.0 (Dec 2018) Program Balance 11.3 (Dec 2018) previous difference reported +$5.1 million
FY 2019 Highway Program Balance
(For Highway Planning Purposes) (x $1,000,000)
2019
Jan 8, 2019

## Slide 4
Chart: Amount Awarded vs Amount Programmed (monthly) (4R, 3R, BR, SR, NR, MI Projects)
| Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19 | Mar 19 | Apr 19 | May 19 | Jun 19
Amount Programmed ($) | 93423000 | 645000 | 7288000 | 112298000 | 28571000 | 83516000 | 57365000 | 95293000 | 38314000 | 11613000 | 22236000 | 158696000
Amount Awarded ($) | 102062838 | 888102 | 7507954 | 98602646 | 26919220 | 88791150 | 0 | 0 | 0 | 0 | 0 | 0
Chart: Cumulative Difference (Awarded vs. Programmed)
| Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18
Series 1 | -8639838 | -8882940 | -9102894 | 4592460 | 6244240 | 969090
Note:
June 2019 letting includes $88 million for cash flow portion of programmed amount for I-74 Mississippi River Bridge
Jan 8, 2019

## Slide 5
Construction Status
(mock-up for comment)

## Slide 6
Fiscal Year Overview
Revenue: Continues to fluctuate from month-to-month but overall higher than forecast and expect that to continue.
Lettings:
  46 percent of the Program has been let
  Approximately $383 m of work remains to be let
Construction has been slowed by winter weather until spring
Jan 8, 2019

## Slide 7
Primary Road Fund Balance
Primary Road Fund balance (Nov. 1): $252.5 million
  Previous month: $253.7 million
Lowest projected balance in FY 2019: $133.4 million in May 2019
  Previous month: $111.7 million in May 2019
Lowest projected balance in FY 2020: -$25.0 million in Nov. 2019
  Previous month: -$37.8 million in Nov. 2019
Current RISE Fund Balance: $55.4 million
  Previous month: $55.4 million
Jan 8, 2019