## Slide 1: Primary Road Fund Experience July 2018 to January 2019
Forecast PRF receipts $467.2 million
Actual PRF receipts $502.4 million
Difference +$35.2 million
previous difference reported +$35.4 million
Mar 12, 2019

## Slide 2: Project Costs vs. Programmed Amounts July 2018 to February 2019
Programmed Amounts $449.1 million
Project Costs $444.2 million
Difference +$4.9 million
previous difference reported -$0.5 million
Mar 12, 2019

## Slide 3: Program Balance (19.3) (June 2018) PRF Forecast Experience 35.2 (Jan 2019) Project Costs vs. Programmed Amounts 4.9 (Feb 2019) Program Balance 20.8 (Feb 2019) previous difference reported +$15.6 million
FY 2019 Highway Program Balance
(For Highway Planning Purposes) (x $1,000,000)
2019
Mar 12, 2019

## Slide 4
Chart: Amount Awarded vs Amount Programmed (monthly) (4R, 3R, BR, SR, NR, MI Projects)
| Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19 | Mar 19 | Apr 19 | May 19 | Jun 19
Amount Programmed ($) | 93423000 | 645000 | 7288000 | 112298000 | 28571000 | 83516000 | 52301000 | 71027000 | 39612000 | 18563000 | 41147000 | 160696000
Amount Awarded ($) | 102062838 | 888102 | 7507954 | 98602646 | 26919220 | 88791150 | 53782647 | 65624840 | 0 | 0 | 0 | 0
Chart: Cumulative Difference (Awarded vs. Programmed)
| Jul 18 | Aug 18 | Sep 18 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19
Series 1 | -8639838 | -8882940 | -9102894 | 4592460 | 6244240 | 969090 | -512557 | 4889603
Note:
June 2019 letting includes $88 million for cash flow portion of programmed amount for I-74 Mississippi River Bridge
Mar 12, 2019

## Slide 5
Fiscal Year Overview
Revenue: Continues to fluctuate from month-to-month but overall higher than forecast and expect that to continue.
Lettings:
  63 percent of the Program has been let
  Approximately $260 million of work remains to be let
Construction has been slowed by winter weather until spring
Mar 12, 2019

## Slide 6
Primary Road Fund Balance
March 12, 2019
Primary Road Fund balance (Jan. 1): $249.4 million
  Previous month: $221.5 million
Lowest projected balance in FY 2019: $176.3 million in May 2019
  Previous month: $146.5 million in May 2019
Lowest projected balance in FY 2020: $20.4 million in Nov. 2019
  Previous month: -$34.0 million in Nov. 2019
Current RISE Fund Balance: $50.9 million
  Previous month: $57.7 million