## Slide 1: 2020-2024 Highway Program Development
March 12, 2019

## Slide 2
Overview
  Discuss 2020-2024 available Highway Program Funding
  Discuss 2020-2024 Highway Program Options
  Determine 2020-2024 Highway Program Objectives
  Action Item: Line Item Targets for Programming
March 12, 2019

## Slide 3
Commission Program Development Schedule (2020-2024)
  March 2019
  Discuss 2020-2024 available Highway Program funding
  Discuss 2020-2024 Highway Program Options
  Determine 2020-2024 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2019
  Develop the Draft 2020-2024 Highway Program
  Action Item: 2020-2024 Highway Program Objectives
  May 2019
  Present the Draft 2020-2024 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2020–2024 Highway Program)
  June 2019
  Action Item: Approve the 2020–2024 Iowa Transportation Improvement Program
March 12, 2019

## Slide 4: Decision Points
Should projects in the 2020-2023 program continue to be programmed with cost/schedule updates?
How should program balances be utilized?
March 12, 2019

## Slide 5: FY 19-24 Primary Road/TIME-21 Funds Forecast (x $1,000,000)
March 12, 2019

## Slide 6
2020 - 2024 Highway Program Funding Assumptions
RUTF/TIME-21
(For Highway Planning Purposes Only)
  Reflects slowing of revenues from fees for new registration after several years of robust new vehicle sales.
  Reflects future reduction in fuel tax revenue due to decreased fuel consumption that results from the greater fuel efficiency of the new vehicles that have been purchased over the past several years.
  TIME-21 funding cap of $225 million has been met.
  Average combined RUTF/TIME-21 growth of 0.5% annually
March 12, 2019

## Slide 7
2020 - 2024 Forecast of
Iowa Federal-Aid Formula Transportation Authorized Funds
(x $1,000)
(For Highway Planning Purposes Only)
National Highway Performance Program 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400
Surface Transportation Block Grant 144,700 5,800 144,700 5,800 144,700 5,800 144,700 5,800 144,700 5,800
Congestion Mitigation & Air Quality 11,900 4,900 11,900 4,900 11,900 4,900 11,900 4,900 11,900 4,900
Highway Safety Improvement Program 28,400 26,400 28,400 26,400 28,400 26,400 28,400 26,400 28,400 26,400
Rail-Highway Crossing 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800
Transportation Alternatives Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Flexible TAP Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Federal Recreational Trails Set-aside 1,400 — 1,400 — 1,400 — 1,400 — 1,400 —
Metropolitan Planning 2,100 — 2,100 — 2,200 — 2,200 — 2,200 —
Statewide Planning and Research 10,700 10,300 10,700 10,300 10,700 10,300 10,700 10,300 10,700 10,300
National Highway Freight Program 18,400 16,600 18,400 16,600 18,400 16,600 18,400 16,600 18,400 16,600
Total 544,300 381,200 544,300 381,200 544,300 381,200 544,300 381,200 544,300 381,200
Total Federal-Aid Formula Funds Forecast to DOT Programs
(x $1,000,000)
2020 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) + (HIP $23.5) = $389.2
2021 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2022 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2023 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2024 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2020 2021 2022 2023 2024
to to to to to
Cities, 2020 Cities, 2021 Cities, 2022 Cities, 2023 Cities 2024
Counties, to Counties, to Counties, to Counties, to Counties, to
DOT DOT DOT DOT DOT DOT DOT DOT DOT DOT
Beyond FAST Act (HTF insolvency risk)
March 12, 2019

## Slide 8
Federal Funding Status
The FAST Act authorizes federal funding through September 30, 2020.
Core programs remain in place with some growth in funding.
FAST Act funding allocations were determined by Commission in 2016.
The next Highway Trust Fund cliff is in 2021, leaving uncertainty in the last four years of this next five-year program.
Federal Fiscal Year 2019 Appropriations Bill passed on Feb. 15.
Highway Infrastructure Program funding again included in FFY 2019 Appropriations (estimated $34.1 million total to Iowa).
March 12, 2019

## Slide 9
Federal Funding Status cont.
Contingency plan has been developed should significant reduction in federal funding occur. Consider identifying specific project impacts with this Program.
Criteria for identifying specific projects to delay include:
- Statewide Equity
- Length of time a project has been considered for programming
- How many times a project has been rescheduled
- Purpose of a project
- Whether the project is already underway
- Local efforts to move forward on a project
- Current conditions and need for the project
March 12, 2019

## Slide 10
Estimated Income
A. Primary Road Fund (PRF) 665.3 22.4 671.0 22.8 673.4 29.8 674.2 29.0
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 365.7 23.5 365.7 365.7 365.7
(based on $280M )
Estimated Income Total 1191.0 45.9 1196.7 22.8 1199.1 29.8 1199.9 29.0
Allocations
E. Budget (PRF)
Operations/Maintenance 355.5 7.7 367.3 -8.5 379.2 -8.9 391.0 -9.0
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 34.8 34.8 34.8 34.8
G. Statewide Consultant Services 80.0 2.5 80.0 2.5 80.0 2.5 80.0 2.5
H. Statewide Contract Maintenance 31.4 31.4 31.4 31.4
I. RR Crossing Protection 5.0 5.0 5.0 5.0
Allocations Total 506.7 10.2 518.5 -6.0 530.4 -6.4 542.2 -6.5
Funds Available for ROW/Construction 684.3 35.7 678.2 28.8 668.7 36.2 657.7 35.5
2020 2020 2021 2021 2022 2022 2023 2023
(Mar ‘18) (Mar ‘19) (Mar ‘18) (Mar ‘19) (Mar ‘18) (Mar ‘19) (Mar ‘18) (Mar ‘19)
change change change change
2020 - 2023 Highway Program Funding with Possible Changes
That Could Impact Funds Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 12, 2019

## Slide 11
Estimated Income
A. Primary Road Fund (PRF) 687.7 693.8 703.2 703.2 710.2
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 389.2 365.7 365.7 365.7 365.7
Estimated Income Total 1236.9 1219.5 1228.9 1228.9 1235.9
Allocations
E. Budget (PRF)
Operations/Maintenance 363.2 358.8 370.3 382.0 393.5
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 34.8 34.8 34.8 34.8 34.8
G. Statewide Consultant Services 82.5 82.5 82.5 82.5 82.5
H. Statewide Contract Maintenance 31.4 31.4 31.4 31.4 31.4
I. RR Crossing Protection 5.0 5.0 5.0 5.0 5.0
Allocations Total 516.9 512.5 524.0 535.7 547.2
Funds Available for ROW/Construction 720.0 707.0 704.9 693.2 688.7
2020 2021 2022 2023 2024
2020 - 2024 Highway Program Funding
Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 12, 2019

## Slide 12
Projected Funds (as of March 2018) 649.3 643.2 633.7 657.7 657.7 657.7 657.7 657.7 657.7 657.7
Highway Program Components
Interstate Stewardship 148.2 173.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0 185.0
Non-Interstate Pavement Modernization 100.0 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0 170.0
Non-Interstate Bridge Modernization 54.7 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0 185.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 155.6 110.4 106.5 166.7
IA 9 Allamakee Mississippi River Bridge 40.0
IA 17 Boone N of US 30 and E 3 mi 6.0 0.1
US 30 Story E of I-35 to E of 600th Ave 0.3
US 30 Benton from IA 21 to US 218 0.2
US 61 Des Moines from 210th St to N of Mediapolis 14.6 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 17.8 2.8 22.3 0.1
IA 92 Washington/Louisa from US 218 to IA 70 0.2
Major Interstate Capacity/System Enhancement 191.4 209.3 150.3 95.6
I-35 Polk/Story 30.5 52.5 1.0
I-80 Cedar 33.0 34.0
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance (25.6) (36.7) (3.5) (17.3) 85.1 (31.8) 159.4 152.6 122.7 92.7
Proposed Highway Program Extended Highway Program
2020 2021 2022 2023 2024 2025 2026 2027 2028 2029
2020-2029 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Approved by the Commission as of June 12, 2018, or implied commitment by the Commission by an established target amount or multi-year project
    Green: Changes since previous discussion
    ( ): Indicates Highway Program is over-programmed
March 12, 2019

## Slide 13
Projected Funds as of March 2019 720.0 707.0 704.9 693.2 688.7 688.7 688.7 688.7 688.7 688.7
Program Balance (FY 18) Carryover 16.2
Federal Fiscal Year 2018 Redistribution 43.1
Operations Budget Reversion (FY 18) 11.7
INFRA Grant 50.0
Cash Flow Adjustment (70.0) (35.0) (35.0)
Projected Funds 721.0 722.0 669.9 693.2 688.7 688.7 688.7 688.7 688.7 688.7
Highway Program Components
Interstate Stewardship 148.2 173.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0 185.0
Interstate Stewardship 50.0
Non-Interstate Pavement Modernization 100.0 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0 170.0
Non-Interstate Bridge Modernization 54.7 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0 185.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 155.6 110.4 106.5 166.7
IA 9 Allamakee Mississippi River Bridge 40.0
IA 17 Boone N of US 30 and E 3 mi 6.0 0.1
US 30 Story E of I-35 to E of 600th Ave 0.3
US 30 Benton from IA 21 to US 218 0.2
US 61 Des Moines from 210th St to N of Mediapolis 14.6 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 17.8 2.8 22.3 0.1
IA 92 Washington/Louisa from US 218 to IA 70 0.2
Major Interstate Capacity/System Enhancement 191.4 209.3 150.3 95.6
I-35 Polk/Story 30.5 52.5 1.0
I-80 Cedar 33.0 34.0
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance 46.1 (7.9) 32.7 18.2 116.1 (0.8) 190.4 183.6 153.7 123.7
Proposed Highway Program Extended Highway Program
2020 2021 2022 2023 2024 2025 2026 2027 2028 2029
2020-2029 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
    Changes to Projected Funds
March 12, 2019

## Slide 14
Projected Funds as of March 2019 721.0 722.0 669.9 693.2 688.7 688.7 688.7 688.7 688.7 688.7
FY 2019 Projects Rescheduled 13.7
Projected Funds 734.7
Highway Program Components
Interstate Stewardship 148.2 223.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0 185.0
Interstate Stewardship 7.1
Non-Interstate Pavement Modernization 100.0 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0 170.0
Non-Interstate Pavement Modernization 0.4
Non-Interstate Bridge Modernization 54.7 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0 185.0
Non-Interstate Bridge Modernization 3.6
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 155.6 110.4 106.5 166.7
Non-Interstate Capacity/System Enhancement 2.0
IA 9 Allamakee Mississippi River Bridge 40.0
IA 17 Boone N of US 30 and E 3 mi 6.0 0.1
US 30 Story E of I-35 to E of 600th Ave 0.3
US 30 Benton from IA 21 to US 218 0.2
US 61 Des Moines from 210th St to N of Mediapolis 14.6 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 17.8 2.8 22.3 0.1
IA 92 Washington/Louisa from US 218 to IA 70 0.2
Major Interstate Capacity/System Enhancement 191.4 209.3 150.3 95.6
Major Interstate Capacity/System Enhancement 0.6
I-35 Polk/Story 30.5 52.5 1.0
I-80 Cedar 33.0 34.0
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance 46.1 (7.9) 32.7 18.2 116.1 (0.8) 190.4 183.6 153.7 123.7
Proposed Highway Program Extended Highway Program
2020 2021 2022 2023 2024 2025 2026 2027 2028 2029
2020-2029 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Changes to Projected Funds
    FY 2019 Projects Rescheduled
Should projects in the 2020-2023 program continue to be programmed with cost/schedule updates?
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 12, 2019

## Slide 15
Projected Funds as of March 2019 734.7 722.0 669.9 693.2 688.7 688.7 688.7 688.7 688.7 688.7
Highway Program Components
Interstate Stewardship 155.3 223.1 175.8 162.5 165.0 165.0 170.0 175.0 180.0 185.0
Interstate Stewardship 43.0 16.7 8.9 (17.7) (36.3)
Non-Interstate Pavement Modernization 100.4 105.0 115.0 125.0 130.0 135.0 140.0 150.0 160.0 170.0
Non-Interstate Bridge Modernization 58.3 57.1 64.6 100.2 110.0 125.0 140.0 155.0 170.0 185.0
Non-Interstate Bridge Modernization 0.2 0.1 0.8
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 157.6 110.4 106.5 166.7 39.1
Non-Interstate Capacity/System Enhancement 19.2 (3.8) (16.4) (21.3) 10.2
IA 9 Allamakee Mississippi River Bridge 40.0
A 17 Boone N of US 30 and E 3 mi 0.1
US 61 Des Moines from 210th St to N of Mediapolis 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 2.8 23.5 0.1
Major Interstate Capacity/System Enhancement 192.0 209.3 150.3 95.6 63.5
Major Interstate Capacity/System Enhancement (49.4) (5.3) 44.4 10.5 19.6
I-35 Polk/Story 52.5 1.0
I-80 Cedar 56.3
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance 33.3 (15.7) (4.3) 45.9 122.6 (23.1) 190.4 183.6 153.7 123.7
Proposed Highway Program Extended Highway Program
2020 2021 2022 2023 2024 2025 2026 2027 2028 2029
2020-2029 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Changes to Projected Funds
    FY 2019 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2020 to 2023, add 2024
Should projects in the 2020-2023 program continue to be programmed with cost/schedule updates?
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 12, 2019

## Slide 16
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
6 | Pottawattamie | 6th St in Council Bluffs to I-80 (Broadway Avenue) | Operational & Safety | Construct Intersection Improvements (TJ to city) | Y | Complete | $10 M
6 | Scott | Kimberly Rd in Davenport from N Brady St to Elmore Ave | Operational & Safety | Construct Intersection Improvements | Y | Inactive | 
9 | Allamakee | Mississippi River Bridge | Structurally Deficient | Replace Bridge | Y | Active | $40 M
12 | Woodbury | Gordon Dr Viaduct in Sioux City | Structurally Deficient | Replace Bridge | Y | Active | $55 M
20 | Dubuque | Mississippi River Bridge | Functionally Obsolete | Add 2nd Bridge | Y | Complete | $100 M
30 | Harrison | Missouri Valley Bypass | Operational & Safety | Construct Bypass | Y | Active | $99 M
30 | Carroll | Carroll Bypass | Operational & Safety | Construct Bypass | N | Inactive | $120 M
30 | Carroll/Greene/ Boone | Co Rd N33 to E Jct US 169 | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Inactive | $265 M $130 M
30 | Story | Intersections in Nevada | Operational & Safety | Construct Interchanges | NA | Active | $25 M
30 | Tama | Intersection At Meskwaki Casino | Operational & Safety | Construct Interchange | NA | Inactive | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 12, 2019

## Slide 17
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
30 | Cedar | Lisbon bypass to Stanwood | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Active | $100 M $50 M
30 | Clinton | Calamus to US 61 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Active | $75 M $40 M
35 | Story | N of IA 210 to E 13th St in Ames | Add Capacity | Construct 6-Lane | Y | Active | $120 M
35/80 | Polk | I-235 Interchange SW of Des Moines | Add Capacity and Improve Operations | Reconstruct Interchange, Add Lanes | Y | Active | $300 M
35/80 | Polk | SW to NE Mixmasters | Add Capacity and Improve Operations | Add Lanes or Modernize | Y | Active | 
58 | Black Hawk | Greenhill Road in Cedar Falls | Operational & Safety | Construct Interchange | NA | Complete | $32 M
61 | Louisa | 1 mi N of IA 78 to 130th St 2 mi S of IA 92 | Add Capacity | Construct 4-Lane | Y | Complete | $108 M
63 | Davis/Wapello | S of Co Rd J37 to Co Rd J12 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Inactive | 
63 | Mahaska | NW Oskaloosa Bypass | Operational & Safety | Construct 2-Lane Bypass | Y | Active | $40 M
63 | Mahaska/ Poweshiek | N of Oskaloosa to I-80 | Operational | Modernize 2-Lane | Y | Inactive | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 12, 2019

## Slide 18
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
65/69 | Warren | Hillcrest Ave in Indianola to IA 5 | Operational & Safety | Improve Intersections | NA | Inactive | 
67 | Scott | Mississippi River Bridge | Structurally Deficient | Replace Bridge (IL Lead) | Y | Inactive | $110 M
74 | Scott | North of Lincoln Road in Bettendorf to I-80 in Davenport | Add Capacity | Construct 6-Lane | N | Complete | $150 M
75 | Plymouth | In Hinton | Operational & Safety | Modernize 4-Lane | NA | Inactive | 
75 | Plymouth/Sioux | IA 60 in Le Mars to IA 10 | Operational | Modernize 2-Lane | Y | Inactive | 
80 | Dallas/Polk | Co Rd R16 to Jordan Creek | Add Capacity | Construct 6-Lane | Y | Inactive | 
80 | Polk/Jasper/ Poweshiek/Iowa | Altoona to I-380 | Add Capacity | Construct 6-Lane | Y | Active | 
80 | Johnson | 1st Ave in Coralville | Add Capacity | Replace Interchange | NA | Complete | $21 M
80 | Cedar | West Branch to Cedar River | Add Capacity | Construct 6-Lane | Y | Inactive | 
80 | Cedar/Scott | County Road Y26 to W of I-280 | Add Capacity | Construct 6-Lane | Y | Inactive | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 12, 2019

## Slide 19
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
80 | Scott | W of I-280 to W of I-74 | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of I-74 to W of Middle Rd in Bettendorf | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of Middle Rd in Bettendorf to Mississippi River Bridge | Capacity & Operations | Replace Interchange (Bi-State req. 06/10/08) | NA | Active | 
80 | Scott | Mississippi River Bridge in Le Claire | Add Capacity | Replace with Wider Bridge (IL Lead) | Y | Active | $150 M
92 | Mahaska | SE Oskaloosa Bypass | Operational | Construct 2-Lane Bypass | Y | Inactive | 
100 | Linn | Collins Rd in Cedar Rapids from W of Council St to 1st Ave | Add Capacity | Construct 6-Lane (Local Lead) | Y | Active | 
151 | Linn | Co Rd X20 Intersection in Springville | Operational & Safety | Construct Interchange | NA | Complete | $23 M
218 | Black Hawk/ Bremer | Janesville to Waverly | Operational | Add Interchanges | NA | Complete | $32 M
380 | Johnson | Forevergreen Rd to S of Co Rd F12 | Add Capacity | Construct 6-Lane | Y | Active | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 12, 2019

## Slide 20
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
380 | Johnson/Linn | S of Co Rd F12 to S of US 30 | Add Capacity | Construct 6-Lane | Y | Active | 
380 | Linn | S of US 30 to Blairs Ferry Road | Add Capacity | Construct 6-Lane | Y | Inactive | 
380 | Linn | In Cedar Rapids at Boyson Rd Interchange | Add Capacity | Replace Interchange | NA | Active | $15 M
380 | Linn | Blairs Ferry Rd to County Home Rd | Add Capacity | Construct 6-Lane | N | Active | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 12, 2019

## Slide 21
FY 2019-2023 Highway Program Objectives
  Stewardship Investments
  Interstate (Pavement Reconstruction/Modernization, Bridges, Pavement Patching/Maint., Rest Areas/Misc.)
  - Maintain scheduled completion of I-35 in Polk County from Oralabor Road to NE 36th St. in Ankeny
  - Maintain scheduled completion of I-35/80 Interchange NE of Des Moines in Polk County
  - Maintain scheduled completion of I-80 in Polk County at Iowa 141 interchange in Urbandale
  - Maintain scheduled completion of I-80/380 interchange reconstruction in Johnson County
  Non-Interstate Pavement Modernization
  Non-Interstate Bridge Modernization
  Safety
  Major Interstate Capacity/System Enhancement Projects
  Maintain scheduled completion of I-29/I-80/I-480 in Council Bluffs (CBIS)
  Maintain scheduled completion of I-74 in Davenport/Bettendorf (Central Section)
  Maintain scheduled completion of I-80 in Johnson/Cedar Counties
  Maintain scheduled completion of I-380 in Linn County for Tower Terrace
  Non-Interstate Capacity/System Enhancement Projects
  Maintain scheduled completion of Iowa 1 in Jefferson County in Fairfield
  Maintain scheduled completion of Iowa 3 in Dubuque County from Luxemburg to Sageville
  Maintain scheduled completion of Iowa 13 in Linn County from N of County Home Rd to S of Central City
  Maintain scheduled completion of Iowa 14 in Marshall and Grundy Counties from Co Rd E18 to Iowa 175
  Maintain scheduled completion of Iowa 17 in Boone County north of U.S. 30
  Maintain scheduled completion of U.S. 18 in Floyd County at the U.S. 218 intersection in Floyd
  Maintain scheduled completion of U.S. 20 in Webster County from E of Co Rd P73 to Iowa 17
  Maintain scheduled completion of U.S. 20 in Black Hawk County from Iowa 21 to I-380 in Waterloo
  Maintain scheduled completion of U.S. 20 in Dubuque County at Swiss Valley Road intersection
  Maintain scheduled completion of U.S. 30 in Story County from 0.5 miles east of I-35 to east of 590th Ave
  Maintain scheduled completion of U.S. 30 in Tama and Benton Counties
  Maintain scheduled completion of U.S. 52 in Jackson County from the Mississippi River to Sabula
  Maintain scheduled completion of U.S. 61 in Des Moines County from Burlington to N of Mediapolis
  Maintain scheduled completion of U.S. 69 in Polk County from I-80 to SE 33rd St in Ankeny
  Maintain scheduled completion of U.S. 69 in Wright County from N of UP RR to Co Rd C20
  Maintain scheduled completion of U.S. 75 in Plymouth County from Hinton to Merrill
  Maintain scheduled completion of Iowa 92 in Washington and Louisa Counties
March 12, 2019
(as shown February 11, 2019)

## Slide 22
 |  |  |  |  |  |  |  |  |  | Score
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 1 Johnson: SB in Iowa City from Burlington to N Dodge St |  |  |  | 3.1 |  |  |  |  | 51 | 2
IA 9 Allamakee: Mississippi River Bridge (state share) |  |  |  |  | 40.0 |  |  |  | 66 | 18
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  |  |  |  | TBD |  | 43 | NA
IA 13 Delaware: N of Co Rd D13 to S Jct IA 3 |  |  |  |  | 10.0 |  |  |  | 76 | 20
IA 21 Iowa: South of Belle Plaine |  |  |  |  |  | TBD |  |  | 82 | NA
US 20 Woodbury: US 75 in Sioux City to Little Whiskey Creek (EB/WB) |  |  |  | 11.0 |  |  |  |  | 54 | 4
US 20 Black Hawk: Hudson Rd to US 63 (EB/WB) |  |  |  |  | 14.1 |  |  |  | 62 | 14
US 30 Story: Co Rd S-14 in Nevada |  |  |  | 4.0 |  |  |  |  | 56 | 5
US 34 Montgomery: W of IA 48 to Co Rd H34 |  |  |  |  | 12.0 |  |  |  | 61 | 13
IA 38 Cedar: SCL to NCL in Tipton (state share) |  | 2.1 |  |  |  |  |  |  | 65 | 16
IA 44 Dallas: At Co Rd R30 2 mi W of Grimes (state share) | 0.3 |  |  |  |  |  |  |  | 65 | 17
US 63 Poweshiek: W Jct US 6 to SCL of Tama |  |  |  |  | 10.0 |  |  |  | 71 | 19
IA 64 Jackson: US 61 to IA 62 in Maquoketa (state share) |  | 3.6 |  |  |  |  |  |  | 60 | 10
US 65 Cerro Gordo: 0.1 mi S of 27th St SW to 6th St S in Mason City |  |  |  |  | 11.1 |  |  |  | 48 | 1
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  | 39 | NA
US 71 Dickinson: Okoboji Grove Rd in Arnolds Park to East View Ave |  |  |  | 11.2 |  |  |  |  | 58 | 8
US 75 Plymouth: Woodbury Co to S of W Grover St in Hinton (SB) | 13.2 |  |  |  |  |  |  |  | 53 | 3
US 75 Sioux: In Sioux Center pavement replacement (state share) |  |  | 0.3 | 20.0 |  |  |  |  | 61 | 12
US 75 Sioux: N of Sioux Center to US 18 |  |  |  |  |  | 10.0 |  |  | 69 | NA
IA 150 Buchanan: In Independence from 8th St to CN RR |  | 3.8 |  |  |  |  |  |  | 57 | 7
IA 141 Polk: NW 121st St intersection including local road connections |  |  |  |  | 7.8 |  |  |  | 63 | 15
IA 160 Polk: DMACC Blvd in Ankeny (state share) | 0.5 |  |  |  |  |  |  |  | 56 | 6
IA 415 Polk: Co Rd R6F/NW Beaver Dr 1.5 mi NE of IA 141 (state share) |  | 0.4 |  |  |  |  |  |  | 78 | 21
IA 922 Linn: 29th to 31st St NE in Cedar Rapids (state share) | 0.5 |  |  |  |  |  |  |  | 58 | 9
ITS (multiple locations statewide) | 0.8 |  |  | 0.8 |  |  |  |  | NA | NA
Culverts (multiple locations statewide) | 1.8 | 1.0 | 0.8 | 0.8 |  |  |  |  | NA | NA
Slide Repairs (multiple locations statewide) | 0.9 | 1.0 |  |  |  |  |  |  | NA | NA
Jasper: Traffic Incident Management (TIM) Training Center | TBD | TBD |  |  |  |  |  |  | NA | NA
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 12, 2019

## Slide 23
 |  |  |  |  |  |  |  |  |  |  | Score
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 30 Harrison: Missouri Valley bypass |  |  |  |  | 10.5 | 43.5 | 18.5 | 18.4 |  | 52 | 1
US 30 Tama: Meskwaki interchange |  |  |  |  |  |  |  | TBD |  | 67 | NA
US 61 Louisa: 1 mi N of IA 78 to 2 mi S of IA 92 |  |  |  |  | 5.8 | 37.1 |  | 65.1 |  | 67 | 3
US 63 Mahaska: Bypass NW of Oskaloosa |  |  |  | 6.1 | 14.7 |  | 18.7 | 0.3 |  | 67 | 3
US 218 Bremer: Cedar River in Janesville to IA 116 in Waverly |  |  |  |  | 18.8 | 12.9 |  |  |  | 61 | 2
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  |  |  | TBD |  |  |  | TBD |  |  | 
IA 78 Henry: Olds to Louisa County | 13.7 |  |  |  |  |  |  |  |  |  | 
IA 78 Louisa: Henry County to US 61 | 8.4 |  |  |  |  |  |  |  |  |  | 
Potential Increase for Non-Interstate Pavement Modernization (3R) |  |  |  |  |  |  |  |  |  |  | 
Non-Interstate Pavement Preservation (Statewide) | 37.0 |  |  |  |  |  |  |  |  |  | 
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 12, 2019

## Slide 24
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Total
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  |  |  | 45.0 | 50.0 | 25.0 |  | 120.0
I-74 Scott: In Bettendorf from N of Lincoln Rd to S of US 6 |  |  |  |  |  | 59.5 |  |  |  |  | 59.5
I-74 Scott: US 6 Interchange in Davenport (reconstruction) |  |  |  |  |  |  | 24.9 |  |  |  | 24.9
I-74 Scott: In Davenport from S of US 6 to 67th St |  |  |  |  |  |  |  | 63.7 |  |  | 63.7
I-80 Polk: I-35/235 to US 65 near Altoona |  |  |  |  |  |  | 27.9 | 28.9 |  |  | 56.8
I-80 Polk/Jasper: Altoona to Colfax |  |  |  |  |  |  |  |  |  | TBD | TBD
I-80 Iowa/Johnson: US 151 to I-380 |  |  |  |  |  |  |  |  |  | TBD | TBD
I-80 Cedar: 0.5 mi E of Co Rd X30 to E of the Cedar River |  |  |  |  |  |  |  | 40.0 | 45.0 | 45.0 | 130.0
I-80 Cedar/Scott: 0.5 mi W of Co Rd Y26 to I-280 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: I-280 to US 61 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: US 61 to W of Middle Road in Bettendorf |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-80 Scott: W of Middle Road in Bettendorf to Mississippi River |  |  |  |  | TBD | TBD |  |  |  |  | TBD
I-80 Scott: Mississippi River Bridge |  |  |  |  |  | 150.0 |  |  |  |  | 150.0
I-380 Johnson: Forevergreen Rd to S of Co Rd F12 |  |  |  |  |  |  |  | TBD | TBD | TBD | TBD
I-380 Johnson/Linn: S of Co Rd F12 to US 30 |  |  |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  | TBD | TBD |  |  | TBD
Stewardship (Shelf-Ready) Projects |  | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  | 500.0
    Subject to change as additional information becomes available
March 12, 2019
(as shown February 11, 2019)

## Slide 25: Decision Points
Should projects in the 2020-2023 program continue to be programmed with cost/schedule updates?
How should program balances be utilized?
March 12, 2019

## Slide 26
Potential FY 2020-2024 Highway Program Objectives
  Projects in the 2020-2023 Highway Program will continue to be programmed with cost and schedule updates
  Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas and misc.
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Investing in additional stewardship projects
  Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Optimization through improving operational efficiency and resiliency
    Investing in intelligent transportation systems infrastructure
    Investing in Super-2 improvements
  Transformation through increasing mobility and travel choices
    Potential investment in bypasses and corridor improvements
March 12, 2019

## Slide 27: Next Steps
  Discuss 2020-2024 Highway Program Options
  Determine 2020-2024 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  Develop the Draft 2020-2024 Highway Program
  Action Item: 2020-2024 Highway Program Objectives
March 12, 2019