## Slide 1: 2021-2025 Highway Program Development
March 10, 2020

## Slide 2
Overview
  Discuss 2021-2025 available Highway Program funding
  Discuss 2021-2025 Highway Program Options
  Determine 2021-2025 Highway Program Objectives
  Action Item: Line Item Targets for Programming
March 10, 2020

## Slide 3
Commission Program Development Schedule (2021-2025)
  March 2020
  Discuss 2021-2025 available Highway Program funding
  Discuss 2021-2025 Highway Program Options
  Determine 2021-2025 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2020
  Develop the Draft 2021-2025 Highway Program
  Action Item: 2021-2025 Highway Program Objectives
  May 2020
  Present the Draft 2021-2025 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2021–2025 Highway Program)
  June 2020
  Action Item: Approve the 2021–2025 Iowa Transportation Improvement Program
March 10, 2020

## Slide 4: Decision Points
Should projects in the 2021-2024 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 10, 2020

## Slide 5: FY 20-25 Primary Road/TIME-21 Funds Forecast (x $1,000,000)
March 10, 2020

## Slide 6
2021-2025 Highway Program Funding Assumptions
RUTF/TIME-21
(For Highway Planning Purposes Only)
  Adjusted baseline from last year to reflect higher than expected vehicle sales and fuel tax revenue in FY 2020
  Forecast continues to reflect expected slowing of revenues from fees for new registration and reduced fuel tax revenue
  TIME-21 funding cap of $225 million has been met
  Average combined RUTF/TIME-21 growth of 0.6% annually
March 10, 2020

## Slide 7
2021 - 2025 Forecast of
Iowa Federal-Aid Formula Transportation Authorized Funds
(x $1,000)
(For Highway Planning Purposes Only)
National Highway Performance Program 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400 311,400
Surface Transportation Block Grant 144,700 5,800 144,700 5,800 144,700 5,800 144,700 5,800 144,700 5,800
Congestion Mitigation & Air Quality 11,900 4,900 11,900 4,900 11,900 4,900 11,900 4,900 11,900 4,900
Highway Safety Improvement Program 28,400 26,400 28,400 26,400 28,400 26,400 28,400 26,400 28,400 26,400
Rail-Highway Crossing 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800 5,800
Transportation Alternatives Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Flexible TAP Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Federal Recreational Trails Set-aside 1,400 — 1,400 — 1,400 — 1,400 — 1,400 —
Metropolitan Planning 2,100 — 2,100 — 2,200 — 2,200 — 2,200 —
Statewide Planning and Research 10,700 10,300 10,700 10,300 10,700 10,300 10,700 10,300 10,700 10,300
National Highway Freight Program 18,400 16,600 18,400 16,600 18,400 16,600 18,400 16,600 18,400 16,600
Total 544,300 381,200 544,300 381,200 544,300 381,200 544,300 381,200 544,300 381,200
Total Federal-Aid Formula Funds Forecast to DOT Programs
(x $1,000,000)
2021 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) + (HIP/BR $36.3) = $402.0
2022 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2023 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2024 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2025 - ($381.2 @ 92.0% Obligation Authority = $350.7) + (August Redistribution $15.0) = $365.7
2021 2022 2023 2024 2025
to to to to to
Cities, 2021 Cities, 2022 Cities, 2023 Cities, 2024 Cities 2025
Counties, to Counties, to Counties, to Counties, to Counties, to
DOT DOT DOT DOT DOT DOT DOT DOT DOT DOT
March 10, 2020

## Slide 8
Federal Funding Status
The FAST Act authorizes federal funding through September 30, 2020.
FAST Act funding allocations were determined by Commission in 2016.
The next Highway Trust Fund cliff is in 2022, leaving uncertainty in all but one year of this next five-year program.
Contingency plan has been developed should significant reduction in federal funding occur. Continue to identify specific project impacts with this Program.
Recent annual appropriations have included additional funding beyond authorized levels.
March 10, 2020

## Slide 9
 | DRAFT 2021 - 2025 IOWA HIGHWAY PROGRAM |  |  |  |  |  |  | 
 |  |  |  | PROJECT ESTIMATED COSTS X $1000 |  |  |  | 
 | LOCATION | FUNDING | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
 | EMERGENCY & CONTINGENCY - U-STEP/C-STEP |  | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 10000 | 10000 | 10000 | 10000 | 10000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 10000 | 10000 | 10000 | 10000 | 10000
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 300 | 300 | 300 | 300 | 300
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 60 | 60 | 60 | 60 | 60
 | SCENIC BYWAY PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 82500 | 82500 | 82500 | 82500 | 82500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 31350 | 31350 | 31350 | 31350 | 31350
 | STATEWIDE CONTRACT MAINTENANCE (BRIDGE) |  | MISCELLANEOUS | 2000 | 2000 | 2000 | 2000 | 2000
 | STATEWIDE CONTRACT MAINTENANCE (PAVEMENT) |  | MISCELLANEOUS | 2000 | 2000 | 2000 | 2000 | 2000
 | STATEWIDE RAILROAD CROSSINGS |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE ROADSIDE IMPROVEMENT |  | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE TRAFFIC CONTROL DEVICES |  | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000
 | ABBREVIATIONS |  |  |  |  |  |  | 
 | 4R - INTERSTATE STEWARDSHIP |  |  |  |  |  |  | 
 | 3R - NON-INTERSTATE PAVEMENT MODERNIZATION |  |  |  |  |  |  | 
 | SR - SAFETY SPECIFIC |  |  |  |  |  |  | 
  At what levels should the line item targets be programmed?
  March Action Item: Line Item Targets for Programming
March 10, 2020
as shown Feb 11, 2020

## Slide 10
Estimated Income
A. Primary Road Fund (PRF) 693.8 14.8 703.2 15.8 703.2 18.0 710.2 15.6
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 365.7 36.3 365.7 365.7 365.7
(based on $280M )
Estimated Income Total 1219.5 51.1 1228.9 15.8 1228.9 18.0 1235.9 15.6
Allocations
E. Budget (PRF)
Operations/Maintenance 358.8 -6.4 370.3 -6.5 382.0 -6.5 393.5 -6.5
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 34.8 10.5 34.8 10.5 34.8 10.5 34.8 10.5
G. Statewide Consultant Services 82.5 2.5 82.5 2.5 82.5 2.5 82.5 2.5
H. Statewide Contract Maintenance 31.4 4.0 31.4 4.0 31.4 4.0 31.4 4.0
I. RR Crossing Protection 5.0 5.0 5.0 5.0
Allocations Total 512.5 10.6 524.0 10.5 535.7 10.5 547.2 10.5
Funds Available for ROW/Construction 707.0 40.5 704.9 5.3 693.2 7.5 688.7 5.1
2021 2021 2022 2022 2023 2023 2024 2024
(Mar ‘19) (Mar ‘20) (Mar ‘19) (Mar ‘20) (Mar ‘19) (Mar ‘20) (Mar ‘19) (Mar ‘20)
change change change change
2021 - 2024 Highway Program Funding with Possible Changes
That Could Impact Funds Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 10, 2020

## Slide 11
Estimated Income
A. Primary Road Fund (PRF) 708.6 719.0 721.2 725.8 729.8
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 402.0 365.7 365.7 365.7 365.7
Estimated Income Total 1270.6 1244.7 1246.9 1251.5 1255.5
Allocations
E. Budget (PRF)
Operations/Maintenance 352.4 363.8 375.5 387.0 398.6
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 45.3 45.3 45.3 45.3 45.3
G. Statewide Consultant Services 85.0 85.0 85.0 85.0 85.0
H. Statewide Contract Maintenance 35.4 35.4 35.4 35.4 35.4
I. RR Crossing Protection 5.0 5.0 5.0 5.0 5.0
Allocations Total 523.1 534.5 546.2 557.7 569.3
Funds Available for ROW/Construction 747.5 710.2 700.7 693.8 686.2
2021 2022 2023 2024 2025
2021 – 2025 Highway Program Funding
Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 10, 2020

## Slide 12
Projected Funds as of March 2019 722.0 669.9 693.2 688.7 688.7 688.7 688.7 688.7 688.7 688.7
Highway Program Components
Interstate Stewardship 239.8 184.7 144.8 128.7 165.0 170.0 175.0 180.0 185.0 190.0
Non-Interstate Pavement Modernization 105.0 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 57.3 64.7 101.0 110.0 125.0 140.0 155.0 170.0 185.0 190.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 118.5 91.2 202.4 204.1
IA 17 Boone N of US 30 and E 3 mi 0.1
US 61 Des Moines from 210th St to N of Mediapolis 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 2.8 22.3 0.1
US 30 Missouri Valley bypass 49.7 21.1 20.6
US 61 1 mi N of IA 78 to 2 mi S of IA 92 37.1 65.1
US 63 NW Oskaloosa bypass 18.7 0.3
US 218 Bremer Janesville to Waverly 12.9
Major Interstate Capacity/System Enhancement 204.0 194.7 106.1 83.1
I-35 Polk/Story 52.5 1.0
I-80 Cedar 56.3
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance (27.6) (5.4) (26.1) (7.2) (137.8) 135.6 82.6 138.7 108.7 93.7
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 10, 2020
as shown
Feb 11, 2020

## Slide 13
Projected Funds as of March 2020 747.5 710.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Program Balance (FY 19) Carryover 22.1
Federal FY 2019 Redistribution 19.9
Operations Budget Reversion (FY 19) 1.1
INFRA Grant 50.0
Federal Bridge Programs 5.4
Partial FY 20 Program Balance carryover (50.0)
Cash Flow Adjustment (70.0) (35.0)
Projected Funds 726.0 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 239.8 184.7 144.8 128.7 165.0 170.0 175.0 180.0 185.0 190.0
Non-Interstate Pavement Modernization 105.0 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 57.3 64.7 101.0 110.0 125.0 140.0 155.0 170.0 185.0 190.0
Non-Interstate Bridge Modernization 5.4
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 118.5 91.2 202.4 204.1
IA 17 Boone N of US 30 and E 3 mi 0.1
US 61 Des Moines from 210th St to N of Mediapolis 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 2.8 22.3 0.1
US 30 Missouri Valley bypass 49.7 21.1 20.6
US 61 1 mi N of IA 78 to 2 mi S of IA 92 37.1 65.1
US 63 NW Oskaloosa bypass 18.7 0.3
US 218 Bremer Janesville to Waverly 12.9
Major Interstate Capacity/System Enhancement 204.0 194.7 106.1 83.1
I-35 Polk/Story 52.5 1.0
I-80 Cedar 56.3
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance (29.0) (0.1) (18.6) (2.1) (140.3) 133.1 80.1 136.2 106.2 91.2
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 10, 2020
    Changes to Projected Funds

## Slide 14
Projected Funds as of March 2020 726.0 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
FY 2020 Projects Rescheduled 108.5
Projected Funds 834.5 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 239.8 184.7 144.8 128.7 165.0 170.0 175.0 180.0 185.0 190.0
Interstate Stewardship 2.6
Non-Interstate Pavement Modernization 105.0 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Bridge Modernization 62.7 64.7 101.0 110.0 125.0 140.0 155.0 170.0 185.0 190.0
Non-Interstate Bridge Modernization 1.2
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 118.5 91.2 202.4 204.1
Non-Interstate Capacity/System Enhancement 29.4
IA 17 Boone N of US 30 and E 3 mi 0.1
US 61 Des Moines from 210th St to N of Mediapolis 0.1
US 61 Des Moines N of Mediapolis to N of IA 78 2.8 22.3 0.1
US 30 Missouri Valley bypass 49.7 21.1 20.6
US 61 1 mi N of IA 78 to 2 mi S of IA 92 37.1 65.1
US 63 NW Oskaloosa bypass 18.7 0.3
US 218 Bremer Janesville to Waverly 12.9
Major Interstate Capacity/System Enhancement 204.0 194.7 106.1 83.1
Major Interstate Capacity/System Enhancement 75.3
I-35 Polk/Story 52.5 1.0
I-80 Cedar 56.3
I-80 Scott Mississippi River Bridge 150.0
Highway Program Balance (29.0) (0.1) (18.6) (2.1) (140.3) 133.1 80.1 136.2 106.2 91.2
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 10, 2020
    Changes to Projected Funds
    FY 2020 Projects Rescheduled

## Slide 15
Projected Funds as of March 2020 834.5 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 242.4 184.7 144.8 128.7 165.0 170.0 175.0 180.0 185.0 190.0
Interstate Stewardship (0.3) (2.7) 1.4 24.1 12.3
Non-Interstate Pavement Modernization 105.0 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
Non-Interstate Pavement Modernization 0.7
Non-Interstate Bridge Modernization 63.9 64.7 101.0 110.0 125.0 140.0 155.0 170.0 185.0 190.0
Non-Interstate Bridge Modernization 0.2 0.3 0.3 (0.5) 0.9
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Safety Specific 0.6
Non-Interstate Capacity/System Enhancement 147.9 91.2 202.4 204.1 102.7
Non-Interstate Capacity/System Enhancement* (7.8) 74.5 5.5 9.0 3.6
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.3
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 279.3 194.7 106.1 83.1 258.8
Major Interstate Capacity/System Enhancement 0.8 5.8 5.7 (14.2) (133.4)
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Cedar (scaled back to just include replacement of Sugar Creek bridges)
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (23.2) (78.0) (31.5) (20.5) (23.7) 94.3 38.5 136.2 106.2 91.2
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 10, 2020
    Changes to Projected Funds
    FY 2020 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2021 to 2024, add 2025
Should projects in the 2021-2024 program continue to be programmed with cost/schedule updates?
Non-Interstate Capacity/System Enhancement changes include:
  Advance Iowa 17 Boone by two years
  Advance US 75 Plymouth by one year to 2021

## Slide 16: 2021-2025 Highway Program Analysis (with updated revenue, FY 2020 projects rescheduled, project cost updates and schedule updates)
Chart: 
| 2021 | 2022 | 2023 | 2024 | 2025
Interstate Stewardship | 242.1 | 182 | 146.2 | 152.8 | 177.3
Major Interstate | 280.1 | 200.5 | 111.8 | 68.9 | 125.4
Non-Interstate Pavement Modernization | 105.7 | 115 | 140 | 145 | 150
Non-Interstate Bridge Modernization | 64.1 | 65 | 101.3 | 109.5 | 125.9
Non-Interstate Capacity/Enhancement | 140.1 | 165.7 | 207.9 | 213.1 | 106.3
Safety | 25.6 | 25 | 25 | 25 | 25

## Slide 17
Highway Program Components
Interstate Stewardship 242.1 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0
- Funds in years 2026 and beyond are placeholders (not programmed yet)
- Projects in 2021-2025 are specifically identified in the highway program
- Identified projects are 38% roadway reconstruction, 20% pavement resurfacing and maintenance, 21% bridge replacements,
10% bridge repairs or overlays, 5% rest area improvements and maintenance, 7% other (traffic signs, erosion control, lighting, etc.)
- Major projects continuing in the current program include:
Johnson I-80/380/US 218 Interchange reconstruction in 2021-2023
Johnson I-80 1st Ave Interchange reconstruction in Coralville beginning in 2024
Linn I-380 Boyson Rd Interchange reconstruction in Hiawatha recommended to move from 2024 to 2025
Polk I-35/80/235 Northeast mixmaster improvements recommended to move from 2022-2023 to 2023-2024
Poweshiek I-80/IA 146 Interchange reconstruction at Grinnell in 2021-2022
Warren I-35 reconstruction at various locations between IA 92 and IA 5 in 2021-2025
Woodbury I-29/IA 141 Interchange reconstruction in 2023
- There are four rest area building replacements:
Mills NB I-29 in 2021 is currently programmed
Iowa EB I-80 in 2022 is currently programmed
Linn SB I-380 in 2023 is to be considered for programming
Polk EB I-80 in 2024 is currently programmed but is recommended to remove from Program
Pottawattamie WB I-80 in 2025 is to be considered for programming
- Major projects for consideration to add to the program this year include:
Polk I-35/80 Hickman interchange is to be considered for programming beginning in 2025
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 10, 2020

## Slide 18
Highway Program Components
Non-Interstate Pavement Modernization 105.7 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0
- Funds in Years 2022 and beyond are placeholders (no specific projects identified)
- Projects in 2021 will be specifically identified in the highway program (to be handed
out in April)
- 2021 draft projects are 93% pavement resurfacing, 6% pavement widening, and 1% other
Non-Interstate Bridge Modernization 64.1 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0
- Funds in years 2026 and beyond are placeholders (not programmed yet)
- Projects in 2021-2025 will be specifically identified in the highway program (to be handed
out in April)
- Draft projects are 61% bridge replacements, 36% bridge repairs or overlays, 2% culvert repairs
or replacements, 1% other
Safety Specific 25.6 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
- Funds in Years 2022 and beyond are mostly placeholders (few specific projects identified)
- Projects in 2021 will be specifically identified in the highway program (to be handed out in April)
- 2021 draft projects are 86% shoulder paving and widening, 8% interstate median guardrail,
6% other
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 10, 2020

## Slide 19
Highway Program Components
Non-Interstate Capacity/System
Enhancement 140.1 165.7 207.9 213.1 106.3 49.7 76.7
- Funds in Years 2026 and beyond are project completion costs for projects already in Program
- Includes advancing the Iowa 17 Boone County project by two years to meet earmark deadlines
- Includes advancing US 75 Plymouth County pavement reconstruction from 2022 to 2021 to help
reduce 2022 overprogrammed amount
Major Interstate Capacity/System
Enhancement 280.1 200.5 111.8 68.9 125.4 52.2 51.0
- Funds in years 2026 and beyond are project completion costs for projects already in Program
- Includes Interstate project changes consistent with Iowa Interstate Investment Plan
recommendations discussed at December 2019 workshop. This includes the following changes
- Scale back I-80 Cedar County to just include replacement of Sugar Creek bridges
- Add in I-80 Dallas County from Grand Prairie Parkway to Jordan Creek Parkway
- Does not add in I-380 Penn Street Interchange area
Proposed Highway Program Extended Highway Program
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
2021-2030 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 10, 2020

## Slide 20
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
6 | Pottawattamie | 6th St in Council Bluffs to I-80 (Broadway Avenue) | Operational & Safety | Construct Intersection Improvements (TJ to city) | Y | Complete | $10 M
6 | Scott | Kimberly Rd in Davenport from N Brady St to Elmore Ave | Operational & Safety | Construct Intersection Improvements | Y | Inactive | 
12 | Woodbury | Gordon Dr Viaduct in Sioux City | Structurally Deficient | Replace Bridge | Y | Active | $55 M
20 | Dubuque | Mississippi River Bridge | Functionally Obsolete | Add 2nd Bridge | Y | Complete | $100 M
30 | Carroll | Carroll Bypass | Operational & Safety | Construct Bypass | N | Inactive | $120 M
30 | Carroll/Greene/ Boone | Co Rd N33 to E Jct US 169 | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Inactive | $265 M $130 M
30 | Story | Intersections in Nevada | Operational & Safety | Construct Interchanges | NA | Active | $25 M
30 | Tama | Intersection At Meskwaki Casino | Operational & Safety | Construct Interchange | NA | Inactive | 
30 | Cedar | Lisbon bypass to Stanwood | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Active | $100 M $50 M
30 | Clinton | Calamus to US 61 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Active | $75 M $40 M
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 10, 2020

## Slide 21
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
35 | Story | N of IA 210 to E 13th St in Ames | Add Capacity | Construct 6-Lane | Y | Active | $120 M
35/80 | Polk | I-235 Interchange SW of Des Moines | Add Capacity and Improve Operations | Reconstruct Interchange, Add Lanes | Y | Active | $300 M
35/80 | Polk | SW to NE Mixmasters | Add Capacity and Improve Operations | Add Lanes or Modernize | Y | Active | 
58 | Black Hawk | Greenhill Road in Cedar Falls | Operational & Safety | Construct Interchange | Y | Complete | $32 M
63 | Davis/Wapello | S of Co Rd J37 to Co Rd J12 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Inactive | 
63 | Mahaska/ Poweshiek | N of Oskaloosa to I-80 | Operational | Modernize 2-Lane | Y | Inactive | 
65/69 | Warren | Hillcrest Ave in Indianola to IA 5 | Operational & Safety | Improve Intersections | NA | Inactive | 
67 | Scott | Mississippi River Bridge | Structurally Deficient | Replace Bridge (IL Lead) | Y | Inactive | $110 M
74 | Scott | North of Lincoln Road in Bettendorf to I-80 in Davenport | Add Capacity | Construct 6-Lane | N | Complete | $150 M
75 | Plymouth | In Hinton | Operational & Safety | Modernize 4-Lane | NA | Inactive | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 10, 2020

## Slide 22
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
75 | Plymouth/Sioux | IA 60 in Le Mars to IA 10 | Operational | Modernize 2-Lane | Y | Inactive | 
80 | Dallas/Polk | Co Rd R16 to Jordan Creek | Add Capacity | Construct 6-Lane | Y | Inactive | 
80 | Polk/Jasper/ Poweshiek/Iowa | Altoona to I-380 | Add Capacity | Construct 6-Lane | Y | Active | 
80 | Cedar | West Branch to Cedar River | Add Capacity | Construct 6-Lane | Y | Inactive | 
80 | Cedar/Scott | County Road Y26 to W of I-280 | Add Capacity | Construct 6-Lane | Y | Inactive | 
80 | Scott | W of I-280 to W of I-74 | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of I-74 to W of Middle Rd in Bettendorf | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of Middle Rd in Bettendorf to Mississippi River Bridge | Capacity & Operations | Replace Interchange (Bi-State req. 06/10/08) | NA | Active | 
80 | Scott | Mississippi River Bridge in Le Claire | Add Capacity | Replace with Wider Bridge (IL Lead) | Y | Active | $150 M
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 10, 2020

## Slide 23
Highway Program Candidates
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
92 | Mahaska | SE Oskaloosa Bypass | Operational | Construct 2-Lane Bypass | Y | Inactive | 
100 | Linn | Collins Rd in Cedar Rapids from W of Council St to 1st Ave | Add Capacity | Construct 6-Lane (Local Lead) | Y | Active | 
151 | Linn | Co Rd X20 Intersection in Springville | Operational & Safety | Construct Interchange | NA | Complete | $23 M
380 | Johnson | Forevergreen Rd to S of Co Rd F12 | Add Capacity | Construct 6-Lane | Y | Active | 
380 | Johnson/Linn | S of Co Rd F12 to S of US 30 | Add Capacity | Construct 6-Lane | Y | Active | 
380 | Linn | S of US 30 to Blairs Ferry Road | Add Capacity | Construct 6-Lane | Y | Inactive | 
380 | Linn | Blairs Ferry Rd to County Home Rd | Add Capacity | Construct 6-Lane | N | Active | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 10, 2020

## Slide 24
March 10, 2020
as approved
April 9, 2019
  Projects in the 2020-2023 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in bypasses and corridor improvements
FY 2020-2024 Highway Program Objectives

## Slide 25
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Beyond | Total | Score | Rank
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  |  | 4.9 | 30.7 | 39.3 | 67.6 | 1.2 | 143.7 | 47 | 4
I-80 Polk: Hickman Rd Interchange (4R) |  |  |  |  | 28.0 | 38.4 | 10.0 |  |  |  | 76.4 | 37 | 1
I-80 Scott: Mississippi River Bridge |  |  |  |  | 50.0 | 50.0 | 50.0 |  |  |  | 150.0 | 38 | 2
I-380 Johnson: Segment 1 N of Forevergreen Rd to N of Penn St |  |  |  |  |  |  |  | 9.9 | 12.5 | 13.0 | 35.4 | 49 | 6
I-380 Johnson: Segment 2 N of Penn St to N of Iowa River |  |  |  |  | 38.6 | 44.6 | 26.1 |  |  |  | 109.3 | 48 | 5
I-380 Johnson: Segment 3 N of Iowa River to N of 120th St NW |  |  |  |  |  |  |  | 16.6 | 9.5 |  | 26.1 | 49 | 6
I-380 Linn: Segment 4 N of 120th St NW to US 30 |  |  |  |  | 32.4 | 18.6 |  |  |  |  | 51.0 | 38 | 2
I-380 Linn: Blairs Ferry Road to County Home Rd (add lanes) |  |  |  |  |  | 14.8 |  | 12.4 |  |  | 27.2 | 56 | 8
Stewardship (Shelf-Ready) Projects |  | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  | 500.0 |  | 
    Subject to change as additional information becomes available
March 10, 2020

## Slide 26
 |  |  |  |  |  |  |  |  |  | Score
 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 2 Fremont: Missouri River Overflow to I-29 | 10.0 |  |  |  |  |  |  |  | 63 | 6
US 6 Polk: NW 128th St in Clive/Urbandale | 0.5 |  |  |  |  |  |  |  | 61 | 5
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  |  |  |  | TBD |  | 41 | 1
IA 21 Iowa: South of Belle Plaine |  |  |  |  | 5.0 |  |  |  | 83 | 10
US 34 Mills: Resiliency improvements (could be ER) | TBD |  |  |  |  |  |  |  | 79 | 8
US 34 Wapello: Wildwood Dr to US 63 in Ottumwa |  |  |  |  |  | 30.8 |  |  | 44 | 2
US 65 Polk: SB turn lane at exit ramp to IA 163 in Pleasant Hill | 0.3 |  |  |  |  |  |  |  | 58 | 4
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  | 50 | 3
US 75 Sioux: N of Sioux Center to US 18 |  |  |  |  | 10.0 |  |  |  | 71 | 7
US 218 Lee: NB On Ramp to IA 27 |  | 0.3 |  |  |  |  |  |  | 80 | 9
Polk: Traffic Incident Management (TIM) Training Center |  |  |  | TBD | TBD |  |  |  |  | 
ITS (multiple locations statewide) |  |  | 0.1 |  | 0.3 |  |  |  |  | 
Culverts (multiple locations statewide) | 1.4 | 0.3 |  | 0.4 |  |  |  |  |  | 
Slide Repairs (multiple locations statewide) | 0.9 | 0.2 | 1.3 |  |  |  |  |  |  | 
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 10, 2020

## Slide 27
 |  |  |  |  |  |  |  |  | Priority |  | Score
 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond | Corridor | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 18 Hancock: E Branch Iowa River to Country Club Dr (Super-2) |  |  |  |  | 3.0 |  |  |  | N | 71 | 1
US 30 Cedar/Clinton: ECL Lisbon to ECL Mechanicsville (Super-2) |  |  |  |  | 0.4 | 17.0 |  |  | Y | 75 | 2
US 63 Tama: Toledo to Co Rd E29 (Super-2) |  |  |  |  | 9.0 |  |  |  | N | 80 | 3
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  |  | TBD |  |  |  |  |  |  |  | 
IA 78 Henry: Olds to Louisa County | 13.7 |  |  |  |  |  |  |  |  |  | 
IA 78 Louisa: Henry County to US 61 | 8.4 |  |  |  |  |  |  |  |  |  | 
Options of Projects to add to the Highway Program
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 10, 2020

## Slide 28: Decision Points
Should projects in the 2021-2024 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 10, 2020

## Slide 29
March 10, 2020
  Projects in the 2021-2024 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in bypasses and corridor improvements
Potential FY 2021-2025 Highway Program Objectives

## Slide 30: Next Steps
March Business Meeting
Action Item: Line Item Targets for Programming
Next March Workshop
Discuss 2021-2025 Highway Program Options
Determine 2021-2025 Highway Program Objectives
April
Develop the Draft 2021-2025 Highway Program
Action Item: 2021-2025 Highway Program Objectives
March 10, 2020