## Slide 1: 2022-2026 Highway Program Development
March 9, 2021

## Slide 2
Overview
  Discuss 2022-2026 available Highway Program funding
  Discuss 2022-2026 Highway Program Options
  Determine 2022-2026 Highway Program Objectives
  Action Item: Line Item Targets for Programming
March 9, 2021

## Slide 3
Commission Program Development Schedule (2022-2026)
  March 2021
  Discuss 2022-2026 available Highway Program funding
  Discuss 2022-2026 Highway Program Options
  Determine 2022-2026 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2021
  Develop the Draft 2022-2026 Highway Program
  Action Item: 2022-2026 Highway Program Objectives
  May 2021
  Present the Draft 2022-2026 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2022–2026 Highway Program)
  June 2021
  Action Item: Approve the 2022–2026 Iowa Transportation Improvement Program
March 9, 202`

## Slide 4: Decision Points
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 9, 2021

## Slide 5: FY 21-26 Primary Road/TIME-21 Funds Forecast (x $1,000,000)
March 9, 2021

## Slide 6
2022-2026 Highway Program Funding Assumptions
RUTF/TIME-21
(For Highway Planning Purposes Only)
  Overall forecast is conservative based on unknown long-term impacts of COVID-19
  Forecast continues to reflect expected slowing of revenues from fees for new registration and reduced fuel tax revenue
  TIME-21 funding cap of $225 million has been met
  Average combined RUTF/TIME-21 growth of 0.4% annually
March 9, 2021

## Slide 7
2022 - 2026 Forecast of
Iowa Federal-Aid Formula Transportation Authorized Funds
(x $1,000)
(For Highway Planning Purposes Only)
National Highway Performance Program 307,400 307,400 307,400 307,400 307,400 307,400 307,400 307,400 307,400 307,400
Surface Transportation Block Grant 146,500 5,900 146,500 5,900 146,500 5,900 146,500 5,900 146,500 5,900
Congestion Mitigation & Air Quality 11,800 4,800 11,800 4,800 11,800 4,800 11,800 4,800 11,800 4,800
Highway Safety Improvement Program 28,100 26,100 28,100 26,100 28,100 26,100 28,100 26,100 28,100 26,100
Rail-Highway Crossing 5,700 5,700 5,700 5,700 5,700 5,700 5,700 5,700 5,700 5,700
Transportation Alternatives Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Flexible TAP Set-aside 4,700 — 4,700 — 4,700 — 4,700 — 4,700 —
Federal Recreational Trails Set-aside 1,400 — 1,400 — 1,400 — 1,400 — 1,400 —
Metropolitan Planning 2,100 — 2,100 — 2,100 — 2,100 — 2,100 —
Statewide Planning and Research 10,600 10,200 10,600 10,200 10,600 10,200 10,600 10,200 10,600 10,200
National Highway Freight Program 18,200 16,400 18,200 16,400 18,200 16,400 18,200 16,400 18,200 16,400
Total 541,200 376,500 541,200 376,500 541,200 376,500 541,200 376,500 541,200 376,500
Total Federal-Aid Formula Funds Forecast to DOT Programs
(x $1,000,000)
2022 - ($376.5 @ 89.0% Obligation Authority = $335.1) + (August Redistribution $15.0) + (HIP/BR $22.6) = $372.7
2023 - $372.7
2024 - $372.7
2025 - $372.7
2026 - $372.7
2022 2023 2024 2025 2026
to to to to to
Cities, 2022 Cities, 2023 Cities, 2024 Cities, 2025 Cities 2026
Counties, to Counties, to Counties, to Counties, to Counties, to
DOT DOT DOT DOT DOT DOT DOT DOT DOT DOT
March 9, 2021

## Slide 8
Federal Funding Status
The FAST Act authorizes federal funding through September 30, 2021.
FAST Act funding allocations were determined by Commission in 2016.
The next Highway Trust Fund cliff is in early FFY 2022, leaving uncertainty in all but one year of this next five-year program.
Contingency plan has been developed should significant reduction in federal funding occur. Continue to identify specific project impacts with this Program.
Recent annual appropriations have included additional funding beyond authorized levels.
March 9, 2021

## Slide 9
  At what levels should the line item targets be programmed?
  March Action Item: Line Item Targets for Programming
March 9, 2021
as shown Feb 9, 2021
 | DRAFT 2022 - 2026 IOWA HIGHWAY PROGRAM |  |  |  |  |  |  | 
 |  |  |  | PROJECT ESTIMATED COSTS X $1000 |  |  |  | 
 | LOCATION | FUNDING | TYPE OF WORK | 2022 | 2023 | 2024 | 2025 | 2026
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 1000 | 1000 | 1000 | 1000 | 1000
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 250 | 500 | 750 | 1000 | 1000
 | EMERGENCY & CONTINGENCY - U-STEP/C-STEP |  | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 20000 | 20000 | 20000 | 20000 | 20000
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 360 | 360 | 360 | 360 | 360
 | BYWAY PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 85000 | 85000 | 85000 | 85000 | 85000
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 35350 | 35350 | 35350 | 35350 | 35350
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 500 | 1000 | 1500 | 2000 | 2500
 | STATEWIDE RAILROAD CROSSINGS |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE ROADSIDE IMPROVEMENT |  | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE TRAFFIC CONTROL DEVICES |  | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000

## Slide 10
Estimated Income
A. Primary Road Fund (PRF) 719.0 5.0 721.2 5.1 725.8 6.7 729.8 7.2
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 365.7 7.0 365.7 7.0 365.7 7.0 365.7 7.0
(based on $280M )
Estimated Income Total 1244.7 12.0 1246.9 12.1 1251.5 13.7 1255.5 14.2
Allocations
E. Budget (PRF)
Operations/Maintenance 363.8 -9.8 375.5 -10.7 387.0 -10.3 398.6 -10.1
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 45.3 0.3 45.3 0.5 45.3 0.8 45.3 1.0
G. Statewide Consultant Services 85.0 85.0 85.0 85.0
H. Statewide Contract Maintenance 35.4 0.5 35.4 1.0 35.4 1.5 35.4 2.0
I. RR Crossing Protection 5.0 5.0 5.0 5.0
Allocations Total 534.5 -9.0 546.2 -9.2 557.7 -8.0 569.3 -7.1
Funds Available for ROW/Construction 710.2 21.0 700.7 21.3 693.8 21.7 686.2 21.3
2022 2022 2023 2023 2024 2024 2025 2025
(Mar ‘20) (Mar ‘21) (Mar ‘20) (Mar ‘21) (Mar ‘20) (Mar ‘21) (Mar ‘20) (Mar ‘21)
change change change change
2022 - 2025 Highway Program Funding with Possible Changes
That Could Impact Funds Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 9, 2021

## Slide 11
Estimated Income
A. Primary Road Fund (PRF) 724.0 726.3 732.5 737.0 743.3
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 372.7 372.7 372.7 372.7 372.7
Estimated Income Total 1256.7 1259.0 1265.2 1269.7 1276.0
Allocations
E. Budget (PRF)
Operations/Maintenance 354.0 364.8 376.7 388.5 400.4
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 45.6 45.8 46.1 46.3 46.3
G. Statewide Consultant Services 85.0 85.0 85.0 85.0 85.0
H. Statewide Contract Maintenance 35.9 36.4 36.9 37.4 37.9
I. RR Crossing Protection 5.0 5.0 5.0 5.0 5.0
Allocations Total 525.5 537.0 549.7 562.2 574.6
Funds Available for ROW/Construction 731.2 722.0 715.5 707.5 701.4
2022 2023 2024 2025 2026
2022 – 2026 Highway Program Funding
Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 9, 2021

## Slide 12
Projected Funds as of March 2020 675.2 700.7 693.8 686.2 686.2 686.2 686.2 686.2 686.2 686.2
Highway Program Components
Interstate Stewardship 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0 195.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 137.8 226.7 217.6 102.1
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 30 ECL Lisbon to ECL Mechanicsville 17.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 200.5 111.8 68.9 125.4
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (50.1) (50.3) (25.0) (19.5) 34.4 87.8 84.7 106.2 91.2 76.2
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 9, 2021
    Added 2026 project completion cost

## Slide 13
Projected Funds as of March 2021 731.2 722.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Program Balance (FY 20) Carryover (52.3)
Federal FY 2020 Redistribution 45.8
Operations Budget Reversion (FY 20) 4.4
COVID Relief Funds 55.5
Cash Flow Adjustment (70.0) (35.0)
Projected Funds 714.6 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0 195.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 137.8 226.7 217.6 102.1
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 30 ECL Lisbon to ECL Mechanicsville 17.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 200.5 111.8 68.9 125.4
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (10.7) (64.0) (3.3) 1.8 49.6 103.0 99.9 121.4 106.4 91.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 9, 2021
    Changes to Projected Funds

## Slide 14
Projected Funds as of March 2021 714.6 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
FY 2021 Projects Rescheduled 40.1
Projected Funds 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 182.0 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0 195.0
Interstate Stewardship 1.2
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0 195.0
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Non-Interstate Capacity/System Enhancement 137.8 226.7 217.6 102.1
Non-Interstate Capacity/System Enhancement 11.6
US 61 Des Moines N of Mediapolis to N of IA 78 24.8 0.1
US 30 Missouri Valley bypass 12.6 27.0
US 30 ECL Lisbon to ECL Mechanicsville 17.0
US 61 1 mi N of IA 78 to 2 mi S of IA 92 42.9 51.5
US 63 NW Oskaloosa bypass 12.3 0.3
Major Interstate Capacity/System Enhancement 200.5 111.8 68.9 125.4
Major Interstate Capacity/System Enhancement 27.3
I-35 Polk/Story 2.0 1.0
I-80 Dallas 0.2
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (10.7) (64.0) (3.3) 1.8 49.6 103.0 99.9 121.4 106.4 91.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 9, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled

## Slide 15
Projected Funds as of March 2021 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 183.2 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0 195.0
Interstate Stewardship 14.4 15.9 (9.3) (25.6) (21.0)
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 2.7
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization (0.5) 0.4 1.1 (0.1) 0.3
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Safety Specific 1.9
Safety Specific (target increase) 5.0 6.0 7.0 8.0 9.0 10.0 11.0 12.0 13.0 14.0
Non-Interstate Capacity/System Enhancement 149.4 226.7 217.6 102.1 109.6
Non-Interstate Capacity/System Enhancement (15.7) (36.2) 48.7 26.9 30.3
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 30 ECL Lisbon to ECL Mechanicsville
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
Major Interstate Capacity/System Enhancement 227.8 111.8 68.9 125.4 52.2
Major Interstate Capacity/System Enhancement 60.2 (21.8) 1.6 (15.8) 24.3
I-35 Polk/Story 1.2
I-80 Dallas
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (78.7) (28.3) (52.4) 8.4 6.7 48.8 83.7 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 9, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2022 to 2025, add 2026
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?

## Slide 16: 2022-2026 Highway Program Analysis (with updated revenue, FY 2021 projects rescheduled, project cost updates and schedule updates)
Chart: 
| 2022 | 2023 | 2024 | 2025 | 2026
Interstate Stewardship | 197.6 | 162.1 | 143.5 | 151.7 | 149
Major Interstate | 288 | 90 | 70.5 | 109.6 | 76.5
Non-Interstate Pavement Modernization | 117.7 | 140 | 145 | 150 | 155
Non-Interstate Bridge Modernization | 64.5 | 101.7 | 110.6 | 125.8 | 140.3
Non-Interstate Capacity/Enhancement | 133.7 | 190.5 | 266.3 | 129 | 139.9
Safety | 31.9 | 31 | 32 | 33 | 34
Projected Revenue

## Slide 17
Highway Program Components
Interstate Stewardship 197.6 162.1 143.5 151.7 149.0 175.0 180.0 185.0 190.0 195.0
- Funds in years 2027 and beyond are placeholders (not programmed yet)
- Projects in 2022-2026 are specifically identified in the highway program
- Identified projects are 33% roadway reconstruction, 20% pavement resurfacing and maintenance, 26% bridge replacements,
7% bridge repairs or overlays, 6% rest area improvements and maintenance, 8% other (traffic signs, erosion control, lighting, etc.)
- Major projects continuing in the current program include:
Dallas I-80 from US 6/169 to Co Rd R16 reconstruction in 2022-2024
Johnson I-80/380/US 218 Interchange reconstruction in 2022-2023
Johnson I-80 1st Ave Interchange reconstruction in Coralville recommended to move from 2024 to 2023 to align with BUILD Grant timeline
Linn I-380 Boyson Rd Interchange reconstruction in Hiawatha in 2025
Polk I-80 from Northeast mixmaster to US 65 recommend to move from beginning in 2024 to beginning 2025
Polk I-35/80 Hickman interchange reconstruction beginning in 2025
Polk I-35/80/235 Northeast mixmaster improvements in 2023-2024
Poweshiek I-80/IA 146 Interchange reconstruction at Grinnell in 2022
Warren NB I-35 from S of Co Rd G14 to N of Adams Street reconstruction recommend to move from 2025 to 2026
Warren NB I-35 from Clarke County to Clanton Creek paving recommend to move from 2025 to 2026
Woodbury I-29/IA 141 Interchange reconstruction recommend to move from 2023 to 2024
- There are four rest area building replacements:
Iowa EB I-80 in 2022 is currently programmed
Iowa EB I-80 truck parking expansion is recommended to move from 2023 to 2024
Linn SB I-380 in 2023 is currently programmed
Mills NB I-29 in 2021 is currently programmed
Polk EB I-80 in 2026 is recommended to be programmed
Pottawattamie WB I-80 in 2025 is currently programmed
- Recommend adding weigh station ramp/parking improvements with one site per year
- Recommend adding I-235 ramp metering in 2023
- Major projects for consideration to add to the program this year include:
Warren NB I-35 from N or North River to S of Badger Creek in 2026
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 9, 2021

## Slide 18
Highway Program Components
Non-Interstate Pavement Modernization 117.7 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
- Funds in Years 2023 and beyond are placeholders (no specific projects identified)
- Projects in 2022 will be specifically identified in the highway program (to be handed
out in April)
- 2022 draft projects are 96% pavement resurfacing, 3% pavement widening, and 1% other
Non-Interstate Bridge Modernization 64.5 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
- Funds in years 2027 and beyond are placeholders (not programmed yet)
- Projects in 2022-2026 will be specifically identified in the highway program (to be handed
out in April)
- Draft projects are 65% bridge replacements, 33% bridge repairs or overlays, 2% culvert repairs
or replacements, 1% other
Safety Specific 31.9 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
- Funds in Years 2023 and beyond are mostly placeholders (few specific projects identified)
- Recommend increasing safety target by $5 million in FY 2022 and increasing $1 million per year
- Projects in 2022 will be specifically identified in the highway program (to be handed out in April)
- 2022 draft projects are 78% shoulder paving and widening, 10% interstate median guardrail,
12% other
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 9, 2021

## Slide 19
Highway Program Components
Non-Interstate Capacity/System
Enhancement 133.7 190.5 266.3 129.0 139.9 71.4 6.7
- Funds in Years 2027 and beyond are project completion costs for projects already in Program
- Dubuque Iowa 3 reconstruction delayed from 2021 to 2022
Major Interstate Capacity/System
Enhancement 288.0 90.0 70.5 109.6 76.5 51.2 50.0
- Funds in years 2027 and beyond are project completion costs for projects already in Program
- Johnson I-80 from East of Iowa 1 to E of Co Rd X30 schedule adjusted due to delayed letting and
concept modification
- Scott I-80 Mississippi River Bridge moved to begin in 2026 from 2025 due to development schedule
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 9, 2021

## Slide 20
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
6 | Pottawattamie | 6th St in Council Bluffs to I-80 (Broadway Avenue) | Operational & Safety | Construct Intersection Improvements (TJ to city) | Y | Complete | $10 M
6 | Scott | Kimberly Rd in Davenport from N Brady St to Elmore Ave | Operational & Safety | Construct Intersection Improvements | Y | -- | 
12 | Woodbury | Gordon Dr Viaduct in Sioux City | Structurally Deficient | Replace Bridge | Y | Active | $90 M
18 | Clay/Palo Alto/ Kossuth/Hancock | Spencer to Garner | Mobility & Safety | Modernize 2-Lane | Y | Active | 
20 | Dubuque | W of Old Highway Rd to Devon Drive in Dubuque | Operational & Safety | Modernize intersection with Northwest Arterial | Y | Begin FY 21 | 
20 | Dubuque | Mississippi River Bridge | Functionally Obsolete | Add 2nd Bridge | Y | Complete | $100 M
30 | Carroll/Greene/ Boone | Co Rd N33 to E Jct US 169 | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | -- | $265 M $130 M
30 | Story | Intersections in Nevada | Operational & Safety | Construct Interchanges | NA | Complete | $25 M
30 | Tama | Intersection At Meskwaki Casino | Operational & Safety | Construct Interchange | NA | -- | 
30 | Cedar | Lisbon bypass to Stanwood | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Complete | $100 M $50 M
30 | Clinton | Calamus to US 61 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Complete | $75 M $40 M
34 | Mills/Montgomery/ Adams | E of Glenwood to E of Creston | Mobility & Safety | Modernize 2-Lane | Y | Begin FY 21 | 
March 9, 2021

## Slide 21
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
34 | Union/ Clarke/Lucas/ Monroe/Wapello | E of Creston to W of Ottumwa | Mobility & Safety | Modernize 2-Lane | Y | -- | 
35 | Story | N of IA 210 to E 13th St in Ames | Add Capacity | Construct 6-Lane | Y | Active | $120 M
35/80 | Polk | I-235 Interchange SW of Des Moines | Add Capacity and Improve Operations | Reconstruct Interchange, Add Lanes | Y | Active | $300 M
35/80/235 | Polk | SW to NE Mixmasters | Add Capacity and Improve Operations | Add Lanes, Modernize, and/or ICM strategies | Y | Active | Phase I - $90 M
58 | Black Hawk | Greenhill Road in Cedar Falls | Operational & Safety | Construct Interchange | Y | Complete | $32 M
63 | Davis/Wapello | Bloomfield to Ottumwa | Provide 4-Lane Continuity Mobility and Safety | Construct 4-Lane or Modernize 2-Lane | N Y | -- Begin FY 21 | 
63 | Mahaska/ Poweshiek | N of Oskaloosa to I-80 | Operational | Modernize 2-Lane | Y | -- | 
63 | Poweshiek/Tama/ Black Hawk | W Jct US 6 to Hudson | Mobility and Safety | Modernize 2-Lane | Y | Active | 
65/69 | Warren | Hillcrest Ave in Indianola to IA 5 | Operational & Safety | Improve Intersections | NA | -- | 
69 | Polk | Army Post Road to I-80 | Operational & Safety |  | Y | Active | 
67 | Scott | Mississippi River Bridge | Structurally Deficient | Replace Bridge (IL Lead) | Y | -- | $110 M
74 | Scott | North of Lincoln Road in Bettendorf to I-80 in Davenport | Add Capacity | Construct 6-Lane | N | Complete | $150 M
75 | Plymouth | In Hinton | Operational & Safety | Modernize 4-Lane | NA | -- | 
March 9, 2021

## Slide 22
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
75 | Plymouth/Sioux | IA 60 in Le Mars to IA 10 | Operational | Modernize 2-Lane | Y | -- | 
80 | Dallas/Polk | Co Rd R16 to Jordan Creek | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Polk/Jasper/ Poweshiek/Iowa | Altoona to I-380 | Add Capacity | Construct 6-Lane | Y | Active | 
80 | Cedar | West Branch to Cedar River | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Cedar/Scott | County Road Y26 to W of I-280 | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Scott | W of I-280 to W of I-74 | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of I-74 to W of Middle Rd in Bettendorf | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of Middle Rd in Bettendorf to Mississippi River Bridge | Capacity & Operations | Replace Interchange (Bi-State req. 06/10/08) | NA | Active | 
80 | Scott | Mississippi River Bridge in Le Claire | Add Capacity | Replace with Wider Bridge (IL Lead) | Y | Active | $150 M
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 9, 2021

## Slide 23
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
92 | Mahaska | SE Oskaloosa Bypass | Operational | Construct 2-Lane Bypass | Y | Inactive | 
100 | Linn | Collins Rd in Cedar Rapids from W of Council St to 1st Ave | Add Capacity | Construct 6-Lane (Local Lead) | Y | Active | 
150/52 | Benton/ Buchanan/ Fayette/ Winneshiek | I-380 to Minnesota State Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
151 | Linn | Co Rd X20 Intersection in Springville | Operational & Safety | Construct Interchange | NA | Complete | $23 M
380 | Johnson/Linn | Forevergreen Rd to S of US 30 | Add Capacity | Construct 6-Lane | Y | Complete | $224 M
380 | Linn | S of US 30 to N of US 30 | Operational | Reconstruct interchange | Y | Proposed FY 22 | 
380 | Linn | S of US 30 to Blairs Ferry Road | Add Capacity | Construct 6-Lane | Y | -- | 
380 | Linn | Blairs Ferry Rd to County Home Rd | Add Capacity | Construct 6-Lane | N | Complete | $27.2 M
380 | Linn | I-380 through Cedar Rapids | Operational | ICM strategies | Y | Proposed FY 22 | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 9, 2021

## Slide 24
  Projects in the 2021-2024 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
FY 2021-2025 Highway Program Objectives
March 9, 2021
as approved April 14, 2020

## Slide 25
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Beyond | Total | Score | Rank
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  |  | 4.9 | 30.7 | 39.3 | 67.6 | 1.2 | 143.7 | 45 | 3
I-80 Scott: Middle Road Interchange (4R or MI) |  |  |  |  |  |  |  |  |  |  |  | 52 | 5
I-380 Johnson: Segment 1 N of Forevergreen Rd to N of Penn St |  |  | 9.7 | 29.8 | 18.0 |  |  |  |  |  | 29.8 | 46 | 4
I-380 Johnson: Segment 2 N of Penn St to N of Iowa River |  |  |  |  |  |  |  | 40.0 | 46.1 | 27.0 | 113.1 | 43 | 2
I-380 Johnson: Segment 3 N of Iowa River to N of 120th St NW |  |  |  |  |  |  | 17.8 | 10.2 |  |  | 28.0 | 46 | 4
I-380 Linn: Segment 4 N of 120th St NW to US 30 |  |  |  |  |  | 33.5 | 19.2 |  |  |  | 52.7 | 38 | 1
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  |  |  | 15.4 | 32.5 | 47.9 | 54 | 6
Stewardship (Shelf-Ready) Projects | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  |  | 500.0 |  | 
    Subject to change as additional information becomes available
March 9, 2021

## Slide 26
 |  |  |  |  |  |  |  |  |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 2 Fremont: Resiliency improvements (Phase II) | 0.1 | 3.5 |  |  |  |  |  |  | 63 | 5
IA 3 Cherokee: 1.3 miles E of US 59 to 1.8 miles E of US 59 |  |  |  |  | 4.4 |  |  |  | 72 | 9
IA 3 Plymouth: W side of Remsen to Cherokee County |  | 2.8 |  |  |  |  |  |  | 76 | 10
IA 7 Buena Vista: IA 110 Intersection in Storm Lake | 0.9 |  |  |  |  |  |  |  | 69 | 7
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  | 18.9 | TBD | TBD |  |  | 40 | 1
IA 21 Iowa: South of Belle Plaine |  |  |  | 5.0 |  |  |  |  | 82 | 11
US 34 Wapello: Wildwood Dr to W Jct US 63 in Ottumwa |  |  |  |  | 32.1 |  |  |  | 41 | 2
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  | 45 | 3
US 75 Sioux: N of Sioux Center to S Jct US 18 |  |  |  | 11.1 |  |  |  |  | 71 | 8
US 75 Plymouth: Hinton |  |  |  |  | 3.5 | 6.1 |  |  | 71 | 8
IA 76 Clayton: McGregor | 4.8 |  |  |  |  |  |  |  | 65 | 6
IA 149: Des Moines River Bridge to Woodland Ave in Ottumwa |  |  |  | 5.9 |  |  |  |  | 55 | 4
Polk: Traffic Incident Management (TIM) Training Center |  |  | TBD | TBD |  |  |  |  |  | 
US 20 Black Hawk: Iowa 21 to E Jct I-380 Interchange (ITS) |  |  |  |  | 1.7 |  |  |  |  | 
Culverts/Slide Repairs (multiple locations statewide) | 2.9 | 0.8 | 1.0 | 0.2 |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 9, 2021

## Slide 27
 |  |  |  |  |  |  |  |  | Priority |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Corridor | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | N |  | 
US 18 Kossuth/Hancock: 1.65 miles East of Co Rd P64 to Hutchins (Super-2) | 4.8 |  |  |  |  |  |  |  | N | 75 | 4
US 30 Cedar: WCL Mechanicsville to WCL Stanwood (Super-2) |  |  |  | 0.4 | 10.1 |  |  |  | Y | 70 | 3
US 30 Cedar: WCL Stanwood to ECL Clarence (Super-2) |  |  |  |  |  | 11.5 |  |  | Y | 70 | 3
US 63 Tama: Toledo to Co Rd E29 (Super-2) |  |  | 0.1 | 8.1 |  |  |  |  | N | 80 | 5
US 63 Tama: NCL Traer to Hudson (Super-2) |  |  |  |  | 7.1 |  |  |  | N | 75 | 4
US 151 Linn: Co Rd X-20 Interchange at Springville |  |  |  |  | 24.0 |  |  |  | N | 57 | 1
IA 58: Greenhill Road Interchange |  |  |  |  | 32.1 |  |  |  | N | 59 | 2
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  | 17.0 |  |  |  |  |  |  |  |  | 
IA 81 Van Buren: Missouri State Line to IA 2 | TBD |  |  |  |  |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 9, 2021

## Slide 28: Decision Points
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 9, 2021

## Slide 29
March 9, 2021
  Projects in the 2022-2025 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
Potential FY 2022-2026 Highway Program Objectives

## Slide 30: Next Steps
March Business Meeting
Action Item: Line Item Targets for Programming
Next March Workshop
Discuss 2022-2026 Highway Program Options
Determine 2022-2026 Highway Program Objectives
April
Develop the Draft 2022-2026 Highway Program
Action Item: 2022-2026 Highway Program Objectives
March 9, 2021