## Slide 1
2025-2029 Highway Program Development
3/2/2023
March 12, 2024

## Slide 2
Agenda
TOPIC 1
2025-2029 Highway Program Funding
TOPIC 2
Statewide Line Items
TOPIC 3
Highway Program Analysis
TOPIC 4
Program Development Considerations
TOPIC 5
Determine Highway Program Objectives
TOPIC 6
Next Steps

## Slide 3
March 12, 2024
Highway Program Development Schedule (2025-2029)
March 2024
  Discuss 2025-2029 available Highway Program funding
  Discuss 2025-2029 Highway Program options
  Determine 2025-2029 Highway Program objectives
  Action Item: Line Item Targets for Programming
April 2024
  Develop the Draft 2025-2029 Highway Program
  Action Item: 2025-2029 Highway Program objectives
May 2024
  Present the Draft 2025-2029 Iowa Transportation Improvement Program to the public (including all previous Program approvals and Draft 2025-2029 Highway Program)
June 2024
  Action Item: Approve the 2025-2029 Iowa Transportation improvement Program

## Slide 4
March 12, 2024
2025-2029 Iowa Highway Program
Decision Points
Should projects in the 2025-2028 Program continue to be programmed with cost/schedule updates?
2. How should Program be balanced?

## Slide 5
Topic 1
2025-2029 Highway Program Funding

## Slide 6
March 12, 2024

## Slide 7
March 12, 2024
2025-2029 Iowa Highway Program Funding Assumptions
RUTF/TIME-21
(For Highway Planning Purposes Only)
Overall forecast is conservative
Forecast continues to reflect expected reduction in fuel tax revenue
TIME-21 funding cap of $225 million has been met
Average combined RUTF/TIME-21 growth of 0.7% annually

## Slide 8
March 12, 2024
Federal Funding Status
  FFY 2024 Appropriation:
    Bill signed into law on March xx, 2024
    Highway Infrastructure Program bridge funding not included in FFY 2024 appropriations bill
  August Redistribution expected to be large once again
  Federal Funding forecast increased due to current estimates of August Redistribution to Iowa
  Infrastructure Bill authorizes federal funding through September 30, 2026, leaving some funding uncertainty for the last three years of this Program.
  Infrastructure Bill funding allocations based on Commission action in June 2022.
  The next Highway Trust Fund cliff is in 2028.

## Slide 9
March 12, 2024
2025-2029 Forecast of Iowa Federal-Aid Formula Transportation Authorized Funds
(x $1,000)
(For Highway Planning Purposes Only)
Total Federal-Aid Formula Funds Forecast to DOT Programs
(x $1,000,000
2025 - ($524.1 @ 87.0% Obligation Authority = $456.0) + (August Redistribution $60.0) = $516.0
2026 - ($533.3 @ 87.0% Obligation Authority = $464.0) + (August Redistribution $30.0 + $18.4 HIP Bridge) = $512.4
2027 - ($533.3 @ 87.0% Obligation Authority = $464.0) + (August Redistribution $30.0 + $18.4 HIP Bridge) = $512.4
2028 - ($533.3 @ 87.0% Obligation Authority = $464.0) + (August Redistribution $30.0 + $18.4 HIP Bridge) = $512.4
2029 - ($533.3 @ 87.0% Obligation Authority = $464.0) + (August Redistribution $30.0 + $18.4 HIP Bridge) = $512.4

## Slide 10
March 12, 2024
2025-2028 Highway Program Funding with Possible Changes That Could Impact Funds Available for ROW/Construction
($ in millions)
(For Highway Planning Purposes Only)
 |  | 2025 |  | 2025 |  | 2026 |  | 2026 |  | 2027 |  | 2027 |  | 2028 |  | 2028
 |  | (Mar '23) |  | (Mar '24) |  | (Mar '23) |  | (Mar '24) |  | (Mar '23) |  | (Mar '24) |  | (Mar '23) |  | (Mar '24)
 |  |  |  | change |  |  |  | change |  |  |  | change |  |  |  | change
Estimated Income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A. Primary Road Fund (PRF) |  | 775.1 |  | 42.5 |  | 783.6 |  | 43.1 |  | 787.1 |  | 43.7 |  | 793.7 |  | 44.6
B. Est. Time 21 Revenue to PRF |  | 135.0 |  |  |  | 135.0 |  |  |  | 135.0 |  |  |  | 135.0 |  | 
C. Miscellaneous (State) |  | 25.0 |  |  |  | 25.0 |  |  |  | 25.0 |  |  |  | 25.0 |  | 
D. Federal Aid (Formula) |  | 505.1 |  | 10.9 |  | 513.3 |  | -0.9 |  | 513.3 |  | -0.9 |  | 513.3 |  | -0.9
Estimated Income Total |  | 1440.2 |  | 53.4 |  | 1456.9 |  | 42.2 |  | 1460.4 |  | 42.8 |  | 1467.0 |  | 43.7
Allocations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E. Operations/Maintenance Budget (PRF) |  | 390.8 |  | 18.1 |  | 402.9 |  | 12.5 |  | 415.1 |  | 18.4 |  | 427.3 |  | 12.8
F. Back of Program Line Items and Rail Highway |  | 186.0 |  | 13.9 |  | 187.0 |  | 15.9 |  | 188.0 |  | 15.9 |  | 193.6 |  | 16.0
Allocations Total |  | 576.8 |  | 32.0 |  | 589.9 |  | 28.4 |  | 603.1 |  | 34.3 |  | 620.9 |  | 28.8
Funds Available for ROW/Construction |  | 863.4 |  | 21.4 |  | 867.0 |  | 13.8 |  | 857.3 |  | 8.5 |  | 846.1 |  | 14.9
Black: Previous discussion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Green: Changes since previous discussion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 11
March 12, 2024
2025-2029 Highway Program Funding Available for ROW/Construction
($ in millions)
(For Highway Planning Purposes Only)
 |  | 2025 |  | 2026 |  | 2027 |  | 2028 |  | 2029
Estimated Income |  |  |  |  |  |  |  |  |  | 
A. Primary Road Fund (PRF) |  | 817.6 |  | 826.7 |  | 830.8 |  | 838.3 |  | 845.5
B. Est. Time 21 Revenue to PRF |  | 135.0 |  | 135.0 |  | 135.0 |  | 135.0 |  | 135.0
C. Miscellaneous (State) |  | 25.0 |  | 25.0 |  | 25.0 |  | 25.0 |  | 25.0
D. Federal Aid (Formula) |  | 516.0 |  | 512.4 |  | 512.4 |  | 512.4 |  | 512.4
Estimated Income Total |  | 1493.6 |  | 1499.1 |  | 1503.2 |  | 1510.7 |  | 1517.9
Allocations |  |  |  |  |  |  |  |  |  | 
E. Operations/Maintenance Budget (PRF) |  | 408.9 |  | 415.4 |  | 433.5 |  | 440.1 |  | 458.2
F. Back of Program Line Items and Rail Highway |  | 199.9 |  | 202.9 |  | 203.9 |  | 209.6 |  | 210.6
Allocations Total |  | 608.8 |  | 618.3 |  | 637.4 |  | 649.7 |  | 668.8
Funds Available for ROW/Construction |  | 884.8 |  | 880.8 |  | 865.8 |  | 861.0 |  | 849.1
Black: Previous discussion |  |  |  |  |  |  |  |  |  | 

## Slide 12
Topic 2
Statewide Line Items

## Slide 13
March 12, 2024
Draft 2025-2029 Iowa Highway Program Line Items
($ in thousands)
  At what levels should the line item targets be programmed?
  March Action Item:
  Line Item Targets for Programming

## Slide 14
Topic 3
Highway Program Analysis

## Slide 15
March 12, 2024 as presented February 13, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)

## Slide 16
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)

## Slide 17
March 12, 2024
Stewardship Targets - Possible Adjustments
Non-Interstate Pavement Modernization
  Pavement needs are increasing faster than current stewardship target increases
  Increase 2027 target by $5m and 2028-2034 targets by $10m annually
Non-Interstate Bridge Modernization
  Significant increases in stewardship investment and innovative preventative maintenance has resulted in significant progress in reducing Iowa’s primary system bridges in poor condition
  Reduce the magnitude of future stewardship target increases by $5m in 2027 and $10m annually in 2028-2034.
  Stewardship investment targets continue to grow through 2034 with this possible change
Safety Specific
  Allow for quicker implementation of statewide centerline rumble strip program. Ninety-six percent implementation on two lane highways by end of 2025
  One time increase of $1.5m in 2025 target

## Slide 18
March 12, 2024
2025-2034 Stewardship Targets with Possible Changes
($ in millions)
(For Highway Planning Purposes Only)

## Slide 19
March 12, 2024
2025-2034 Stewardship Targets
($ in millions)
(For Highway Planning Purposes Only)

## Slide 20
March 12, 2024
Underfunded Projects with Possible Changes
($ in millions)
(For Highway Planning Purposes Only)

## Slide 21
March 12, 2024
Underfunded Projects
($ in millions)
(For Highway Planning Purposes Only)

## Slide 22
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)

## Slide 23
March 12, 2024
Notable 2025-2028 Iowa Highway Program Changes
US 30 Missouri Valley Bypass
  Decrease in program amount from $113.2m to $62.6m
  Decrease due to changes in design
    Removal of flood gates
    Levee removal
US 61 Louisa County
  Move project one year in program
  Due to design changes

## Slide 24
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)

## Slide 25
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)

## Slide 26
March 12, 2024
2025-2029 Highway Program Analysis
($ in millions)
(With Updated Revenue, FY 24 Projects Rescheduled, Project Cost and Schedule Updates)
(Updated Revenue includes Assumed Grant Awards)
(For Highway Planning Purposes Only)

## Slide 27
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)
Highway Program Components
Interstate Stewardship 306.7 226.4 179.3 185.0 190.0 195.0 200.0 205.0 210.0 215.0
- Funds in years 2030 and beyond are placeholders (not programmed yet)
- Projects in 2025-2029 are specifically identified in the highway program and include the following major schedule changes and additions:
Adair I-80 bridges at Co Rd N54 delayed beyond 2029
Benton I-380 pavement rehabilitation advanced from 2026 to 2025
Cass I-80 bridges at 770th St delayed to 2029
Franklin I-35 pavement rehabilitation added to 2025
Iowa I-80 pavement rehabilitation advanced from 2027 to 2026
Mills I-29 pavement rehabilitation added to 2025
Polk I-80 Hickman Interchange work advanced from 2027 to 2026
Poweshiek I-80 US 63 Interchange delayed from 2028 to 2029
Poweshiek I-80 pavement rehabilitation added to 2025
Warren I-35 pavement replacement changed to pavement rehabilitation
Worth I-35 pavement rehabilitation advanced from 2027 to 2026
Proposed Highway Program Extended Highway Program
2025 2026 2027 2028 2029 2030 2031 2032 2033 2034

## Slide 28
March 12, 2024
Changes to Rest Area Program
Rest Area Program was reevaluated since completion of 2024 Program
Emphasis placed on retaining/adding truck parking
  Additions to I-29 prioritized to mitigate losses from Sergeant Bluff rest area closure
  Delayed removals of parking only sites to end of rest area program
    Addition of vault toilet facilities at parking only sites
Programmed rest area projects in the draft Program include:
  2025
    Linn I-380 SB parking (+14 spaces)
    Iowa I-80 WB rest area building near Victor
  2026
    Monona I-29 NB parking near Onawa (+25 spaces)
    Woodbury I-29 NB/SB rest area removal near Sergeant Bluff (-29 spaces)
  2027
    Monona I-29 NB rest area building near Onawa
    Iowa I-80 WB parking near Victor (+16 spaces)
  2028
    Polk I-80 EB rest area building near Mitchellville
  2029
    Monona I-29 SB rest area building near Onawa
    Polk I-80 EB parking near Mitchellville (+11 spaces)
2025-2029 Program will add 14 spaces on I-380, add 10 spaces on I-29*, and add 27 spaces on I-80
* Includes additional parking at reconstructed Salix weigh station

## Slide 29
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)
Highway Program Components
Non-Interstate Pavement Modernization 151.2 155.0 205.0 220.0 230.0 235.0 240.0 245.0 250.0 255.0
- Funds in Years 2026 and beyond are placeholders (no specific projects identified except for 3R reconstruction)
- Projects in 2025 and 3R reconstruction projects in 2027-2029 will be specifically identified in the highway program (to be handed
out in April)
- Includes proposed adjustment to stewardship target.
Non-Interstate Bridge Modernization 160.9 148.9 172.8 179.6 197.0 200.0 205.0 210.0 215.0 220.0
- Funds in years 2030 and beyond are placeholders (not programmed yet)
- Projects in 2025-2029 will be specifically identified in the highway program (to be handed
out in April)
-Includes proposed adjustment to stewardship target.
Safety Specific 35.4 34.0 35.0 36.0 37.0 38.0 39.0 40.0 41.0 42.0
- Funds in Years 2026 and beyond are placeholders (no specific projects identified)
- Projects in 2025 will be specifically identified in the highway program (to be handed out in April)
-Includes proposed adjustment to 2025 Safety target
Proposed Highway Program Extended Highway Program
2025 2026 2027 2028 2029 2030 2031 2032 2033 2034

## Slide 30
March 12, 2024
2025-2034 Highway Program Analysis
($ in millions)
(For Highway Planning Purposes Only)
Highway Program Components
Non-Interstate Capacity /
System Enhancement 163.3 213.1 260.4 166.7 220.5 106.6
- Funds in Years 2030 and beyond are project completion costs for projects already in Program
- Black Hawk US 218 delayed one year from 2025 to 2026
- Dubuque US 52/IA 3 delayed one year from 2024 to 2025
- Louisa US 61 delayed one year (ROW moves from 2025 to 2026 with corresponding changes in construction schedule)
Major Interstate Capacity /
System Enhancement 208.1 160.2 117.3 67.1 82.3 77.7 1.2
- Funds in years 2030 and beyond are project completion costs for projects already in Program
- Johnson I-80 advanced median grading from 2026 to 2025
Proposed Highway Program Extended Highway Program
2025 2026 2027 2028 2029 2030 2031 2032 2033 2034

## Slide 31
March 12, 2024
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent with SLRTP | Planning Status | Approx Cost
1 | Johnson/Linn | I-80 to US 30 | Mobility & Safety | Modernize 2-Lane | Y | -- | 
6 | Scott | Kimberly Rd in Davenport from N Brady St to Elmore Ave | Operational & Safety | Construct Intersection Improvements | Y | -- | 
12 | Woodbury | Gordon Dr Viaduct in Sioux City | Structurally Deficient | Replace Bridge | Y | Active | $150 M
18 | Clay / Palo Alto / Kossuth / Hancock | Spencer to Garner | Mobility & Safety | Modernize 2-Lane | Y | Complete | 
18 | Floyd / Chickasaw | Charles City to US 63 | Mobility & Safety | Modernize 2-Lane | Y | Begin in FY 24 | 
18 | O'Brien / Clay | O'Brien Co Line to US 71 | Mobility & Safety | Modernize 2-Lane | Y | Begin in FY 24 | 
20 | Dubuque | W of Old Highway Rd to Devon Dr in Dubuque | Operational & Safety | Access Control | Y | -- | 
20 | Dubuque | Intersection with NW Arterial | Operational & Safety | Construct Intersection Improvements | Y | Complete | 
20 | Dubuque | Mississippi River Bridge | Functionally Obsolete | Add 2nd Bridge or Replace | Y | -- | 
30 | Carroll / Greene / Boone | Co Rd N33 to E Jct US 169 | Mobility & Safety | Construct 4-Lane or Modernize 2-Lane | N/Y | -- | $265 M/ $130 M
30 | Tama | Intersection at Meskwaki Casino | Operational & Safety | Construct Interchange | NA | Begin FY 24 | 
30 | Cedar/Clinton | Stanwood to Calamus | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N/Y | Complete | $100 M/ $50 M
30 | Clinton | Calamus to US 61 | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N/Y | Complete | $75 M/ $40 M
30 | Crawford / Carroll | Denison to Greene Co Line | Mobility & Safety | Modernize 2-Lane | Y | Begin in 24 | 

## Slide 32
March 12, 2024
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent with SLRTP | Planning Status | Approx Cost
30 | Harrison / Crawford | E of Missouri Valley to E of Denison | Mobility & Safety | Modernize 2-Lane | Y | -- | 
34 | Mills | RR Bridge 0.9 mi E of Co Rd L55 to Co Rd L66 | Mobility & Safety | Modernize 2-Lane | Y | Begin FY 24 | 
34 | Mills/ Montgomery/ Adams | Co Rd L66 to E. Clark County Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
34 | Union / Clarke / Lucas / Monroe / Wapello | E of Creston to W of Ottumwa | Mobility & Safety | Modernize 2-Lane | Y | Active | 
34 | Monroe / Wapello | E of Albia to W of Ottumwa | Mobility & Safety | Modernize 2-Lane | Y | Active | 
35 | Story | N of IA 315th St to 1.4 mi S of US 30 | Add Capacity | Construct 6-Lane | Y | Complete | $83 M
35 | Story | N of US 30 to 13th St in Ames | Add Capacity | Construct 6-Lane | Y | Complete | 
35 | Polk | Oralabor (IA 160) Interchange | Add Capacity and Improve Operations | Improve Interchange |  | -- | 
35/80 | Polk | I-235 Interchange SW of Des Moines | Add Capacity and Improve Operations | Reconstruct Interchange and Add Lanes | Y | Complete | $300 M
35/80 | Polk | W of IA 415 to E of NE Mixmaster | Add Capacity and Improve Operations | Reconstruct and Add Lanes | Y | -- | 
35/80/235 | Polk | SW to NE Mixmasters | Add Capacity and Improve Operations | Add, Modernize, and/or ICM Strategies | Y | Complete | Phase 1 - $90 M
63 | Davis / Wapello | Missouri St Line to Ottumwa | Mobility & Safety | Modernize 2-Lane | Y | Active | 
63 | Mahaska / Poweshiek | N of Oskaloosa to I-80 | Operational | Modernize 2-Lane | Y | -- | 
63 | Poweshiek / Tama / Black Hawk | W Jct US 6 to Hudson | Mobility & Safety | Modernize 2-Lane | Y | Complete | 

## Slide 33
March 12, 2024
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent with SLRTP | Planning Status | Approx Cost
63 | Chickasaw / Howard | New Hampton to Minnesota St Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
65/69 | Warren | Hillcrest Ave in Indianola to IA 5 | Operational & Safety | Improve Intersections | NA | -- | 
67 | Scott | Mississippi River Bridge | Structurally Deficient | Replace Bridge (IL Lead) | Y | -- | $110 M
69 | Polk | Army Post Rd to I-80 | Operational & Safety |  | Y | Complete | 
71 | Carroll / Sac | IA 141 to W of IA 175 | Mobility & Safety | Modernize 2-Lane | Y | Begin FY 24 | 
71 | Page / Montgomery / Cass / Audubon | Missouri St Line to Audubon Co Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
74 | Scott | N of Lincoln Rd in Bettendorf to I-80 in Davenport | Add Capacity | Construct 6-Lane | N | Complete | $150 M
75 | Plymouth / Sioux | IA 60 in Le Mars to IA 10 | Operational | Modernize 2-Lane | Y | -- | 
80 | Dallas | Co Rd R16 to W of Grand Prairie Parkway | Add Capacity | Construct 6-Lane | Y | Complete | 
80 | Polk / Jasper / Poweshiek / Iowa | Altoona to I-380 | Add Capacity | Construct 6-Lane | Y | Complete | 
80 | Cedar | West Branch to Cedar River | Add Capacity | Construct 6-Lane | Y | -- | $210 M
80 | Cedar / Scott | County Rd Y26 to W of I-280 | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Scott | W of I-280 to W of I-74 | Capacity and Operations | Construct 6-Lane | Y | Complete | 
80 | Scott | W of I-74 to W of Middle Rd in Bettendorf | Capacity and Operations | Construct 6-Lane | Y | Active | 

## Slide 34
March 12, 2024
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent with SLRTP | Planning Status | Approx Cost
80 | Scott | W of Middle Rd in Bettendorf to Mississippi River Bridge | Capacity and Operations | Construct 6-Lane | NA | Active | 
80 | Scott | Mississippi River Bridge in Le Claire | Add Capacity | Replace with Wider Bridge (Ill Lead) | Y | Active | 
100 | Linn | Collins Rd in Cedar Rpaids from W of Council St to 1st Ave | Add Capacity | Construct 6-Lane Local Lead) | Y | -- | 
122 | Cerro Gordo | West Side of Mason City | Operational | Convert to Urban Section (Locally Led) | Y | Active | 
141 | Polk | Towner Dr Interchange in Grimes | Operational | Local Lead | Y | Active | 
150 | Benton / Buchanan / Fayette / Winneshiek | I-380 to N of Oelwein | Mobility & Safety | Modernize 2-Lane | Y | Active | 
151 | Benton/Iowa/Linn | Amana to SCL Fairfax | Mobility & Safety | Modernize 2-Lane | Y | Begin FY 24 | 
150 / 52 | Fayette / Winneshiek | N of Oelwein to Minnesota State Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
175 | Monona | Missouri River Bridge | Structurally Deficient | Evaluate Alternatives | Y | -- | 
380 | Johnson | N of Swan Lake Rd to 120th St | Add Capacity | Construct 6-Lane | Y | Complete | $174 M
380 | Linn | S of US 30 to N of US 30 | Operational | Reconstruct Interchange/Construct 6-Lane | Y | -- | 
380 | Linn | N of US 30 to Blairs Ferry Rd | Add Capacity | Construct 6-Lane | Y | -- | 
380 | Linn | Blairs Ferry Rd to County Home Rd | Add Capacity | Construct 6-Lane | N | Complete | $47 M
380 | Linn | I-380 through Cedar Rapids | Operational | ICM Strategies | Y | -- | 
Legend: |  |  |  |  |  |  | 
- SLRTP is State Long Range Transportation Plan |  |  |  |  |  |  | 
- Inactive means no planning study work has been done or previous work is currently obsolete |  |  |  |  |  |  | 
- Active means planning study work is in progress |  |  |  |  |  |  | 
- Complete means planning study work is completed and the project could start development |  |  |  |  |  |  | 
- NA means not addressed |  |  |  |  |  |  | 

## Slide 35
March 12, 2024
2025-2033 Highway Program Candidates
($ in millions)
(For Highway Planning Purposes Only)
 | 2025 |  | 2026 |  | 2027 |  | 2028 |  |  | 2029 |  | 2030 |  | 2031 |  | 2032 |  | 2033 |  | Beyond |  | Total |  | Score |  | Rank
Major Interstate Capacity/System Enhancement (MI Funds) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of 315th St to E57/260th St |  |  |  |  |  |  |  |  |  | 2.0 |  | 6.0 |  | 38.3 |  | 37.0 |  |  |  |  |  | 83.3 |  | 38 |  | 1
I-380 Johnson: Segment 2 Swan Lake Rd to 120th St |  |  |  |  |  |  |  |  |  | 7.9 |  | 36.3 |  | 70.5 |  | 77.7 |  |  |  |  |  | 192.4 |  | 46 |  | 3
I-380 Linn: Blairs Ferry Rd to County Home Rd (add lanes) |  |  |  |  |  |  |  |  |  |  |  | 15.4 |  | 32.5 |  |  |  |  |  |  |  | 47.9 |  | 44 |  | 2
I-80 Cedar: West Branch to Cedar River |  |  |  |  |  |  |  |  |  |  |  | 4.9 |  | 4.7 |  | 65.3 |  | 68.7 |  |  |  | 143.6 |  | 48 |  | 4
I-80 Pottawattamie: Interchange with US 6 |  |  |  |  |  |  |  |  |  | 0.7 |  |  |  |  |  |  |  |  |  |  |  | 0.7 |  | 55 |  | 5
Mitigation (multiple locations statewide) | 0.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.3 |  |  |  | 

## Slide 36
March 12, 2024
2025-2033 Highway Program Candidates
($ in millions)
(For Highway Planning Purposes Only)

## Slide 37
March 12, 2024
2025-2029 Iowa Highway Program
Decision Points
Should projects in the 2025-2028 Program continue to be programmed with cost/schedule updates?
What modifications to the Program should be considered?
  Adjust non-Interstate pavement and bridge stewardship targets?
  Add projects to the Program from the Program Candidates list?
How should Program be balanced?
  Overall Program balances are reasonable, but some years may need adjustment (i.e. 2028 and 2029)
  One option to balance 2028 and 2029 could be to advance some 2029 Interstate Stewardship projects to 2028?
  What additional information would be helpful?
  Come back with scenario(s) for March 21 Workshop

## Slide 38
Topic 4
Program Development Considerations

## Slide 39
March 12, 2024
Program Development Considerations
  Construction cost inflation is moderating.
  State road funding continues to come in higher than forecast.
  The last three years of federal funding in this Program are not part of an authorization.
  Continue to prioritize bridge and pavement stewardship investments on existing highway system.
  Pursue grant funding opportunities.
  Assess balance of pavement and bridge stewardship investments.
  Balance capacity improvements with stewardship needs.
  Address major river crossing needs.

## Slide 40
Topic 5
Determine Highway Program Objectives

## Slide 41
March 12, 2024
Potential 2025-2029 Highway Program Objectives
    Safety
      Maintain increasing funding levels for safety
      Advance statewide centerline rumble strip implementation
      Expand enhanced pavement markings to non-interstate highways
    Sustainability
      Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
      Maintain increasing funding levels for non-interstate pavement modernization
      Maintain increasing funding levels for non-interstate bridge modernization
      Invest in additional stewardship projects
      Transfer jurisdiction of portions of primary roadways to cities and counties
    Accessibility
      Invest in truck parking at Interstate Rest Areas
      Invest in vault toilets at parking only sites
      Complete installation of adult changing stations at modernized rest areas
      Invest in corridor improvements
    Flow
      Invest in intelligent transportation systems infrastructure
      Invest in Super-2 improvements
      Invest in operational and Integrated Corridor Management improvements

## Slide 42
Topic 6
Next Steps

## Slide 43
Next Steps
March Business Meeting - Action Item: Line-Item Targets for Programming
March 21 Workshop - Discuss 2025-2029 Highway Program Options
March 21 Workshop - Determine 2025-2029 Highway Program Objectives

## Slide 44
Questions?