## Slide 1: 2023-2027 Highway Program Development
March 8, 2022

## Slide 2
Overview
  Discuss 2023-2027 available Highway Program funding
  Discuss 2023-2027 Highway Program Options
  Determine 2023-2027 Highway Program Objectives
  Action Item: Line Item Targets for Programming
March 8, 2022

## Slide 3
Commission Program Development Schedule (2023-2027)
  March 2022
  Discuss 2023-2027 available Highway Program funding
  Discuss 2023-2027 Highway Program Options
  Determine 2023-2027 Highway Program Objectives
  Action Item: Line Item Targets for Programming
  April 2022
  Develop the Draft 2023-2027 Highway Program
  Action Item: 2023-2027 Highway Program Objectives
  May 2022
  Present the Draft 2023-2027 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2023–2027 Highway Program)
  June 2022
  Action Item: Approve the 2023–2027 Iowa Transportation Improvement Program
March 8, 2022

## Slide 4: Decision Points
Should projects in the 2023-2026 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 8, 2022

## Slide 5: FY 22-27 Primary Road/TIME-21 Funds Forecast (x $1,000,000)
March 8, 2022

## Slide 6
2023-2027 Highway Program Funding Assumptions
RUTF/TIME-21
(For Highway Planning Purposes Only)
  Overall forecast is conservative based on unknown long-term impacts of COVID-19
  Forecast continues to reflect expected slowing of revenues from fees for new registration and reduced fuel tax revenue
  TIME-21 funding cap of $225 million has been met
  Average combined RUTF/TIME-21 growth of 0.6% annually
March 8, 2022

## Slide 7
2023 - 2027 Forecast of
Iowa Federal-Aid Formula Transportation Authorized Funds
(x $1,000)
(For Highway Planning Purposes Only)
Total Federal-Aid Formula Funds Forecast to DOT Programs
(x $1,000,000)
2023 - ($525.3 @ 90.0% Obligation Authority = $472.8) + (August Redistribution $15.0) = $487.8
2024 - ($534.6 @ 90.0% Obligation Authority = $481.1) + (August Redistribution $15.0) = $496.1
2025 - ($544.1 @ 90.0% Obligation Authority = $489.7) + (August Redistribution $15.0) = $504.7
2026 - ($553.8 @ 90.0% Obligation Authority = $498.4) + (August Redistribution $15.0) = $513.4
2027 - ($553.8 @ 90.0% Obligation Authority = $498.4) + (August Redistribution $15.0) = $513.4
March 8, 2022
 | 2023 | 2024 | 2025 | 2026 | 2027
National Highway Performance Program | $ 365,600 | $ 373,000 | $ 380,400 | $ 388,000 | $ 388,000
Surface Transportation Block Grant Program | $ 177,900 | $ 181,400 | $ 185,100 | $ 188,800 | $ 188,800
Highway Safety Improvement Program | $ 35,900 | $ 36,700 | $ 37,600 | $ 38,400 | $ 38,400
Rail-Highway Crossings Program | $ 5,700 | $ 5,700 | $ 5,700 | $ 5,700 | $ 5,700
Congestion Mitigation and Air Quality Program | $ 12,300 | $ 12,500 | $ 12,800 | $ 13,100 | $ 13,100
Metropolitan Planning | $ 2,700 | $ 2,700 | $ 2,800 | $ 2,800 | $ 2,800
National Highway Freight Program | $ 17,000 | $ 17,400 | $ 17,700 | $ 18,100 | $ 18,100
State Planning and Research | $ 12,400 | $ 12,700 | $ 13,000 | $ 13,200 | $ 13,200
Carbon Reduction Program | $ 16,200 | $ 16,500 | $ 16,800 | $ 17,200 | $ 17,200
PROTECT Formula Program | $ 18,400 | $ 18,800 | $ 19,100 | $ 19,500 | $ 19,500
Bridge Replacement Program | $ 86,300 | $ 86,300 | $ 86,300 | $ 86,300 | $ 86,300
 | $ 750,400 | $ 763,700 | $ 777,300 | $ 791,100 | $ 791,100
Iowa DOT Share (70%) | $ 525,280 | $ 534,590 | $ 544,110 | $ 553,770 | $ 553,770

## Slide 8
Federal Funding Status
Infrastructure Bill authorizes federal funding through September 30, 2026.
Still operating under a continuing resolution for FY 2022 through March 11, 2022
Infrastructure Bill funding allocations are yet to be determined with discussions underway leading to Commission action.
The next Highway Trust Fund cliff is in 2026/2027, leaving uncertainty in the last year of this next five-year program.
March 8, 2022

## Slide 9
  At what levels should the line item targets be programmed?
  March Action Item: Line Item Targets for Programming
March 8, 2022
as shown February 8, 2022
 | DRAFT 2023 - 2027 IOWA HIGHWAY PROGRAM |  |  |  |  |  |  | 
 |  |  |  | PROJECT ESTIMATED COSTS X $1000 |  |  |  | 
 | LOCATION | FUNDING | TYPE OF WORK | 2023 | 2024 | 2025 | 2026 | 2027
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
 | AMERICANS WITH DISABILITIES ACT |  | MISCELLANEOUS | 500 | 1000 | 1500 | 2000 | 2500
 | CONSTRUCTION INDUSTRY TRAINING PROGRAM |  | MISCELLANEOUS | 1000 | 1000 | 1000 | 1000 | 1000
 | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH |  | MISCELLANEOUS | 2000 | 2250 | 2500 | 2500 | 2500
 | EMERGENCY & CONTINGENCY - U-STEP/C-STEP |  | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
 | POST LETTING PROJECT COST |  | MISCELLANEOUS | 20000 | 20000 | 20000 | 20000 | 20000
 | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES |  | MISCELLANEOUS | 360 | 360 | 360 | 360 | 360
 | BYWAY PROGRAM |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | 85000 | 85000 | 85000 | 85000 | 85000
 | STATEWIDE CONSULTANT SERVICES |  | OUTSIDE SERV. ENGINEER | -9000 | -9000 | -9000 | -9000 | -9000
 | STATEWIDE OPERATIONS |  | OUTSIDE SERV. ENGINEER | 9000 | 9000 | 9000 | 9000 | 9000
 | STATEWIDE CONTRACT MAINTENANCE |  | MISCELLANEOUS | 36350 | 36850 | 37350 | 37850 | 38350
 | STATEWIDE RAILROAD CROSSINGS |  | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
 | STATEWIDE ROADSIDE IMPROVEMENT |  | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
 | STATEWIDE TRAFFIC CONTROL DEVICES |  | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000

## Slide 10
Estimated Income
A. Primary Road Fund (PRF) 726.3 21.0 732.5 20.6 737.0 21.0 743.3 21.6
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 372.7 115.1 372.7 123.4 372.7 132.0 372.7 140.7
Estimated Income Total 1259.0 136.1 1265.2 144.0 1269.7 153.0 1276.0 162.3
Allocations
E. Budget (PRF)
Operations/Maintenance 364.8 3.1 376.7 2.9 388.5 3.4 400.4 3.8
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 45.8 0.5 46.1 1.0 46.3 1.5 46.3 2.0
G. Statewide Consultant Services 85.0 -9.0 85.0 -9.0 85.0 -9.0 85.0 -9.0
H. Statewide Operations 0.0 9.0 0.0 9.0 0.0 9.0 0.0 9.0
I. Statewide Contract Maintenance 36.4 36.9 37.4 0.0 37.9 0.0
J. RR Crossing Protection 5.0 5.0 5.0 5.0
Allocations Total 537.0 3.6 549.7 3.9 562.2 4.9 574.6 5.8
Funds Available for ROW/Construction 722.0 132.5 715.5 140.1 707.5 148.1 701.4 156.5
2023 2023 2024 2024 2025 2025 2026 2026
(Mar ‘21) (Mar ‘22) (Mar ‘21) (Mar ‘22) (Mar ‘21) (Mar ‘22) (Mar ‘21) (Mar ’22)
change change change change
2023 - 2026 Highway Program Funding with Possible Changes
That Could Impact Funds Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 8, 2022

## Slide 11
Estimated Income
A. Primary Road Fund (PRF) 747.3 753.1 758.0 764.9 770.9
B. Est. TIME-21 Revenue to PRF 135.0 135.0 135.0 135.0 135.0
C. Miscellaneous (State) 25.0 25.0 25.0 25.0 25.0
D. Federal-Aid (Formula) 487.8 496.1 504.7 513.4 513.4
Estimated Income Total 1395.1 1409.2 1422.7 1438.3 1444.3
Allocations
E. Budget (PRF)
Operations/Maintenance 367.9 379.6 391.9 404.2 416.5
F. Emergency, Contingency, U-STEP,
C-STEP, Traffic Control Devices, Roadside
Improvements, Research, Byways, Others 46.3 47.1 47.8 48.3 48.8
G. Statewide Consultant Services 76.0 76.0 76.0 76.0 76.0
H. Statewide Operations 9.0 9.0 9.0 9.0 9.0
I. Statewide Contract Maintenance 36.4 36.9 37.4 37.9 38.4
J. RR Crossing Protection 5.0 5.0 5.0 5.0 5.0
Allocations Total 540.6 553.6 567.1 580.4 593.7
Funds Available for ROW/Construction 854.5 855.6 855.6 857.9 850.6
2023 2024 2025 2026 2027
2023 – 2027 Highway Program Funding
Available for ROW/Construction
For Highway Planning Purposes Only (x $1,000,000)
March 8, 2022

## Slide 12
Projected Funds as of March 2021 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Projected Funds 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 157.9 151.5 149.9 149.0 175.0 180.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
Safety Specific 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
Non-Interstate Capacity/System Enhancement 178.4 267.4 141.2 156.1
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
US 75 Plymouth: Hinton 6.1
Major Interstate Capacity/System Enhancement 90.0 80.2 177.2 117.2
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 20.7 24.8
Highway Program Balance (12.0) (71.2) (69.6) (50.2) 22.0 58.9 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 8, 2022, as presented February 8, 2022

## Slide 13
Projected Funds as of March 2022 854.5 855.6 855.6 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Program Balance (FY 21) Carryover 38.9
Federal FY 2021 Redistribution 40.3
Operations Budget Reversion (FY 21) 3.6
Additional FY 22 Federal Funds 38.9
FY 22 Program Balance (50.0)
Cash Flow Adjustment (75.0)
Local Jurisdiction Drawdown (35.0)
Projected Funds 816.2 855,6 855.6 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 157.9 151.5 149.9 149.0 175.0 180.0 185.0 190.0 195.0 200.0
Non-Interstate Pavement Modernization 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0 200.0
Non-Interstate Bridge Modernization 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0 200.0
Safety Specific 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0 40.0
Non-Interstate Capacity/System Enhancement 178.4 267.4 141.2 156.1
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
US 75 Plymouth: Hinton 6.1
Major Interstate Capacity/System Enhancement 90.0 80.2 177.2 117.2
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 20.7 24.8
Highway Program Balance 117.2 68.9 78.5 106.3 171.2 208.1 258.6 242.6 226.6 210.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 8, 2022
    Changes to Projected Funds

## Slide 14
Projected Funds as of March 2022 816.2 855.6 855.6 857.9 850.6 850.6 850.6 850.6 850.6 850.6
FY 2022 Projects Rescheduled 4.7 0.5
Projected Funds 820.9 855,6 856.1 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 157.9 151.5 149.9 149.0 175.0 180.0 185.0 190.0 195.0 200.0
Non-Interstate Pavement Modernization 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0 200.0
Non-Interstate Bridge Modernization 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0 200.0
Safety Specific 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0 40.0
Non-Interstate Capacity/System Enhancement 178.4 267.4 141.2 156.1
Non-Interstate Capacity/System Enhancement 2.3 0.5
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
US 75 Plymouth: Hinton 6.1
Major Interstate Capacity/System Enhancement 90.0 80.2 177.2 117.2
Major Interstate Capacity/System Enhancement 2.4
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 20.7 24.8
Highway Program Balance 117.2 68.9 78.5 106.3 171.2 208.1 258.6 242.6 226.6 210.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 8, 2022
    Changes to Projected Funds
    FY 2022 Projects Rescheduled

## Slide 15
Projected Funds 820.9 855.6 856.1 857.9 850.6 850.6 850.6 850.6 850.6 850.6
Highway Program Components
Interstate Stewardship 157.9 151.5 149.9 149.0 175.0 180.0 185.0 190.0 195.0 200.0
Interstate Stewardship 8.4 (14.8) 43.7 73.3 0.0
Non-Interstate Pavement Modernization 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0 200.0
Non-Interstate Pavement Modernization (0.5)
Non-Interstate Bridge Modernization 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0 200.0
Non-Interstate Bridge Modernization 0.1 (1.5) 19.8 0.7 0.0
Safety Specific 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0 40.0
Safety Specific 0.0
Non-Interstate Capacity/System Enhancement 178.4 267.4 141.2 156.1 77.5
Non-Interstate Capacity/System Enhancement 43.6 33.1 (30.2) 62.8 (52.6)
US 61 Des Moines N of Mediapolis to N of IA 78
US 30 Missouri Valley bypass 32.9
US 61 1 mi N of IA 78 to 2 mi S of IA 92 45.7
US 63 NW Oskaloosa bypass
US 75 Plymouth: Hinton
Major Interstate Capacity/System Enhancement 90.0 80.2 177.2 117.2 71.9
Major Interstate Capacity/System Enhancement 26.0 13.1 (57.2) 56.3 4.5
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 24.7 39.0 1.0
I-80 Johnson IA1 to Co Rd X30 0.5
Highway Program Balance 44.2 39.0 102.9 (86.8) 219.3 122.0 257.6 242.6 226.6 210.6
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 8, 2022
    Changes to Projected Funds
    FY 2022 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2023 to 2026, add 2027
Should projects in the 2023-2026 program continue to be programmed with cost/schedule updates?

## Slide 16: 2023-2027 Highway Program Analysis (with updated revenue, FY 2022 projects rescheduled, project cost updates and schedule updates)
Chart: 
| 2023 | 2024 | 2025 | 2026 | 2027
Interstate Stewardship | 166.3 | 136.7 | 193.6 | 222.3 | 175
Major Interstate | 116 | 93.3 | 120 | 173.5 | 76.4
Non-Interstate Pavement Modernization | 139.5 | 145 | 150 | 155 | 165
Non-Interstate Bridge Modernization | 101.8 | 109.1 | 145.6 | 141 | 155
Non-Interstate Capacity/Enhancement | 222 | 300.5 | 111 | 218.9 | 24.9
Safety | 31 | 32 | 33 | 34 | 35
Projected Revenue

## Slide 17
Highway Program Components
Interstate Stewardship 166.3 136.7 193.6 222.3 175.0 180.0 185.0 190.0 195.0 200.0
- Funds in years 2028 and beyond are placeholders (not programmed yet)
- Projects in 2023-2027 are specifically identified in the highway program
- Major projects continuing in the current program include:
Fremont I-29 recommend adding resiliency work in 2023
Dallas I-80 from US 6/169 to Co Rd R16 reconstruction in 2023-2024
Johnson I-80/380/US 218 Interchange reconstruction in 2023
Johnson I-80 1st Ave Interchange reconstruction in Coralville begins in 2023
Linn I-380 Boyson Rd Interchange reconstruction in Hiawatha in 2025
Polk I-80 from Northeast mixmaster to US 65 in 2025-2026
Polk I-35/80 Hickman interchange reconstruction beginning in 2025
Polk I-35/80/235 Northeast mixmaster improvements in 2023-2024
Warren SB I-35 from N of IA 92 to S of North River in 2023
Warren NB I-35 from S of Co Rd G14 to N of Adams Street reconstruction in 2026
Warren NB I-35 from Clarke County to Clanton Creek paving in 2026-2027
Warren NB I-35 from N or North River to S of Badger Creek in 2026
Woodbury I-29/IA 141 Interchange reconstruction begins in 2024
- Rest area projects:
Adair WB I-80 pavement replacement in 2023 is recommended to be programmed
Iowa EB I-80 truck parking expansion in 2023 is currently programmed (+13 spots)
Linn SB I-380 in 2023 is currently programmed with truck parking expansion in 2024 (+14 spots)
Woodbury NB I-29 recommend removing Sergeant Bluff rest area in 2024 (-14 spots)
Harrison NB I-29 recommend removing parking only spot at Mondamin in 2025 (-5 spots)
Iowa WB I-80 replace building and add truck parking in 2025 (+16 spots)
Polk EB I-80 recommend moving building replacement from 2026 to 2028 (next Program) but add truck parking in 2026 (+11 spots)
Polk WB I-80 recommend adding truck parking in 2026 (+13 spots)
Harrison NB I-19 recommend removing rest area in 2026 (-13 spots)
Pottawattamie WB I-80 replace building is recommended to move from 2025 to 2026
Cedar WB I-80 recommend truck parking expansion in 2027 (+22 spots)
Harrison SB I-29 recommend removing rest area in 2027 (-13 spots)
Monona SB I-29 recommend replace building in 2027
Pottawattamie WB I-80 recommend truck parking expansion in 2027 (+9 spots)
Story SB I-35 recommend removing overlook
- Weigh station ramp/parking improvements with one site per year
- Recommend removing I-235 ramp metering
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 8, 2022

## Slide 18
Highway Program Components
Non-Interstate Pavement Modernization 139.5 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0 200.0
- Funds in Years 2024 and beyond are placeholders (no specific projects identified)
- Projects in 2023 will be specifically identified in the highway program (to be handed
out in April)
Non-Interstate Bridge Modernization 101.8 109.1 145.6 141.0 155.0 170.0 185.0 190.0 195.0 200.0
- Funds in years 2028 and beyond are placeholders (not programmed yet)
- Projects in 2023-2027 will be specifically identified in the highway program (to be handed
out in April)
Safety Specific 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0 40.0
- Funds in Years 2024 and beyond are mostly placeholders (a few specific projects identified)
- Projects in 2023 will be specifically identified in the highway program (to be handed out in April)
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 8, 2022

## Slide 19
Highway Program Components
Non-Interstate Capacity/System
Enhancement 222.0 300.5 111.0 218.9 24.9 78.6
- Funds in Years 2028 and beyond are project completion costs for projects already in Program
- Missouri Valley Bypass delayed one year (ROW moves from 2024 to 2025 with corresponding changes in construction schedule))
Major Interstate Capacity/System
Enhancement 116.0 93.3 120.0 173.5 76.4 89.0 1.0
- Funds in years 2028 and beyond are project completion costs for projects already in Program
- Scott I-80 Mississippi River Bridge is still scheduled to begin in 2026.
Proposed Highway Program Extended Highway Program
2023 2024 2025 2026 2027 2028 2029 2030 2031 2032
2023-2032 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 8, 2022

## Slide 20
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
6 | Pottawattamie | 6th St in Council Bluffs to I-80 (Broadway Avenue) | Operational & Safety | Construct Intersection Improvements (TJ to city) | Y | Complete | $10 M
6 | Scott | Kimberly Rd in Davenport from N Brady St to Elmore Ave | Operational & Safety | Construct Intersection Improvements | Y | -- | 
12 | Woodbury | Gordon Dr Viaduct in Sioux City | Structurally Deficient | Replace Bridge | Y | Active | $90 M
18 | Clay/Palo Alto/ Kossuth/Hancock | Spencer to Garner | Mobility & Safety | Modernize 2-Lane | Y | Active | 
20 | Dubuque | W of Old Highway Rd to Devon Drive in Dubuque | Operational & Safety | Access control | Y | -- | 
20 | Dubuque | Intersection with NW Art | Operational & Safety | Construct Intersection Improvements | Y | Active | 
20 | Dubuque | Mississippi River Bridge | Functionally Obsolete | Add 2nd Bridge | Y | Complete | $100 M
30 | Carroll/Greene/ Boone | Co Rd N33 to E Jct US 169 | 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | -- | $265 M $130 M
30 | Story | Intersections in Nevada | Operational & Safety | Construct Interchanges | NA | Complete | $25 M
30 | Tama | Intersection At Meskwaki Casino | Operational & Safety | Construct Interchange | NA | -- | 
30 | Cedar | Lisbon bypass to Stanwood | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Complete | $100 M $50 M
30 | Clinton | Calamus to US 61 | Provide 4-Lane Continuity or Mobility | Construct 4-Lane or Modernize 2-Lane | N Y | Complete | $75 M $40 M
34 | Mills/Montgomery/ Adams | E of Glenwood to E of Creston | Mobility & Safety | Modernize 2-Lane | Y | Begin FY 23 | 
March 8, 2022

## Slide 21
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
34 | Union/ Clarke/Lucas/ Monroe/Wapello | E of Creston to W of Ottumwa | Mobility & Safety | Modernize 2-Lane | Y | Begin in FY 22 | 
35 | Story | N of IA 210 to E 13th St in Ames | Add Capacity | Construct 6-Lane | Y | Complete | $120 M
35/80 | Polk | I-235 Interchange SW of Des Moines | Add Capacity and Improve Operations | Reconstruct Interchange, Add Lanes | Y | Active | $300 M
35/80/235 | Polk | SW to NE Mixmasters | Add Capacity and Improve Operations | Add Lanes, Modernize, and/or ICM strategies | Y | Active | Phase I - $90 M
58 | Black Hawk | Greenhill Road in Cedar Falls | Operational & Safety | Construct Interchange | Y | Complete | $32 M
63 | Davis/Wapello | Bloomfield to Ottumwa | Provide 4-Lane Continuity Mobility and Safety | Construct 4-Lane or Modernize 2-Lane | N Y | -- Begin FY 23 | 
63 | Mahaska/ Poweshiek | N of Oskaloosa to I-80 | Operational | Modernize 2-Lane | Y | -- | 
63 | Poweshiek/Tama/ Black Hawk | W Jct US 6 to Hudson | Mobility and Safety | Modernize 2-Lane | Y | Active | 
65/69 | Warren | Hillcrest Ave in Indianola to IA 5 | Operational & Safety | Improve Intersections | NA | -- | 
69 | Polk | Army Post Road to I-80 | Operational & Safety |  | Y | Active | 
67 | Scott | Mississippi River Bridge | Structurally Deficient | Replace Bridge (IL Lead) | Y | -- | $110 M
74 | Scott | North of Lincoln Road in Bettendorf to I-80 in Davenport | Add Capacity | Construct 6-Lane | N | Complete | $150 M
75 | Plymouth | In Hinton | Operational & Safety | Modernize 4-Lane | NA | Begin in FY 22 | 
March 8, 2022

## Slide 22
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
75 | Plymouth/Sioux | IA 60 in Le Mars to IA 10 | Operational | Modernize 2-Lane | Y | -- | 
80 | Dallas/Polk | Co Rd R16 to Jordan Creek | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Polk/Jasper/ Poweshiek/Iowa | Altoona to I-380 | Add Capacity | Construct 6-Lane | Y | Active | 
80 | Cedar | West Branch to Cedar River | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Cedar/Scott | County Road Y26 to W of I-280 | Add Capacity | Construct 6-Lane | Y | -- | 
80 | Scott | W of I-280 to W of I-74 | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of I-74 to W of Middle Rd in Bettendorf | Capacity & Operations | Construct 6-Lane | Y | Active | 
80 | Scott | W of Middle Rd in Bettendorf to Mississippi River Bridge | Capacity & Operations | Replace Interchange (Bi-State req. 06/10/08) | NA | Active | 
80 | Scott | Mississippi River Bridge in Le Claire | Add Capacity | Replace with Wider Bridge (IL Lead) | Y | Active | $150 M
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 8, 2022

## Slide 23
Highway Program Studies/Requests
Route | County | Location | Purpose | Description | Consistent w/ SLRTP | Planning Status | Approx Cost
92 | Mahaska | SE Oskaloosa Bypass | Operational | Construct 2-Lane Bypass | Y | Inactive | 
100 | Linn | Collins Rd in Cedar Rapids from W of Council St to 1st Ave | Add Capacity | Construct 6-Lane (Local Lead) | Y | Active | 
122 | Cerro Gordo | West side of Mason City | Operational | Convert to urban section |  | Begin in FY 22 (local led) | 
150 | Benton/ Buchanan/ Fayette/ Winneshiek | I-380 to N of Oelwein | Mobility & Safety | Modernize 2-Lane | Y | Begin in FY 22 | 
150/52 | Fayette/ Winneshiek | N of Oelwein to Minnesota State Line | Mobility & Safety | Modernize 2-Lane | Y | -- | 
151 | Linn | Co Rd X20 Intersection in Springville | Operational & Safety | Construct Interchange | NA | Active | $23 M
380 | Johnson/Linn | Forevergreen Rd to S of US 30 | Add Capacity | Construct 6-Lane | Y | Complete | $224 M
380 | Linn | S of US 30 to N of US 30 | Operational | Reconstruct interchange | Y | Proposed FY 22 | 
380 | Linn | S of US 30 to Blairs Ferry Road | Add Capacity | Construct 6-Lane | Y | -- | 
380 | Linn | Blairs Ferry Rd to County Home Rd | Add Capacity | Construct 6-Lane | N | Complete | $27.2 M
380 | Linn | I-380 through Cedar Rapids | Operational | ICM strategies | Y | Proposed FY 22 | 
Legend:
SLRTP is State Long Range Transportation Plan
Inactive means no planning study work has been done, or previous work is currently obsolete
Active means planning study work is in progress
Complete means planning study work is completed and the project could start development
NA means not addressed
March 8, 2022

## Slide 24
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Beyond | Total | Score | Rank
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  | 4.9 | 30.7 | 39.3 | 67.6 | 1.2 |  | 143.7 | 38 | 4
I35/80/235 Polk: Southwest Mixmaster |  |  |  |  | 36.1 | 86.4 | 13.0 |  |  |  | 135.5 | 34 | 1
I-80 Scott: Middle Road Interchange (4R or MI) |  |  | 45.8 |  |  |  |  |  |  |  | 45.8 | 55 | 7
I-80 Pottawattamie: Madison Avenue (advancement candidate) | 60.4 | 45.6 | (37.8) | (22.7) | (20.7) | (24.8) |  |  |  |  |  | 37 | 2
I-380 Johnson: Segment 2 Swan Lake Rd to 120th St |  |  |  |  |  |  | 40.0 | 46.1 | 27.0 |  | 113.1 | 48 | 6
I-380 Linn: Segment 3 120th St NW to US 30 (Wright Brothers Blvd Interchange) |  |  | 99.5 |  |  |  |  |  |  |  | 99.5 | 37 | 2
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  |  | 15.4 | 32.5 |  | 47.9 | 45 | 5
Stewardship (Shelf-Ready) Projects | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  |  | 500.0 |  | 
    Subject to change as additional information becomes available
March 8, 2022

## Slide 25
 |  |  |  |  |  |  |  |  |  | Score
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  | 18.9 |  | TBD | TBD |  |  | 33 | 1
IA 21 Benton/Iowa: South of Belle Plaine resiliency |  |  |  |  |  |  |  |  | 82 | 8
US 34 Wapello: Wildwood Dr to W Jct US 63 in Ottumwa |  |  |  | 32.1 |  |  |  |  | 36 | 2
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  | 47 | 4
US 75 Sioux: N of Sioux Center to S Jct US 18 |  |  | 11.1 |  |  |  |  |  | 70 | 6
Iowa 100 Linn: Council St to Northland Ave in Cedar Rapids |  |  |  |  |  |  |  |  | 47 | 4
IA 149: Des Moines River Bridge to Woodland Ave in Ottumwa |  |  | 5.9 |  |  |  |  |  | 39 | 3
IA 333: Hamburg resiliency | 2.0 |  |  |  |  |  |  |  | 73 | 7
Polk: Iowa Traffic Training Center – Phase 1 | 10.0 |  |  |  |  |  |  |  | N/A | 
Culverts/Slide Repairs (multiple locations statewide) | 2.9 | 0.5 | 0.6 | 0.5 | 0.5 |  |  |  | N/A | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 8, 2022

## Slide 26
 |  |  |  |  |  |  |  |  | Priority |  | Score
 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Beyond | Corridor | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 30 Tama: Meskwaki Interchange |  |  |  |  |  |  |  |  | N | 67 | 3
US 30 Story: 610th Ave Interchange (Nevada) |  |  |  |  |  |  |  |  | N | 74 | 5
US 30 Cedar: WCL Stanwood to ECL Clarence (Super-2) |  |  |  |  |  | 11.5 |  |  | Y | 70 | 4
US 63 Tama: NCL Traer to Hudson (Super-2) |  |  |  |  | 7.1 |  |  |  | N | 75 | 6
IA 58 Black Hawk: Greenhill Road Interchange |  |  |  | 32.1 |  |  |  |  | N | 53 | 1
US 151 Linn: Co Rd X-20 Interchange at Springville |  |  |  |  | 24.0 |  |  |  | N | 53 | 1
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 | 7.0 | 5.0 | 5.0 |  |  |  |  |  | N | N/A | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 8, 2022

## Slide 27: Decision Points
Should projects in the 2023-2026 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
  What additional information is desired (more detailed project discussion?)
  Consider opportunities to increase stewardship levels beyond already scheduled increases? (i.e., pavement, bridge, safety)
  Consider advancing I-80/Madison Avenue to reassess balances with that move?
  Come back with some scenarios for March 24?
March 8, 2022

## Slide 28
March 8, 2022, as presented
April 12, 2021
  Projects in the 2022-2025 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing funding levels for safety
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
FY 2022-2026 Highway Program Objectives

## Slide 29
March 8, 2022
  Projects in the 2022-2026 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing funding levels for safety
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
    Invest in operational and Integrated Corridor Management improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
Potential FY 2023-2027 Highway Program Objectives

## Slide 30: Next Steps
March Business Meeting
Action Item: Line Item Targets for Programming
Next March Workshop
Discuss 2023-2027 Highway Program Options
Determine 2023-2027 Highway Program Objectives
April
Develop the Draft 2023-2027 Highway Program
Action Item: 2023-2027 Highway Program Objectives
March 8, 2022