## Slide 1: 2022-2026 Highway Program Development
March 25, 2021

## Slide 2
Overview
  Discuss 2022-2026 available Highway Program funding
  Discuss 2022-2026 Highway Program Options
  Determine 2022-2026 Highway Program Objectives
March 25, 2021

## Slide 3
Commission Program Development Schedule (2022-2026)
  March 25, 2021
  Discuss 2022-2026 available Highway Program funding
  Discuss 2022-2026 Highway Program Options
  Determine 2022-2026 Highway Program Objectives
  April 2021
  Develop the Draft 2022-2026 Highway Program
  Action Item: 2022-2026 Highway Program Objectives
  May 2021
  Present the Draft 2022-2026 Iowa Transportation Improvement Program to the public
  (including all previous program approvals and draft 2022–2026 Highway Program)
  June 2021
  Action Item: Approve the 2022–2026 Iowa Transportation Improvement Program
March 25, 2021

## Slide 4: Decision Points
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 25, 2021

## Slide 5
Projected Funds as of March 2021 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 183.2 146.2 152.8 177.3 170.0 175.0 180.0 185.0 190.0 195.0
Interstate Stewardship 14.4 15.9 (9.3) (25.6) (21.0)
Non-Interstate Pavement Modernization 115.0 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 2.7
Non-Interstate Bridge Modernization 65.0 101.3 109.5 125.9 140.0 155.0 170.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization (0.5) 0.4 1.1 (0.1) 0.3
Safety Specific 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0 25.0
Safety Specific 1.9
Safety Specific (target increase) 5.0 6.0 7.0 8.0 9.0 10.0 11.0 12.0 13.0 14.0
Non-Interstate Capacity/System Enhancement 149.4 226.7 217.6 102.1 109.6
Non-Interstate Capacity/System Enhancement (15.7) (36.2) 48.7 26.9 30.3
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 30 ECL Lisbon to ECL Mechanicsville
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
Major Interstate Capacity/System Enhancement 227.8 111.8 68.9 125.4 52.2
Major Interstate Capacity/System Enhancement 60.2 (21.8) 1.6 (15.8) 24.3
I-35 Polk/Story 1.2
I-80 Dallas
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (78.7) (28.3) (52.4) 8.4 6.7 48.8 83.7 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 25, 2021
as presented March 9, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2022 to 2025, add 2026
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?

## Slide 6
Projected Funds as of March 2021 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 197.6 162.1 143.5 151.7 149.0 175.0 180.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 117.7 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 64.5 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
Safety Specific 31.9 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
Non-Interstate Capacity/System Enhancement 133.7 190.5 266.3 129.0 139.9
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
Major Interstate Capacity/System Enhancement 288.0 90.0 70.5 109.6 76.5
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
Highway Program Balance (78.7) (28.3) (52.4) 8.4 6.7 48.8 83.7 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 25, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2022 to 2025, add 2026
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?

## Slide 7
Highway Program Components
Interstate Stewardship 197.6 162.1 143.5 151.7 149.0 175.0 180.0 185.0 190.0 195.0
- Funds in years 2027 and beyond are placeholders (not programmed yet)
- Projects in 2022-2026 are specifically identified in the highway program
- Identified projects are 33% roadway reconstruction, 20% pavement resurfacing and maintenance, 26% bridge replacements,
7% bridge repairs or overlays, 6% rest area improvements and maintenance, 8% other (traffic signs, erosion control, lighting, etc.)
- Major projects continuing in the current program include:
Dallas I-80 from US 6/169 to Co Rd R16 reconstruction in 2022-2024
Johnson I-80/380/US 218 Interchange reconstruction in 2022-2023
Johnson I-80 1st Ave Interchange reconstruction in Coralville recommended to move from 2024 to 2023 to align with BUILD Grant timeline
Linn I-380 Boyson Rd Interchange reconstruction in Hiawatha in 2025
Polk I-80 from Northeast mixmaster to US 65 recommend to move from beginning in 2024 to beginning 2025
Polk I-35/80 Hickman interchange reconstruction beginning in 2025
Polk I-35/80/235 Northeast mixmaster improvements in 2023-2024
Poweshiek I-80/IA 146 Interchange reconstruction at Grinnell in 2022
Warren NB I-35 from S of Co Rd G14 to N of Adams Street reconstruction recommend to move from 2025 to 2026
Warren NB I-35 from Clarke County to Clanton Creek paving recommend to move from 2025 to 2026
Woodbury I-29/IA 141 Interchange reconstruction recommend to move from 2023 to 2024
- There are four rest area building replacements:
Iowa EB I-80 in 2022 is currently programmed
Iowa EB I-80 truck parking expansion is recommended to move from 2023 to 2024
Linn SB I-380 in 2023 is currently programmed
Mills NB I-29 in 2021 is currently programmed
Polk EB I-80 in 2026 is recommended to be programmed
Pottawattamie WB I-80 in 2025 is currently programmed
- Recommend adding weigh station ramp/parking improvements with one site per year
- Recommend adding I-235 ramp metering in 2023
- Major projects for consideration to add to the program this year include:
Warren NB I-35 from N or North River to S of Badger Creek in 2026
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 25, 2021
as presented March 9, 2021

## Slide 8
Highway Program Components
Non-Interstate Pavement Modernization 117.7 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
- Funds in Years 2023 and beyond are placeholders (no specific projects identified)
- Projects in 2022 will be specifically identified in the highway program (to be handed
out in April)
- 2022 draft projects are 96% pavement resurfacing, 3% pavement widening, and 1% other
Non-Interstate Bridge Modernization 64.5 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
- Funds in years 2027 and beyond are placeholders (not programmed yet)
- Projects in 2022-2026 will be specifically identified in the highway program (to be handed
out in April)
- Draft projects are 65% bridge replacements, 33% bridge repairs or overlays, 2% culvert repairs
or replacements, 1% other
Safety Specific 31.9 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
- Funds in Years 2023 and beyond are mostly placeholders (few specific projects identified)
- Recommend increasing safety target by $5 million in FY 2022 and increasing $1 million per year
- Projects in 2022 will be specifically identified in the highway program (to be handed out in April)
- 2022 draft projects are 78% shoulder paving and widening, 10% interstate median guardrail,
12% other
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 25, 2021
as presented March 9, 2021

## Slide 9
Highway Program Components
Non-Interstate Capacity/System
Enhancement 133.7 190.5 266.3 129.0 139.9 71.4 6.7
- Funds in Years 2027 and beyond are project completion costs for projects already in Program
- Dubuque Iowa 3 reconstruction delayed from 2021 to 2022
Major Interstate Capacity/System
Enhancement 288.0 90.0 70.5 109.6 76.5 51.2 50.0
- Funds in years 2027 and beyond are project completion costs for projects already in Program
- Johnson I-80 from East of Iowa 1 to E of Co Rd X30 schedule adjusted due to delayed letting and
concept modification
- Scott I-80 Mississippi River Bridge moved to begin in 2026 from 2025 due to development schedule
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
March 25, 2021
as presented March 9, 2021

## Slide 10
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond | 
Interstate Stewardship |  |  |  |  |  |  |  | 
I-80 Polk University Ave to North of Douglas |  |  |  | 1.8 |  |  |  | 
I-80 Polk University Ave to North of Douglas (advance ROW) |  |  | 1.8 |  |  |  |  | 
I-235 Polk Ramp Metering (not currently in the program) |  | 5.2 |  |  |  |  |  | 
I-235 Polk Ramp Metering |  |  | 5.2 |  |  |  |  | 
I-80 Western Iowa ITS | 1.5 | 1.0 | 1.0 |  |  |  |  | 
Major Interstate Capacity/System Enhancement |  |  |  |  |  |  |  | 
CBIS: I-80 and Madison Avenue | 115.9 |  |  |  |  |  |  | 
CBIS: I-80 and Madison Avenue | 5.0 |  |  | 37.8 | 22.7 | 20.7 | 24.8 | 
I-380 Johnson: N of Forevergreen Rd to N of Penn St |  |  | 9.7 | 29.8 | 18.0 |  |  | 
Project Reschedule/Addition Scenario
For Highway Planning Purposes Only (x $1,000,000)
March 25, 2021

## Slide 11
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond | 
Non-Interstate Capacity/System Enhancement |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  | 
US 71 Dickinson Okoboji Rd in Arnolds Park to East View Ave | 5.3 | 12.9 |  |  |  |  |  | 
US 71 Dickinson Okoboji Rd in Arnolds Park to East View Ave | 12.9 |  |  |  |  |  |  | 
Iowa 2 Fremont: Resiliency improvements (Phase II) | 3.6 |  |  |  |  |  |  | 
Iowa 3 Cherokee: 1.3 miles E of US 59 to 1.8 miles E of US 59 |  |  |  |  | 4.4 |  |  | 
Iowa 7 Buena Vista: IA 110 Intersection in Storm Lake | 0.9 |  |  |  |  |  |  | 
US 75 Plymouth: Hinton |  |  |  |  | 3.5 | 6.1 |  | 
Iowa 76 Clayton: McGregor | 4.8 |  |  |  |  |  |  | 
US 20 Black Hawk: Iowa 21 to E Jct I-380 Interchange (ITS) |  |  |  |  | 1.7 |  |  | 
Culverts/Slide Repairs (multiple locations statewide) | 2.9 | 0.8 | 1.0 | 0.2 |  |  |  | 
Capacity |  |  |  |  |  |  |  | 
US 30 Cedar: ECL Lisbon to WCL Mechanicsville |  |  |  |  | 3.5 |  |  | 
US 30 Cedar: ECL Lisbon to WCL Mechanicsville |  |  |  | 3.5 |  |  |  | 
US 18 Kossuth/Hancock: 1.65 miles East of Co Rd P64 to Hutchins (Super-2) | 4.8 |  |  |  |  |  |  | 
US 30 Cedar: WCL Mechanicsville to WCL Stanwood (Super-2) |  |  |  | 0.4 | 10.1 |  |  | 
US 63 Tama: Toledo to Co Rd E29 (Super-2) |  |  | 0.1 | 8.1 |  |  |  | 
Non-Interstate Pavement Modernization |  |  |  |  |  |  |  | 
Stewardship | 30.0 |  |  |  |  |  |  | 
Project Reschedule/Addition Scenario
For Highway Planning Purposes Only (x $1,000,000)
March 25, 2021

## Slide 12
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Beyond | Total | Score | Rank
Major Interstate Capacity/System Enhancement (MI funds) |  |  |  |  |  |  |  |  |  |  |  |  | 
I-35 Story: N of IA 210 to E 13th St in Ames |  |  |  |  |  | 4.9 | 30.7 | 39.3 | 67.6 | 1.2 | 143.7 | 45 | 3
I-80 Scott: Middle Road Interchange (4R or MI) |  |  |  |  |  |  |  |  |  |  |  | 52 | 5
I-380 Johnson: Segment 1 N of Forevergreen Rd to N of Penn St |  |  | 9.7 | 29.8 | 18.0 |  |  |  |  |  | 29.8 | 46 | 4
I-380 Johnson: Segment 2 N of Penn St to N of Iowa River |  |  |  |  |  |  |  | 40.0 | 46.1 | 27.0 | 113.1 | 43 | 2
I-380 Johnson: Segment 3 N of Iowa River to N of 120th St NW |  |  |  |  |  |  | 17.8 | 10.2 |  |  | 28.0 | 46 | 4
I-380 Linn: Segment 4 N of 120th St NW to US 30 |  |  |  |  |  | 33.5 | 19.2 |  |  |  | 52.7 | 38 | 1
I-380 Linn: Blairs Ferry Road to County Home Road (add lanes) |  |  |  |  |  |  |  |  | 15.4 | 32.5 | 47.9 | 54 | 6
Stewardship (Shelf-Ready) Projects | 100.0 | 100.0 | 100.0 | 100.0 | 100.0 |  |  |  |  |  | 500.0 |  | 
    Subject to change as additional information becomes available
March 25, 2021

## Slide 13
 |  |  |  |  |  |  |  |  |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | Beyond |  | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  | 
Stewardship |  |  |  |  |  |  |  |  |  | 
IA 2 Fremont: Resiliency improvements (Phase II) | 3.6 |  |  |  |  |  |  |  | 63 | 5
IA 3 Cherokee: 1.3 miles E of US 59 to 1.8 miles E of US 59 |  |  |  |  | 4.4 |  |  |  | 72 | 9
IA 7 Buena Vista: IA 110 Intersection in Storm Lake | 0.9 |  |  |  |  |  |  |  | 69 | 7
IA 12 Woodbury: Gordon Drive bridge in Sioux City |  |  |  | 18.9 | TBD | TBD |  |  | 40 | 1
US 34 Wapello: Wildwood Dr to W Jct US 63 in Ottumwa |  |  |  |  | 32.1 |  |  |  | 41 | 2
US 67 Scott: Mississippi River Bridge |  |  |  |  |  |  | 110.0 |  | 45 | 3
US 75 Sioux: N of Sioux Center to S Jct US 18 |  |  |  | 11.1 |  |  |  |  | 71 | 8
US 75 Plymouth: Hinton |  |  |  |  | 3.5 | 6.1 |  |  | 71 | 8
IA 76 Clayton: McGregor | 4.8 |  |  |  |  |  |  |  | 65 | 6
IA 149: Des Moines River Bridge to Woodland Ave in Ottumwa |  |  |  | 5.9 |  |  |  |  | 55 | 4
Polk: Traffic Incident Management (TIM) Training Center |  |  | TBD | TBD |  |  |  |  |  | 
US 20 Black Hawk: Iowa 21 to E Jct I-380 Interchange (ITS) |  |  |  |  | 1.7 |  |  |  |  | 
Culverts/Slide Repairs (multiple locations statewide) | 2.9 | 0.8 | 1.0 | 0.2 |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 25, 2021

## Slide 14
 |  |  |  |  |  |  |  |  | Priority |  | Score
 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Beyond | Corridor | Score | Rank
Non-Interstate Capacity/System Enhancement (NR funds) |  |  |  |  |  |  |  |  |  |  | 
Capacity |  |  |  |  |  |  |  |  |  |  | 
US 18 Kossuth/Hancock: 1.65 miles East of Co Rd P64 to Hutchins (Super-2) | 4.8 |  |  |  |  |  |  |  | N | 75 | 4
US 30 Cedar: WCL Mechanicsville to WCL Stanwood (Super-2) |  |  |  | 0.4 | 10.1 |  |  |  | Y | 70 | 3
US 30 Cedar: WCL Stanwood to ECL Clarence (Super-2) |  |  |  |  |  | 11.5 |  |  | Y | 70 | 3
US 63 Tama: Toledo to Co Rd E29 (Super-2) |  |  | 0.1 | 8.1 |  |  |  |  | N | 80 | 5
US 63 Tama: NCL Traer to Hudson (Super-2) |  |  |  |  | 7.1 |  |  |  | N | 75 | 4
US 151 Linn: Co Rd X-20 Interchange at Springville |  |  |  |  | 24.0 |  |  |  | N | 57 | 1
IA 58: Greenhill Road Interchange |  |  |  |  | 32.1 |  |  |  | N | 59 | 2
Potential Transfer of Jurisdictions (NR funds) |  |  |  |  |  |  |  |  |  |  | 
US 6 Pottawattamie: 6th St in Council Bluffs east to I-80 |  | 17.0 |  |  |  |  |  |  |  |  | 
IA 81 Van Buren: Missouri State Line to IA 2 | TBD |  |  |  |  |  |  |  |  |  | 
Highway Program Candidates
For Highway Planning Purposes Only (x $1,000,000)
    Subject to change as additional information becomes available
March 25, 2021

## Slide 15
Projected Funds as of March 2021 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 197.6 162.1 143.5 151.7 149.0 175.0 180.0 185.0 190.0 195.0
Interstate Stewardship 1.5 (4.2) 8.0 (1.8)
Non-Interstate Pavement Modernization 117.7 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 30.0
Non-Interstate Bridge Modernization 64.5 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
Safety Specific 31.9 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
Non-Interstate Capacity/System Enhancement 133.7 190.5 266.3 129.0 139.9
Non-Interstate Capacity/System Enhancement 24.6 (12.1) 1.1 12.2 16.2
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
US 75 Plymouth: Hinton 6.1
Major Interstate Capacity/System Enhancement 288.0 90.0 70.5 109.6 76.5
Major Interstate Capacity/System Enhancement (110.9) 9.7 67.6 40.7
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 20.7 24.8
Highway Program Balance (23.9) (12.0) (71.2) (69.6) (50.2) 22.0 58.9 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 25, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2022 to 2025, add 2026
    Added highlighted projects
    Additional project schedule changes
How should the Program be balanced and what projects should be added to the Program?

## Slide 16
Projected Funds as of March 2021 754.7 687.0 715.5 707.5 701.4 701.4 701.4 701.4 701.4 701.4
Highway Program Components
Interstate Stewardship 199.1 157.9 151.5 149.9 149.0 175.0 180.0 185.0 190.0 195.0
Non-Interstate Pavement Modernization 147.7 140.0 145.0 150.0 155.0 165.0 175.0 185.0 190.0 195.0
Non-Interstate Bridge Modernization 64.5 101.7 110.6 125.8 140.3 155.0 170.0 185.0 190.0 195.0
Safety Specific 31.9 31.0 32.0 33.0 34.0 35.0 36.0 37.0 38.0 39.0
Non-Interstate Capacity/System Enhancement 158.3 178.4 267.4 141.2 156.1
US 61 Des Moines N of Mediapolis to N of IA 78 0.4
US 30 Missouri Valley bypass 21.6 6.7
US 61 1 mi N of IA 78 to 2 mi S of IA 92 49.2
US 63 NW Oskaloosa bypass 0.2
US 75 Plymouth: Hinton 6.1
Major Interstate Capacity/System Enhancement 177.1 90.0 80.2 177.2 117.2
I-35 Polk/Story 1.2
I-80 Scott Mississippi River Bridge 50.0 50.0
I-80 Pottawattamie Madison Avenue 20.7 24.8
Highway Program Balance (23.9) (12.0) (71.2) (69.6) (50.2) 22.0 58.9 109.4 93.4 77.4
Proposed Highway Program Extended Highway Program
2022 2023 2024 2025 2026 2027 2028 2029 2030 2031
2022-2031 Highway Program Analysis
For Highway Planning Purposes Only (x $1,000,000)
    Black: Previous discussion
    ( ): Indicates Highway Program is over-programmed
    Green: Changes since previous discussion
March 25, 2021
    Changes to Projected Funds
    FY 2021 Projects Rescheduled
    Rescheduling and cost changes of projects programmed in years 2022 to 2025, add 2026
    Added highlighted projects
    Additional project schedule changes
How should the Program be balanced and what projects should be added to the Program?

## Slide 17: Decision Points
Should projects in the 2022-2025 program continue to be programmed with cost/schedule updates?
How should the Program be balanced and what projects should be added to the Program?
March 25, 2021

## Slide 18
  Projects in the 2021-2024 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
FY 2021-2025 Highway Program Objectives
March 25, 2021
as approved April 14, 2020

## Slide 19
March 25, 2021
as presented March 9, 2021
  Projects in the 2022-2025 Highway Program will continue to be programmed with cost and schedule updates
  Investment Area: Stewardship through maintaining a state of good repair
    Maintain increasing Interstate funding levels for pavement reconstruction, modernization, bridges, pavement patching/maintenance, rest areas, and other miscellaneous projects
    Maintain increasing funding levels for non-interstate pavement modernization
    Maintain increasing funding levels for non-interstate bridge modernization
    Maintain funding levels for safety
    Invest in additional stewardship projects
  Investment Area: Modification through rightsizing the system
    Transfer of jurisdiction for portions of primary roadways to cities and counties
  Investment Area: Optimization through improving operational efficiency and resiliency
    Invest in intelligent transportation systems infrastructure
    Invest in Super-2 improvements
  Investment Area: Transformation through increasing mobility and travel choices
    Invest in corridor improvements
Potential FY 2022-2026 Highway Program Objectives

## Slide 20: Next Steps
Develop the Draft 2022-2026 Highway Program
Action Item: 2022-2026 Highway Program Objectives
March 25, 2021