## Security Roles
Role/Title/Assignment | Brief Description | Responsibilities | Masterworks Capabilities | Role/Resource/Field
Scheduler | Role historically performed by Mark Swenson. Creating projects and editing schedule due dates | Create Projects, maintain/edit schedule due dates | Create and edit projects and phases Create and edit schedules Invite Users to Projects Create and Edit Budget Estimates | role/permission level
Scheduler LEB | For NEPA only review projects, LEB admin who can create and edit schedules | For NEPA only: Create Projects, maintain/edit schedule due dates | Create and edit projects and phases Create and edit schedules Invite Users to Projects Create and Edit Budget Estimates | role/permission level
User Manager | Generic Role who can invite users to projects | Assign staff from their offices in roles | Invite Users to Project, Issue Log and Risk Register, Edit Project Phases | role/permission level
Resource Manager | Generic role who can fill in staff as resources to schedule tasks | Assign staff from their offices as resources on schedule tasks | Invite Users to Project, Issue Log and Risk Register, Edit Project Phases, Ability to Add Resources | role/permission level
Project Manager | Overall of project coordinator | Maintain project users Submit complete project budget for programming | Budget Management,Consultant Contract Management, Project Health Report, Edit Project and Phase Locations, Issue Log and Risk Register | role/permission level
District PM | District Project Contact | Coordinate Agreements for District | Edit Schedule | role/permission level
Lead Designer | Generally the person listed in the 'Assigned To' field on the phase form, or someone they may delegate tasks to. | Lock bid items Advance the workflow to "Ready for Contracts" Ensure plan turn in work is completed Approve cost estimate for the phase | Create and edit bid estimates, enter plan items, lock and unlock plan items. Budget management. Edit Road Design Form. Edit Project and Phase Location. Edit Project and Phase Forms. Enter schedule dates. Advance the workflow to "Ready for Contracts" | role/permission level
Designer | Staff who assist the Lead Designer | Can complete duties assigned by the Lead Designer, but cannot mark the project "Ready for Contracts" or put final approval on phase cost estimates | Create and edit bid estimates, enter plan items, lock and unlock plan items. Budget management. Edit Road Design Form. Edit Project and Phase Location. Edit Project and Phase Forms. Enter schedule dates. | role/permission level
Bridge Designer | Staff who assist the Lead Designer for Bridge Projects | For Bridge Projects: Can complete duties assigned by the Lead Designer, but cannot mark the project "Ready for Contracts" or put final approval on phase cost estimates | Create and edit bid estimates, enter plan items, lock and unlock plan items. Budget management. Edit Bridges and Structures Form. Edit Project and Phase Location. Edit Project and Phase Forms. Enter schedule dates. | role/permission level
Clearance Staff | Can fill in clearance information on schedule | Fill in schedule finish dates and clearances for duties | Edit schedule event inclunding clearances | role/permission level
Schedule User | Generic role to complete schedule dates for all projects - such as utility coordinator or ROW staff | Fill in schedule finish dates for their duties | Edit schedule event excluding clearances | role/permission level
Project User |  |  |  | role/permission level
User |  |  |  | role/permission level
Design Number Manager | Staff to Assign and Create Bridge Design Numbers | Staff to Assign and Create Bridge Design Numbers | Edit Bridges and Structures Form, Edit Project and Phase Location | role/permission level
Design Bureau Engineer | Document Approval Workflow |  | Document Mgmt Only | role/permission level
Geotech Engineer | Administer Geotechnical Project Activities | Invite Soils Design Staff to Projects, Review Submittals | Create and edit bid estimates, enter plan items, lock and unlock plan items. Budget management. Edit Road Design Form. Edit Project and Phase Location. Edit Project and Phase Forms. Enter schedule dates. Invite Users to Project | role/permission level
Railroad Office | Representatives from Rail Office | Complete railroad form and fill in schedule finish dates for their duties. | Edit schedule, edit railroad phase form | role/permission level
LEB Admin | Generic Role for email notification |  | Document Mgmt Only | role/permission level
NEPA Admin | Generic Role for email notification |  | Document Mgmt Only | role/permission level
Environment Resource | Role for Phase 2 |  |  | role/permission level
Environment Coordinator | Role for Phase 2 |  |  | role/permission level
Specifications Engineer | Specifications Engineer | Upload and Approve Special Provisions | Document Mgmt & Change Workflow on Specifications | role/permission level
Proposal Manager | Contracts Bureau staff | ??? |  | role/permission level
Proposal Engineer | Contracts Bureau & Rail staff | Estimator Assignment & Resend Phases to Contracts, Apply Apportionment Codes to Phases | Fund Management, Phase Editing, Edit Schedule Details, Assign Resources | role/permission level
Fund Manager | Program Management staff | Project Funding Verification | Fund Management, Create and Edit: Portfolios, Fund Category, & Budget Estimate. | role/permission level
Programmer | Program Management staff | 5-year Program | Create and Edit: 5-year Program, Global Fund List, Portfolios, Program Category Fund, Budget Estimates. | role/permission level
ADE | Assistant District Engineer | Assign staff from their District as resources on schedule tasks and assign staff from their District in roles | Create and edit plan items, budget estimates, edit schedule details, and edit project and phase location. | role/permission level
District Engineer | District Engineer | ??? |  | role/permission level
Central Construction | Central Construction staff members | Fill in RCE Roles & Fill in 435 and 436 dates | Edit construction form | role/permission level
RCE | staff from the RCE office | Fill in dates for "Open to Traffic" | Edit construction form & fill in schedule actual dates | role/permission level
External Consultant Manager | Non-DOT role for company/contract manager | Manage Contract from Consultant Side | Edit schedule, request change orders, create pay estimates, initiate workflow approvals | role/permission level
External Consultant | Assist External Consultant Manager | Assist External Consultant Manager | Edit schedule, request change orders | role/permission level
Consultant Coordinator | Contracting staff in Propject Mangement Bureau | Handle External Contracts from the DOT side | Contract Preparation: Read, edit expenses and PO's,pay estimates, change orders, edit contract items and calendars, create and edit master contracts and work orders. | role/permission level
Consultant Manager - not in use currently | DOT staff who oversee consultant work | Ensure deliverables from consultant contractss are adequate. provide various workflow approvals. | Contract Preparation: Read, edit expenses and PO's,pay estimates, change orders, edit contract items and calendars, create and edit master contracts and work orders. | role/permission level
Contracting Officer Representative | Email Notification | ??? | ??? | role/permission level
Contractor User | Construction contractor staff when MW is used for RFI and change order tracking |  |  | role/permission level
Resource titles are assigned to events in the schedule. The following roles are able to add resource titles to schedule events: project manager, resource manager; scheduler; and proposal engineer. Once a resource title is added to an event allows individuals to be identifed to complete the task. For newly created tasks the scheduler will be assigned the resource title; for migrated projects any of the identified roles should add the resource title when updating who will be assigned to that task. | Associated Events
ROW Agent | R Series |  |  | resource title from schedule form
ROW Designer | R Series |  |  | resource title from schedule form
Surveyor | T Series, D01 |  |  | resource title from schedule form
Inspector | C02 |  |  | resource title from schedule form
Lead Inspector | C02 |  |  | resource title from schedule form
Estimator | L Series |  |  | resource title from schedule form
Construction Supervisor | C02 |  |  | resource title from schedule form
T&E Engineer | TE Series |  |  | resource title from schedule form
Detailer | B Series |  |  | resource title from schedule form
Checker | B Series |  |  | resource title from schedule form
Environment Manager | A0, TE, W, CP, F, H, IJR, N, NE, P, PL, VE Series |  |  | resource title from schedule form
Reviewer | B Series |  |  | resource title from schedule form
Water Resource | W Series |  |  | resource title from schedule form
Geo Technician | S Series |  |  | resource title from schedule form
Final Consultant | B Series |  |  | resource title from schedule form
Designer | AC, D, E, FP, ITS, TD, TCP Series |  |  | resource title from schedule form
Bridge Designer | B Series |  |  | resource title from schedule form
Technician | B Series |  |  | resource title from schedule form
Data Field Assignment |  |  | Form
Project Manager- project form | Project Manager for Project | Making sure Budget Estimates Approved | Projects | data field assignment- project form
District PM- project form | District Contact for Project |  | Projects | data field assignment- project form
Assigned to | Plan Turn in Responsibility (Pulls from Road or Bridge Design) | advance phase to 'Ready for Contracts" | Project Phases | data field assignment- phase form
Road Designer | DOT Staff Lead Designer for non-Bridge work |  | Project Phases | data field assignment- phase form
Bridge Designer | DOT Staff Lead Designer for Bridge work |  | Project Phases | data field assignment- phase form
RCE | RCE Assigned to Phase |  | Project Phases | data field assignment- phase form
RCE Company Name | Auto Fill (Blank for DOT Staff) |  | Project Phases | data field assignment- phase form
Preliminary Section | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Engineer | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Technician | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Final Section | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Designer | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Checker | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Detailer | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Preliminary Bridge Consultant | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Final Bridge Consultant | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Review Plans- Preliminary | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
Review Plans- Final | Bridges & Structures Resources Assigned to Design Number |  | Bridges & Structures Design Number Details | data field assignment- Bridges and Structures form, design number details
3R Coordinator |  |  |  | role/permission level
GIS Admin |  |  |  | role/permission level
ER Admin |  |  |  | role/permission level
P&I Admin |  |  |  | role/permission level
ER Email Group |  |  |  | role/permission level
Integration Admin |  |  |  | role/permission level
Audit Manager |  |  |  | role/permission level
Accounting Manager |  |  |  | role/permission level
Portfolio User |  |  |  | role/permission level
Portfolio Manager |  |  |  | role/permission level
Projectwise Admin |  |  |  | role/permission level
Accountant |  |  |  | role/permission level
Head of Department |  |  |  | role/permission level
ER Admin Team |  |  |  | role/permission level
System Administrator |  |  |  | role/permission level
Administrator |  |  |  | role/permission level
role/permission level

## Sheet1
County:
PIN:
Project Number:
Location:
Type of Work:
Project Directory:
Development Responsibilities
Executive Project Sponsor | Will commission others to deliver the project and will ensure that it is actively reviewed and will negotiate paths through executive areas of the project. Has ultimate authority and responsibility for the project; makes key organizational decisions for the project; assures availability of essential project resources; approves the budget and decides deliverable tolerances;
Project Sponsor | Set target letting date, budget, and scope of the project within the project development and construction phases.
Project Manager | Develop project schedule. Submit budget information for approval. Project Manager will manage and lead the project team, including consultants; monitor allocation of resources for the project and report to functional manager when progress is falling behind; develop, maintain, and communicate a detailed project plan; manage project deliverables in line with the project plan; record, manage, and communicate project risks, issues, and decisions and will escalate when needed; manage project scope; monitor project progress and performance; provide status reports to the Executive Sponsor and team; facilitate lessons learned at project close out; manage change control; the point of contact for ongoing changes, risks, or issues; be the point of contact for FHWA during program development activities
Functional Managers | Will ensure technical teams are available to deliver the project and continued support; including requesting consultant services. Sponsor will oversee assignments of technical resources; ensure utilization of technical best practices across Iowa DOT, other government agencies, and 3rd party vendors; ensures resolutions of risks and issues are escalated by project team. | ,
PMT Member | Participate in PMT meetings and point out possible conflicts. Review consultant designs and make design suggestions.
Technical Lead | Responsible for design work in their area of expertise. Coordinates with team members in their area and other technical leads as necessary to complete the project. Develops options do address stakeholder or funding needs. Explains design features to the team. Writes design exceptions when needed. Completes annual project estimates.
Team Member | Responsible for developing project documents
Location Engineer
Office Responsibilities
Road Design | Resposible for the preliminary/final roadway design. Develops options do address stakeholder or funding needs. Explains design features to the team. Writes design exceptions when needed. Completes annual project estimates. (more detail needed?)
Bridge Design | Resposible for the preliminary/final bridge and drainage design. Completes annual project estimates.
Geotechnical Design | Responsible for geotechnical exploration, reports, coordination with bridge and roadway designers.
OLE | Coordinate all OLE staff during OLE phase. Ensure permits are aquired and NEPA laws are followed and documented.
Location Engineer
Environmental Permitting
NEPA
Regulated Materials
Rail Coordinator | Responsible for all railroad negotiations and agreements.
Traffic Ops | The Office of Traffic Operations, working with the project team, is responsible for the Program Intelligent Transportation System (ITS) needs during construction, including Intelligent Work Zone needs, and for the ultimate build. Completes annual project estimates.
Transportation Management Plan Developer | Writes and updates TMP.
Financial Plan Developer | Writes and updates financial plan.
Traffic and Safety | Responsible for the design of signing, signals and lighting for the program. They also review consultant plans and operational issues for the Program. Participate in PMTs and point out possible conflicts between disciplines. Completes annual project estimates.
Traffic Engineer
Signing
Lighting
Transportation Management Plan | Review and advise on TMP
Utility Relocation | responsible for coordinating with Utility companies along the program corridor and writing utility agreements associated with the program.
Office of Right-of-Way | Responsible for all ROW design, appraisal, acquisition, relocation, deeds and property management for the program. Completes annual ROW estimates.
Lead designer
Consultant Coordinator
District Office | Responsible for all activities related to existing ROW survey, agreements with local agencies, and managing construction activities; including requesting consultant services. District duties also include public information/education and media outreach. Work with Design and Contracts to establish working days, sites, incentives/disincentives, Special Provisions, and other contract related controls,
Assistant District Engineer
Construction Engineer
Transportation Planner
Staff Engineer
Survey
Office of Contracts | Responsible for the engineers estimate and contract letting
Contracts Engineer
PMT Member
FHWA | See PODI or POCI plan.

## Sheet2
Project Management Functions Matrix
September 13, 2016 DRAFT
Abbreviations: | [7 empty] | PMO develop Plan for each project on how to approach that project
PMO =Project Management Office | [7 empty] | based on District, technical needs, staffing….
District = District Office
FO = Functional Office, as applicable (Location and Environment, Design, Bridge, or Right of Way)
X = Duty performed by the designated office
No. | Function | Major Projects |  |  | Other Projects |  |  | Notes
|  | PMO | District | FO | PMO | District | FO
1 | Point of Contact
1.a | Respond to questions and requests for information from consultants and other offices. | X |  | X |  | X | X | Copy PM (PMO or District) to coordinate and track.
1.b | Respond to requests for information or questions from the general public (coordinate with PMO and FOs as needed) |  | X |  |  | X
2 | Coordinate Information Flow
2.a | Establish PMT membership. | X |  |  |  | X
2.b | Monitor action items or issues established at meetings. | X |  |  |  | X
2.c | Schedule and chair PMT and other project meetings | X |  |  |  | X
2.d | Obtain or provide traffic, crash data, as-builts, aerial photography, survey, location & environmental information and documents. |  |  | X |  |  | X
3 | Resolve Project Issues
3.a | Work with consultant and other offices to resolve issues regarding design criteria, right of way, traffic control, lighting, soils, etc. | X |  |  |  | X
4 | Schedule and Budget
4.a | Coordinate and review development of project schedule | X |  |  | X
4.b | Coordinate and review development of project budget | X |  |  | X
4.c | Prepare cost estimates and / or review estimates prepared by consultants |  |  | X |  |  | X
4.d | Coordinate the approval of any changes to schedule or budget | X |  |  |  | X
4.e | Work with consultant and / or other offices to ensure events are completed on time. | X |  |  |  | X
4.f | Ensure events are cleared in PSS |  |  | X |  |  | X
4.g | Monitor the progress of technical reviews (delete this item? same as consultant reviews below?) | X |  |  |  | X |  | Part of 4.e. and staged submittals and reviews.
5 | Consultant Administration and Oversight
5.a | Plan, coordinate, and monitor the requests for consultant services | X |  |  |  | X
5.b | Develop scope of services. |  |  | X |  |  | X | In coordination with PMO or District
5.c | Establish schedule for consultant deliverables. | X |  |  |  | X
5.d | Manage the consultant procurement process | X |  |  |  | X
5.e | Administer consultant contracts (prepare and execute contracts, pay invoices, monitor schedule and progress reports, contract cost, review scope changes) | X
5.f | Monitor consultant performance and adherence to scope of services |  |  | X |  |  | X
5.g | Coordinate and consolidate review comments from other offices on consultant work products. | X
5.h | Provide technical review of consultant work products. |  | X | X |  | X | X
5.i | Coordinate and monitor consultant evaluations | X |  |  |  | X
5.j | Complete consultant evaluations |  | X | X |  | X | X
6 | Establish and Ensure Documentation of Design Criteria
6.a | Distribute draft design criteria to others for review and comment. |  |  | X |  | X
6.b | Ensure all design exceptions are prepared, submitted and reviewed in accordance with Section 1C-08 of the Design Manual. |  |  | X |  | X
7 | Coordinate Public Hearing Displays
7.a | Work with the various offices to develop the displays for the Public Hearings and Public Information meetings. |  |  | X |  |  | X
7.b | Coordinate the response to questions, concerns, comments and inquiries that arise from the meetings. | X |  |  |  | X
8 | Post Plan Turn-in Activities
| Review proposed addenda, plan revisions |  | X | X |  | X | X
| Provide Office of Contracts with responses to questions submitted during the bid advertisement period (coordinate with District or FO as needed) | X |  |  |  | X

## Sheet3
Improve clarity about roles and responsibilities among all offices
Action plan:
1. Create a comprehensive list of project development duties
a. Use HDR’s MS Project list as a starting point
b. Meeting with Shane Tymkowicz and Brad Hofer - 6/9/17
i. add tasks to the list
ii. develop a list of roles (designer, design PMT rep, etc)
iii. fill in draft assignments
c. To help people review it, break the draft list into 2 formats (Wade Bartz)
i. Chronological list of all duties
ii. Chronological list for each person with “receive from” and “provide to” columns
d. Send the list to office directors for review/comment/thought and ask them to recommend front line staff for meetings
e. Hold a series of meetings with front line staff to correct/complete/detail the list.
2. Publish the list of roles and responsibilities
3. For each project (or group such as 3R in a district), have the PMT discuss/list the appropriate person for each of the roles
4. Find a way to record this data in PSS or a similar system.